## Total Count
SALES
| Total Count | To Discuss | Not Started | In Progress | In Staging | In Demo | Approval | Live | Completed | On Hold
Tasks | 169 | 4 | 4 | 4 | 0 | 0 | 1 | 2 | 143 | 0
Issues | 974 | 3 | 73 | 6 | 2 | 3 | 6 | 8 | 775 | 2
Suggestion | 137 | 1 | 10 | 2 | 0 | 0 | 3 | 0 | 102 | 1
Need to Discuss | 26 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 10 | 1
|  |  | Tasks Assigned | Not Started | In Progress | In Staging | In Demo | Live | Completed
|  | Rijo | 257 | 18 | 1 | 0 | 1 | 2 | 186
|  | Sandeep | 353 | 31 | 7 | 0 | 1 | 3 | 276
|  | Satheesh | 27 | 8 | 1 | 0 | 0 | 0 | 11
|  | Sharan | 500 | 33 | 1 | 2 | 2 | 5 | 405
|  | Not Assigned | 41 | 11 | 0 | 0 | 0 | 0 | 7
LETTINGS
| Total Count | To Discuss | Not Started | In Progress | In Staging | In Demo | Approval | Live | Completed
Tasks
Issues
Suggestion
Need to Discuss
|  |  | Tasks Assigned | Not Started | In Progress | In Staging | In Demo | Live | Completed
Rijo
Sandeep
Satheesh
Sharan
Not Assigned
LETSBID
Sales
Category | Total Count | Completed | Discuss | In Progress | Not Started | UI | Web | Data/AI
Task / Enhancement | 181 | 156 | 8 | 3 | 13 | 0 | 12 | 1
Issue | 894 | 824 | 6 | 10 | 75 | 1 | 60 | 14
Suggestion / Discuss | 160 | 135 | 4 | 2 | 12 | 4 | 7 | 1
Demo | 44 | 35 | 0 | 1 | 8 | 2 | 6 | 0
UK Team | 35 | 16 | 9 | 2 | 9 | 1 | 7 | 1
Lettings
Category | Total Count | Completed | Discuss | In Progress | Not Started | UI | Web | Data/AI
Task / Enhancement | 81 | 68 | 0 | 1 | 10 | 1 | 9 | 0
Issue | 401 | 359 | 0 | 3 | 24 | 0 | 18 | 6
Suggestion / Discuss | 41 | 32 | 2 | 0 | 3 | 0 | 3 | 0
Demo | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UK Team | 15 | 8 | 3 | 1 | 3 | 0 | 3 | 0
Task went Live : 19
Last week went Live : 9
Approval in sales-10
Test demo sales-4
Test demo lettings-7
Approval lettings-1

## Sales - TasksIssue Tracker
| Reported Date | Task Type | Module | Description | Team | Assignee | Status | Priority | Tester | Expected Duration | Start Date | End Date | Live Date | Comments | Branch Name
1 | 2023-04-25 | ISSUE | Listing Page | if we select all the listings in a page by clicking on the select all button, all the 3 toggle buttons are enabled and also all the postcodes are selected |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-04-28 | 2023-05-01 |  | Transfered from abhijith, Tested in staging
2 | 2023-04-25 | ISSUE | Listing Page | after selecting all the listings in a page by clicking on the select all button if the user unselects all the listing by clicking on it again or after adding it to the campaign the listings are still selected |  | SANDEEP | COMPLETED | HIGH | [5 empty] | please check Targeted, withdrawn, price drop, back to market and sold-under offer the selections are not cleared when we add properties to campaign
3 |  | ISSUE | Wallet/Credit | the credits shown in the credits column and wallet section is different |  | RISHIKA | COMPLETED | HIGH
4 | 2023-04-20 | ISSUE | Detail Page | no comparables are shown in the property detail page but while generating reports there are comparables properties eg: 116, Church Road, Birmingham, West Midlands, B13 9AA |  | RISHIKA | COMPLETED | HIGH | [5 empty] | Property details required by rishika
5 |  | ISSUE | Admin | cannot add amount with decimal in ADMIN TOPUP (eg: £16.50 is not possible, only 16, 17 like that) |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-04-14 | 2023-04-17
6 | 2023-04-17 | TASK | Letter management | arthur grace letterhead correction (enquiries@arthurgraceresidential.com) |  | VIPIN | COMPLETED | HIGH | [5 empty] | Sandeep, Sateesh - completed dev,
7 | 2023-04-24 | ISSUE | Probate properties | in executor detail section, instead of some characters ? is shown |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-04-26 | 2023-04-27 |  | Detail testing needed . ? character is provided from the gazatted api itself, sorted in live db
8 | 2023-04-27 | ISSUE | Properties | after unselecting the properties, when we get back from other pages.still shows it as selected |  | MEERA | COMPLETED | HIGH | [5 empty] | Need to test in other browsers , dev- sandeep
9 | 2023-04-17 | SUGGESTION | Report | SELECT/UNSELECT ALL in popup window, if there is more comparables its difficult to unselect one by one |  | VIPIN | COMPLETED | LOW | [5 empty] | Only 10 property will be visible in the comparable popup
10 |  | SUGGESTION | Detail Page | targeted and probate boxes can be rearranged |  | MEERA | COMPLETED | MEDIUM
11 |  | SUGGESTION | Report | make company logo and agent photo smaller and show on top make primary image larger |  | MEERA | COMPLETED | MEDIUM
12 |  | ISSUE | 20-20 Campaign | 20/20 isn't picking up neighbouring properties |  | SHARAN | COMPLETED | URGENT |  |  | 2023-04-27 | 2023-04-28 |  | I found that some properties are not taking 20 properties either side. so i prefer a notification to let the user know that the particular property doesn't have 40 properties before confirming to send it
13 |  | ISSUE | Live campaign | when we print locally or send bulk mail for more than 200 address together, there is an issue over here |  | RISHIKA | COMPLETED | URGENT |  |  | 2023-04-25 | 2023-04-26 |  | Dependency - only we can test after the checkbox issue in all properties section Sandeep
14 | 2023-04-27 | ISSUE | Probate properties | outcode filter gets cleared when we return to the listing page |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-04-28 | 2023-05-01
15 |  | ISSUE | Bulk Mail | Auto refresh to remove property is not working after bulk mail is sent the addresses are not removed from the campaign, user has to manually refresh the page |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-05-12 | 2023-05-16 |  | 20-20 campaign - when sending bulk mail to multiple addresses, only the first address is disabled in the campaign listing addresses are removed only when page is refreshed targeted campaign - when bulk mails are sent, the addresses are removed only when the page is refreshed probate campaign - if we remove the property address and send letters, the address remains in the campaign listing comment updated on 17/05/2023: 20-20 campaign has some issues (tested in staging)
16 |  | SUGGESTION | Anniversary Letter | if the agent has not added a letterhead and they try to preview or local print the letter it just opens a new tab and returns to anniversary letter page please show a message |  | RIJO | COMPLETED | LOW | [5 empty] | updated Aug 2: shows server error when we try to local print without uploading a letterhead | no16_check_letterhead_before_preview_Rijo_27July2023
17 |  | ISSUE | Dashboard | Subscribed outcodes showing duplicate outcodes |  | RIJO | COMPLETED | URGENT |  |  | 2023-05-04 | 2023-05-09 |  | was assigned to Ashik, reassigned to Rijo
18 |  | ISSUE | Report | When removing an image on the reports that clearly isn't a correct google image of the property, the report is still producing the wrong image and looks terrible. |  | RIJO | COMPLETED | URGENT |  |  | 2023-05-03 | 2023-05-03 |  | option to remove satelite image and center the map on first page of report ------------- need to confirm the wordings requires design change
19 | 2023-04-20 | ISSUE | Report | Uploading image issue (if we rotate it by ourself as height to width) |  | SHARAN | CLOSED | LOW
20 | 2023-04-25 | ISSUE | Price Drop | price drop column is blank for some addresses |  | RIJO | COMPLETED | URGENT | [5 empty] | dev assigned - Abhijith
21 | 2023-04-27 | ISSUE | Detail Page | Latest listed activity details are not updated (https://prospectingtool.letsbidproperty.co.uk/properties/p-343122) |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-05-24 | 2023-05-25 |  |  | 21-listing-activity
22 | 2023-04-28 | ISSUE | Live campaign | stannp address issue - special characters |  | SANDEEP | CLOSED | URGENT | [5 empty] | contacting Stannp comment updated 15/05/2023 - looking for solution from stannp side
23 | 2023-04-28 | ISSUE | Campaign History | targeted campaign history - getting a warning pop up when we view the campaign |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-05-01 | 2023-05-01 |  | Sandeep
24 | 2023-04-28 | ISSUE | Listing Page | few addresses with no property type and bedroom count https://prospectingtool.letsbidproperty.co.uk/properties/w-1281501 https://prospectingtool.letsbidproperty.co.uk/properties/b-486460 |  | RIJO | COMPLETED | HIGH | [5 empty] | not getting type and count from rightmove or zoopla
25 |  | ISSUE | Properties | Address - all selecting option issue |  | SANDEEP | COMPLETED | LOW |  |  | 2023-05-01 | 2023-05-03 |  | not correct in withdrawn, price drop, back to market, sold-under offer
26 |  | ISSUE | Dashboard | Quick send- print letters are working before selecting this double checked button ( I have double checked the letter generation using the print preview option) , need to check letter head available ( also in live campaign check ) |  | ANISHA | COMPLETED | LOW | [6 empty] | no-26-dashboard-quicksend-doublecheckissue-anisha6June2023
27 |  | SUGGESTION | Letter management | Already selected trigger can be improved |  | MEERA | COMPLETED | LOW | [5 empty] | Abhay task
28 |  | SUGGESTION | Outcodes | wrong message while adding already added outcode |  | ABHIJITH | COMPLETED | LOW
29 |  | SUGGESTION | Live campaign | its confused while clicking PDF PREVIEW, Two button clicks required |  | ANISHA | COMPLETED | LOW | [5 empty] | Sharan - Passed to Sandeep ----- transferred to Anisha on june 9 -------- comment updated on june 16: instead of edit address it's showing Edit Anniversary Letter pop up | no-29-livecampaign-pdfpreview-anisha9June2023
30 |  | SUGGESTION | Targeted Properties | after export the date format is not in correct order |  | ANISHA | COMPLETED | LOW
31 | 2023-04-15 | SUGGESTION | Withdrawn | Withdrawn , Back to market, price drop - move add to campaign to the very right end |  | ANISHA | COMPLETED | LOW |  |  | 2023-05-29 | 2023-05-29 |  |  | no31-withdrawnbackmarketpricedrop-add_to_campaign-rightend-anisha-29may2023
32 | 2023-04-15 | SUGGESTION | General | In letter management make the Name column bold |  | MEERA | COMPLETED | LOW |  |  | 2023-04-28 | 2023-05-01 |  | Abhay - passed to Rijo
33 | 2023-04-15 | SUGGESTION | General | The four section colour rethink |  | UNASSIGNED | CLOSED | LOW | [5 empty] | Discussion pending
34 | 2023-04-15 | SUGGESTION | General | Tool tip for each section |  | UNASSIGNED | CLOSED | LOW | [5 empty] | Content needed
35 | 2023-04-28 | ISSUE | Wallet/Credit | shows a blank page when we click on the download invoice button for Admin top up |  | ANISHA | COMPLETED | URGENT |  |  | 2023-05-25 | 2023-05-25 |  |  | no35-invoicedownload-admintopup-anisha-25may2023
36 | 2023-04-28 | ISSUE | Wallet/Credit | download invoice- Â shown before the pound symbol in the the page title and the payment title |  | ANISHA | COMPLETED | LOW |  |  | 2023-05-31 | 2023-05-31 |  |  | no36-invoice-invalidcharacter-anisha2june2023
37 |  | SUGGESTION | Website | can be better, compared to our competitors- next meeting discussion |  | ABHAY | COMPLETED | MEDIUM | [5 empty] | On hold, after all fixes
38 | 2023-04-17 | TASK | Static Data | Static data updation population (received data for 2021 against councils) |  | SHARAN | COMPLETED | URGENT |  | 3 days |  |  |  | Aug 8: gp, tram - live population, bus station - pending ------------------- Aug 10: bus station - in progress | NHS_Data_Collection_Sharan-N-P
39 | 2023-04-19 | SUGGESTION | Letter management | Select Trigger popup should be improved |  | ABHAY | COMPLETED | MEDIUM
40 | 2023-04-24 | ISSUE | Detail Page | in the listing activity section, withdrawn activity is repeating multiple times |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-05-04 | 2023-05-05
41 | 2023-04-25 | TASK | Detail Page | highlight listings that are still on the market in List of estate agents section |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-05-15 | 2023-05-15
42 | 2023-04-18 | TASK | Exclude Agent | Branch id update notification from exclude my agent |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-02 | 2023-05-03 |  | pop-up cant be close until its added the id's , Pop is not showing in the all properties section
43 | 2023-04-26 | TASK | Letter management | Preview when images are added breaks the page design |  | ASHIK | COMPLETED | MEDIUM |  |  | 2023-05-17 | 2023-05-18 |  | problem in merging to live - need triage | no43_letter_image_compress_31_05_2023_ack
44 | 2023-04-26 | TASK | Letter management | added images needs to be moved and placed in the correct place - option to drag images |  | ASHIK | COMPLETED | MEDIUM |  |  | 2023-05-18 | 2023-05-25 |  | 3 July - dupliaction of dragged images | no254_image_align_center_19_06_2023_ack
45 | 2023-04-27 | ISSUE | Probate properties | when clicking back button from detail page the selection is not there in all listing page |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-05-02 | 2023-05-03 |  | code delivered by abhijith to sandeep, This same issue was cleared by abhijith in all properties section
46 | 2023-04-28 | SUGGESTION | 20-20 Campaign | Give a notification in the 20-20 listed pop-up, if it doesn't have 40 properties to send campaign |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-16 | 2023-05-16
47 | 2023-04-28 | ISSUE | Withdrawn | listings without address is shown LS16 8EG OL2 6LU LS16 7DF RM13 7BU |  | RIJO | COMPLETED | HIGH |  |  | 4 mat | 2023-05-04 |  | Rijo dev
48 | 2023-04-28 | ISSUE | Withdrawn | spelling error in Withdrawn Date column |  | RISHIKA | COMPLETED | MEDIUM |  |  | 2023-05-02 | 2023-05-02
49 | 2023-04-28 | ISSUE | Live campaign | when we select all address the select trigger for all does not get cleared if user had previously selected any trigger, user will have to select the default option or choose another trigger to reset |  | ANISHA | COMPLETED | HIGH |  |  | 2023-05-24 | 2023-05-24 |  |  | no49-livecampaign-select-triggerall-clear-select-all-anisha-24may2023
50 |  | ISSUE | Dashboard | banner LETSBID word is going out of the box |  | ABHAY | COMPLETED | HIGH |  |  | 2023-04-13 | 2023-04-14 |  | Abhay
51 |  | TASK | AML | AML API work |  | NIKHILA | COMPLETED | HIGH |  |  | 2023-04-13 |  |  | testing links and credentials provided for AML testing task added to Auction sheet
52 |  | SUGGESTION | Anniversary Letter | received details is in tool tip which seems not good to me |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-04-24 |  |  | Complication in opening modal within modal - Rijo dev
53 |  | SUGGESTION | Anniversary Letter | if send history is single for each record then the pop up does not need other fancy stuffs like page number / hide column , etc |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-04-24 |  |  | Complication in opening modal within modal - Rijo dev
54 | 2023-04-15 | SUGGESTION | General | rearrangement in sections take campaignlive, history to bottom and listings section like withdrawn , price drop etc near the all properties |  | RISHIKA | COMPLETED | LOW |  |  | 2023-04-28 | 2023-05-01 |  | Abhay - passed to Rijo
55 | 2023-04-15 | SUGGESTION | General | In Pages instead of title Withdrawn need Withdrawn properties , etc. similar in all pages |  | RISHIKA | COMPLETED | LOW |  |  | 2023-04-28 | 2023-05-01 |  | Abhay - passed to Rijo
56 |  | ISSUE | Probate properties | loading issue, default image |  | ABHAY | COMPLETED | MEDIUM |  |  | 2023-04-14 | 2023-04-14 |  | Sandeep - passed on to Abhay
57 |  | SUGGESTION | Dashboard | banner image words adjustment |  | ABHAY | COMPLETED | MEDIUM |  |  | 2023-04-13 | 2023-04-14 |  | Abhay
58 |  | SUGGESTION | Outcodes | the last requested outcode should come first in the list |  | NIKHILA | COMPLETED | MEDIUM |  |  | 2023-04-14 | 2023-04-14
59 | 2023-04-28 | SUGGESTION | General | convert all pop ups uniform and central readable (instead of square popups we need rectangular pop ups which will make the message look shorter) |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-06-13 |  |  | updated jul 25: 1. probate detail page - delete message for comment is still the old format 2. bulk mail success message is still the old format 3. 20-20 campaign - when removing addresses from the campaign, the addresses are removed before clicking on Confirm button 4. letterhead upload success message closes before clicking on confirm ------------------------------ updated jul 28: 1. warning pop up shown if we dont check the print preview option is in old format - quick send in dashboard and quick send in detail page
60 | 2023-04-25 | TASK | Report | report UI should show property type and square feet if found, if not found show pop up to make them add manually this in the report generation section |  | SHARAN | COMPLETED | URGENT |  |  | 2023-04-28 | 2023-05-02 |  | developer assigned: Sharan change wording in thhe pop up: You have the option to add sqft and property type to get comparable properties if we can't identify the actual data.
61 | 2023-04-26 | TASK | Exclude Agent | Add suggestion option for adding agent id from edit profile |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-05 | 2023-05-10
62 | 2023-04-28 | ISSUE | Live campaign | probate campaign - no preview is shown if we remove the property address of the first address, when sending letters to multiple addresses |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | couldnt reproduce the issue
63 | 2023-04-17 | ISSUE | Properties | in rightmove/zoopla it says 5 bedroom but in our system it is 4 bedroom in listing page and 5 bedroom in detail page (16, Busby Place, London, NW5 2SR ) |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-18 |  | Done by Abhijith
64 | 2023-04-17 | ISSUE | Properties | Some properties without house/flat no: are listed in ALL PROPERTY listings (Howitt Road, London, NW3 4LL, - Wendover road, NW10) |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-18 |  | Done by Abhijith
65 | 2023-04-17 | ISSUE | Properties | there is a flat marketed at 435k but when clicks onto it it is a 5 bed semi marketed for 935k (- Wendover road, NW10) |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-18 |  | Done by Abhijith
66 | 2023-04-18 | ISSUE | Listing Page | when we enable both Company owned and exclusive Listing filter, issue in listing the property |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-18 |  | Tested in staging by Meera, dev- Abhijith
67 | 2023-04-18 | ISSUE | Campaign History | when we try to get back from the campaign history detail page it redirects to the property detail page again |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-05-12 | 2023-05-23 |  | reopened on May 15 please check probate campaign history, when we click on back button it redirects to the property detail page itself comment updated on 16/05/2023 - when we click on the back button from probate campaign history page, please redirect to the probate campaig history abhijith@designdirect.io | campaign-back2
68 | 2023-04-17 | ISSUE | Properties | when clicking back button from detail page the selection is not there in all listing page |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-20 |  | Tested in staging by Meera, dev- Abhijith
69 |  | ISSUE | Properties | actual property is listed in comparable list for probate (3 Hawbush Green, Braintree, CM77 8NY) |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-25 | 2023-04-26 |  | Tested in staging
70 | 2023-04-24 | ISSUE | Report | comparables pop up - user can close the pop up by clicking outside the pop up, if they deselect any property and close by clicking outside in the generated report the property which they removed will be shown |  | MEERA | COMPLETED | [6 empty] | Tested in staging
71 |  | SUGGESTION | Probate properties | cannot select multiple outcode in probate |  | MEERA | COMPLETED | MEDIUM |  |  | 2023-04-17 | 2023-04-19 |  | dev by sandeep
72 |  | SUGGESTION | Live campaign | There is no pop-up, even if doesn't select the trigger in more than a selected option |  | MEERA | COMPLETED | LOW |  |  | 2023-04-19 | 2023-04-20 |  | Tested in staging by Meera, dev- sandeep
73 |  | ISSUE | Targeted Properties | Print preview - Trigger naming issue |  | MEERA | COMPLETED | MEDIUM |  |  | 2023-04-20 | 2023-04-20 |  | Dev- Sandeep
74 | 2023-04-20 | ISSUE | Campaign History | Campaign history status failed issue (Mark Flint acnt) |  | RIJO | COMPLETED | HIGH |  |  | 2023-04-20 | 2023-04-24 |  | Tested in staging by meera
75 | 2023-04-20 | ISSUE | Live campaign | when we select all address option, preselected trigger should be cleared |  | MEERA | COMPLETED | LOW |  |  | 2023-04-20 | 2023-04-20 |  | Dev- Sandeep
76 |  | ISSUE | Back to Market | properties missing |  | ABHIJITH | COMPLETED
77 |  | ISSUE | Live campaign | Targeted campaign - if we are sending letters to multiple addresses, the preview is not shown if the first address is removed |  | SANDEEP | COMPLETED | HIGH
78 |  | ISSUE | Campaign History | 20-20 bulk campaign history - shows letter status and letter not available |  | SANDEEP | COMPLETED | HIGH
79 |  | ISSUE | Campaign History | in second instruction marketing tab please make the first letter capital |  | SANDEEP | COMPLETED | HIGH
80 |  | ISSUE | Campaign History | 20-20 campaign history - even if we remove few neighbouring addresses, in the campaign history all the addresses are shown |  | SANDEEP | COMPLETED | HIGH
81 |  | ISSUE | Campaign History | from campaign history detail page when clicked on the address the detail page appears, but the back is not taking to campaign but instead is taking to all properties |  | ABHIJITH | COMPLETED | URGENT
82 |  | ISSUE | Dashboard | 16 weeks or more count not correct, it includes 143rd day |  | ASHIK | COMPLETED
83 |  | ISSUE | Dashboard | showing an error page |  | JISHNU | COMPLETED
84 |  | ISSUE | Wallet/Credit | download invoice- please show the correct logo |  | NIKHILA | COMPLETED | HIGH
85 |  | ISSUE | Wallet/Credit | download invoice- Â shown before the pound symbol, footer and title |  | NIKHILA | COMPLETED | HIGH
86 |  | ISSUE | Export csv | export csv is not working |  | NIKHILA | COMPLETED
87 |  | ISSUE | Properties | properties missing in the listing when we filter by weeks |  | ABHIJITH | COMPLETED | HIGH
88 |  | ISSUE | Header | when we click on auction it redirects to the estate agent login page |  | RIJO | COMPLETED | HIGH
89 |  | ISSUE | Admin | outcode attcept should check whether the user has already requested for the same outcode |  | NIKHILA | COMPLETED | HIGH
90 |  | ISSUE | Dashboard | summary data is not correct |  | RIJO | COMPLETED | HIGH
91 |  | ISSUE | Outcodes | Outcodes not in our db in Outcodes section needs a message saying , on request this Outcodes will be processed |  | NIKHILA | COMPLETED | URGENT
92 |  | ISSUE | Price Drop | Price drop listing: add - £ in front of price drop |  | ABHIJITH | COMPLETED
93 |  | ISSUE | Price Drop | Price Drop field is showing blank |  | Jinto | COMPLETED
94 |  | ISSUE | Probate properties | remove the unwanted highlighting in the listings, when we click somewhere near the address that row is highlighted |  | SANDEEP | COMPLETED
95 |  | ISSUE | Probate properties | page takes some time to load |  | SANDEEP | COMPLETED | HIGH
96 |  | ISSUE | Properties | check in campagin tag recheck |  | ABHIJITH | COMPLETED | URGENT
97 |  | ISSUE | Properties | Agent Zoopla / Rightmove pop up data missing |  | ABHIJITH | COMPLETED
98 |  | ISSUE | Properties | if we click on R/Z icon below Platform and then click onm the List of Estate Agents button, it shows only either R or Z agents |  | ABHIJITH | COMPLETED
99 |  | ISSUE | Properties | wrong listing type for properties that are for sale the listing type is given as Withdrawn https://prospectingtool.letsbidproperty.co.uk/properties/p-1001870 https://prospectingtool.letsbidproperty.co.uk/properties/p-1002095 https://prospectingtool.letsbidproperty.co.uk/properties/p-1001871 |  | ABHIJITH | COMPLETED
100 |  | ISSUE | Properties | the campaign is shown in the detail page of the removed property |  | ABHIJITH | COMPLETED | HIGH
101 |  | ISSUE | Properties | when we click on Confirm and send or preview the letter and cancel without sending it, in the detail page of the property a campaign with Sending status is created |  | ABHIJITH | COMPLETED | HIGH
102 |  | ISSUE | Properties | hide column upper thin box needs to be removed |  | ABHIJITH | COMPLETED | URGENT
103 |  | ISSUE | Properties | the status changes to Letter Sent when we select the property but remove it before sending (select few properties in the campaign -> remove a property and send the rest -> check the status in listing and detail page of the property which was removed) |  | ABHIJITH | COMPLETED | HIGH
104 |  | ISSUE | Properties | remove the unwanted highlighting in the listings, when we click somewhere near the address that row is highlighted |  | SANDEEP | COMPLETED
105 |  | ISSUE | Recent Valuation | recent valuation - Please hide it |  | NIKHILA | COMPLETED | URGENT
106 |  | ISSUE | Targeted Properties | remove the unwanted highlighting in the listings, when we click somewhere near the address that row is highlighted |  | SANDEEP | COMPLETED | HIGH
107 |  | ISSUE | Targeted Properties | the campaign is shown in the detail page of the removed property |  | ABHIJITH | COMPLETED | HIGH
108 |  | ISSUE | Properties | Detail page- Latest agent listed price is not showing |  | ABHIJITH | COMPLETED
109 |  | SUGGESTION | General | make every name , title, address (the main column) bold |  | ABHIJITH | COMPLETED | HIGH
110 |  | SUGGESTION | Anniversary Letter | In create anniversary letter pop up, add space between the create button and trigger field |  | RIJO | COMPLETED
111 |  | SUGGESTION | Live campaign | 20-20 campaign - if agents select multiple triggers, there is no space between the preview buttons |  | SANDEEP | COMPLETED | MEDIUM
112 |  | SUGGESTION | Dashboard | add Outcodes button and Outcodes looks same |  | ABHIJITH | COMPLETED | HIGH
113 |  | SUGGESTION | Detail Page | comparable need to keep open |  | ABHIJITH | COMPLETED | HIGH
114 |  | SUGGESTION | Loader | Keep only one loader |  | ABHIJITH | COMPLETED
115 |  | SUGGESTION | Properties | we need to give z and r icon in detail page as modal |  | ABHIJITH | COMPLETED
116 |  | SUGGESTION | Properties | clear filter move to a corner |  | ABHIJITH | COMPLETED
117 |  | SUGGESTION | Report | View History report button on dashboard and report page should open up the report historty table |  | SHARAN | COMPLETED | HIGH
118 |  | SUGGESTION | Report | in property estimate section, please add the text 'Or' in between bothe the textboxes |  | SHARAN | COMPLETED
119 |  | SUGGESTION | Report | if the address from detail page after clicking generate report button is not valid from getaddress show message to edit address |  | SHARAN | COMPLETED | HIGH
120 |  | SUGGESTION | Report | report address from detail page not in get address suggestion needs a message to edit address / all address needs to go through get address |  | SHARAN | COMPLETED | HIGH
121 |  | SUGGESTION | Targeted Properties | Postcode in one line for targeted page |  | SHARAN | COMPLETED | HIGH
122 |  | SUGGESTION | Live campaign | Sending bulk mail pop up- remove exclaimation mark |  | SANDEEP | COMPLETED
123 |  | SUGGESTION | Campaign history | Status- change sent in the locally printed campaigns |  | SANDEEP | COMPLETED
124 |  |  | Probate properties | needs space from exclude care homes in probate and export csv in next line as a common format |  | ABHIJITH | COMPLETED | HIGH
125 |  | ISSUE | Campaign History | Name- sort button is not working |  | MEERA | COMPLETED | LOW |  |  | 2023-04-14 | 2023-04-18 |  | Testing done in demo,
126 | 2023-04-18 | ISSUE | Listing Page | only getting exclusive tag without address in property listing page |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-18
127 | 2023-04-18 | ISSUE | Campaign History | Full address is not showing in the campaign history detail page |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-18 | 2023-04-19 |  | Tested in Live
128 |  | TASK | Report | We have to make comparable selected before generating report |  | MEERA | COMPLETED | URGENT |  |  | 2023-04-13 | 2023-04-14 |  | Tested in live
129 |  | ISSUE | Probate properties | CLEAR FILTER not working in PROBATE |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-17 | 2023-04-17 |  | Tested in live
130 |  | SUGGESTION | Properties | If we are in a PROPERTY DETAIL page, we dont know where we are so please HIGHLIGHT the section on the left pane. |  | MEERA | COMPLETED | LOW |  |  | 2023-04-17 | 2023-04-18 |  | Tested in live, please check in campaign history detail page
131 |  | SUGGESTION | Properties | Your comments- Add a question before deleting the comment |  | MEERA | COMPLETED | LOW |  |  | 2023-04-18 | 2023-04-18 |  | Abhijith - completed the dev work ¦ approved, Tested in Live - Popup can be improved
132 |  | SUGGESTION | Withdrawn | withdrawn loading looks little odd to me |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-13 | 2023-04-13 |  | Tested in live
133 |  | ISSUE | Targeted Properties | add to campaign - when we add a property to add to campaign, twice the popup is bringing up |  | MEERA | COMPLETED | MEDIUM |  |  | 2023-04-18 | 2023-04-18 |  | Tested in live
134 | 2023-04-19 | TASK | Report | untick these in buyers report- Market info,soldprices, broadband, crime rate, population, carbon foot |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-19 | 2023-04-20
135 | 2023-04-20 | ISSUE | Report | In the last page address is overlapping hover the content |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-20 | 2023-04-21
136 |  | ISSUE | Live campaign | Letter generation completed- Qr code- change valid number into enter valid number |  | MEERA | COMPLETED | LOW |  |  | 2023-04-20 | 2023-04-20
137 | 2023-04-19 | SUGGESTION | Report | add a comparables pop up before submitting and they can untick what they want before the report generates in sellers report |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-19 | 2023-04-20
138 |  | ISSUE | Report | image is strected in report |  | MEERA | COMPLETED | URGENT |  |  | 2023-04-13 | 2023-04-19 |  | Tested in live
139 |  | ISSUE | Properties | Detail page - comparables autoloading issue |  | MEERA | COMPLETED | URGENT |  |  | 2023-04-14 | 2023-04-14
140 | 2023-04-20 | SUGGESTION | Exclude Agent | adding exclude toggle as common |  | MEERA | COMPLETED | LOW |  |  | 2023-04-27 | 2023-04-27 |  | Sharan - Passed to Sandeep
141 | 2023-04-18 | TASK | Exclude Agent | need to add multiple zoopla/rightmove id's in user profile for exclude listings |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-19 | 2023-04-24 |  | Tested in staging by Meera
142 |  | ISSUE | Exclude Agent | Adding a popup in exclude my agent toggle if it has no id's in profile |  | SHARAN | COMPLETED | HIGH |  |  | 2023-04-26 | 2023-04-26
143 |  | SUGGESTION | Campaign History | print/sent (discuss) |  | MEERA | COMPLETED | LOW |  |  | 2023-04-14 | 2023-04-14 |  | It is in staging, please push that to live
144 |  | ISSUE | Report | There is no university and colleges data on reports |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-14 | 2023-04-14
145 |  | ISSUE | Probate properties | Care home addresses are coming up still even when I have clicked to exclude them |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-14 | 2023-04-14
146 |  | ISSUE | Anniversary Letter | when editing anniversary letter the selected sold date gets cleared |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-20 | 2023-04-20
147 |  | ISSUE | Anniversary Letter | difficult to see the preview icon |  | MEERA | COMPLETED | HIGH |  |  | 2023-04-20 | 2023-04-20
148 | 2023-04-20 | SUGGESTION | Report | Selected property image can be improved (previous image is still there even after changing the custom primary image) |  | MEERA | COMPLETED | MEDIUM |  |  | 2023-04-25 | 2023-04-26 |  | Tested in staging by meera
149 | 2023-04-24 | SUGGESTION | Detail Page | add on market status on the list of agents popup |  | ABHIJITH | COMPLETED | HIGH
150 | 2023-04-24 | SUGGESTION | Report | Info for use custom values for report generation |  | SHARAN | COMPLETED | MEDIUM
151 | 2023-05-02 | ISSUE | 20-20 Campaign | if we send letters to multiple addresses the amount deducted is not correct |  | RISHIKA | COMPLETED | HIGH |  |  | 2023-05-02 | 2023-05-02
152 | 2023-05-02 | ISSUE | Targeted Campaign | amount deducted from the campaign is not correct when sending 5/10 letters |  | RISHIKA | COMPLETED | HIGH
153 | 2023-05-02 | ISSUE | QR Form | in the qr form the Agents name is not given, it's blank |  | RIJO | COMPLETED | HIGH | [5 empty] | happened only in designdirect.r@gmail.com account
154 | 2023-05-02 | ISSUE | Report | for some addresses in the comparables properties list no properties are shown 9, Stonehall Grove, Downhall Road, Harlow, Essex, CM17 0RA |  | SHARAN | COMPLETED | MEDIUM
155 | 2023-05-02 | ISSUE | Live campaign | greeting of the letter gets a little cropped for letters with side panel, in the preview it looks ok but in stannp it looks a bit cropped |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-05-10 | 2023-05-16 |  | please check second instruction, probate, 20-20, targeted campaigns comment updated on 15/05/2023 - please check 20-20, targeted campaigns
156 | 2023-05-02 | ISSUE | Listing Page | all properties - if we click on filter by weeks listing from the menu and then click on All properties, the listing is filtered by the week which was last selected by the user in the menu (click on any of the Filter by week listing > click on All properties > check the filter) |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-05-18 | 2023-05-22
157 | 2023-05-02 | ISSUE | Report | custom value for report - even if the property has sq ft, it is not shown the first time |  | RIJO | COMPLETED | URGENT
158 | 2023-05-02 | ISSUE | Report | custom value for report - limit decimal to 2 places |  | RIJO | COMPLETED | URGENT
159 | 2023-05-02 | ISSUE | Report | custom value for report - difference in sq ft when compared to the report |  | RIJO | COMPLETED | URGENT
160 | 2023-05-02 | ISSUE | 20-20 Campaign | the side panel goes outside the guideline when all 5 data is shown |  | RIJO | COMPLETED | URGENT
161 | 2023-05-02 | SUGGESTION | Listing Page | when adding an address to the 20-20 campaign if a warning message is displayed indicating that no neighbors were found, clicking on "Add all selected properties" does not close the contacted properties pop-up RM16 |  | ANISHA | COMPLETED | MEDIUM | [5 empty] | Can't reproduce the issue ------- | no-161-add-20-20-campaign-popupclose-anishaJune132023
162 | 2023-05-02 | ISSUE | 20-20 Campaign | sub building numbers are missing for some neighbouring addresses, so the addresses seem as though it's repeating 3, Badgers Mount, Orsett, Grays, Thurrock RM16 3JB 5, South View Cottages, Rectory Road, Orsett, Grays, Thurrock RM16 3JX |  | SHARAN | COMPLETED | URGENT | [5 empty] | sub buildings are not shown in the letters
163 | 2023-05-03 | ISSUE | Export csv | probate property - if the user has selected multiple outcodes, in the exported file only the first outcode which was selected is shown |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-05-04 | 2023-05-04 |  | not cleared in live
164 | 2023-05-03 | ISSUE | Export csv | probate property - texts like formerly are shown in the exported file |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-05-04 | 2023-05-04 |  | not cleared in live
165 | 2023-05-03 | ISSUE | Campaign History | when we send bulk mail even if the letters are still being sent, in the campaign history the status is shown as Sent instead of Pending |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | campaign status will be Sent but internal property status will be relative
166 | 2023-05-03 | ISSUE | Header | if we click on Home, in the main dashboard only Auction is enabled |  | RIJO | COMPLETED | MEDIUM | [5 empty] | 4 boxes are enabled only for accounts created from letsbid end
167 | 2023-05-03 | ISSUE | Probate properties | when we click on clear filter the selected outcodes are cleared but the status does not change to the default value |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-05-19 | 2023-05-19 |  |  | no164-selected-outcodes-cleared-sandeep-19may2023
168 | 2023-05-04 | ISSUE | Dashboard | getting an error page on clicking the dashboard for tom.butler@orlandoreid.co.uk |  | SHARAN | COMPLETED | URGENT |  |  | 2023-05-04 | 2023-05-04
169 | 2023-05-04 | ISSUE |  | when we logout from the prospecting tool, redirect to letsbid estate login page |  | ASHIK | COMPLETED | URGENT |  |  | 2023-05-26 | 2023-05-26 |  | when we logout the user is redirected to the main dashboard page https://letsbidproperty.co.uk/main-dashboard.php | no169_logout_redirect_26_05_2023_ack
170 | 2023-05-04 | ISSUE | Listing Page | when we select addresses the full row gets highlighted, please remove the highlight |  | ABHAY | COMPLETED | LOW
171 | 2023-05-04 | ISSUE | Live campaign | probate campaign - when there are multiple letters, it takes time to view the preview of the letter |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | as we use getaddress there will be a time delay
172 | 2023-05-04 | ISSUE | Live campaign | probate campaign - letters are being sent to executor address even after removing it |  | SANDEEP | COMPLETED | URGENT | [5 empty] | there is an issue with addresses that are already in the campaign, works fine with newly added addresses
173 | 2023-05-04 | ISSUE |  | stannp - multiple letters are being sent to the same address |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-05-05 | 2023-05-15 |  | doing in other letters
174 | 2023-05-05 | ISSUE |  | amend orlando reid letters to remove overlapping - tom.butler@orlandoreid.co.uk |  | RIJO | COMPLETED | MEDIUM
175 | 2023-05-05 | ISSUE |  | The average price on the side panel on letters should all be on one line |  | RIJO | COMPLETED | HIGH
176 | 2023-05-05 | ISSUE | Letter management | please make sure the letter preview in letter management is the same as the preview provided while bulk mail/local print |  | UNASSIGNED | CLOSED | MEDIUM
177 | 2023-05-05 | ISSUE | Targeted Properties | the row gets highlighted when we click anywhere near the address |  | ABHAY | COMPLETED | LOW
178 | 2023-05-05 | ISSUE | Local Print | probate campaign - no space between the executor address and reference |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | no174-probate-issue-sandeep-18may2023
179 | 2023-05-05 | ISSUE | Probate properties | in the detail page when we click on Add to campaign, the button changes to Added to campaign only when the page is refreshed |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-05-23 | 2023-05-23 |  |  | no180-detailpage-add-to-campaign-sandeep-23may2023
180 | 2023-05-05 | ISSUE | Listing Page | if we select properties and add them to campaign, the selection does not disappear |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | not completed in probate and targeted
181 | 2023-05-09 | ISSUE | Listing Page | the status is given as Letter Sent but no letter has been sent to these addresses |  | SANDEEP | COMPLETED | MEDIUM
182 | 2023-05-09 | ISSUE | Campaign History | 20-20 campaign - when the letters are being sent out the delivery status of all the addresses are shown as Fail |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-05-15 | 2023-05-15
183 | 2023-05-09 | ISSUE | Report | add report js and css into vite module |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-16 | 2023-05-16
184 | 2023-05-09 | ISSUE | Listing Page | same addresses are not merged, happens mostly in case of flats when sending letters, multiple letters will be sent to the same address https://prospectingtool.letsbidproperty.co.uk/properties/p-1284678 https://prospectingtool.letsbidproperty.co.uk/properties/p-104309 |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-05-23 |  |  | need help from Jinto --- Rahul has informed that properties will be unique from now on, require to merge historical properties ----------------------------------- will keep checking for few days
185 | 2023-05-09 | ISSUE | Exclude Agent | some agents are missing, no suggestions are shown when we search eg: hanover, lsl franchise, jan forster, 66289 |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | checked in staging
186 | 2023-05-09 | ISSUE | Exclude Agent | no suggestions are shown if we type in 3 or 2 characters only eg: TK (Hampstead) Ltd t/a TK International - 66289 |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | checked in staging
187 | 2023-05-09 | ISSUE | Exclude Agent | user can select the same estate agent multiple times |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-16 | 2023-05-16 |  | checked in staging
188 | 2023-05-09 | ISSUE | Live campaign | probate campaign - addresses shown are not correct while removing there is an issue with addresses that are already in the campaign, works fine with newly added addresses |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-05-18 | 2023-05-18 |  | Sandeep transfer to Rijo need to remove all unprocessed campaign properties especially in probate campaign - permission required removed all campaign probate properties in live - Rijo rijo@designdirect.io checked in live with few properties that i had added sometime today, remove is not working properly (reopened on 16/05/2023)
189 | 2023-05-09 | ISSUE | Listing Page | property type not correct for some addresses |  | RIJO | COMPLETED | MEDIUM | [5 empty] | type
190 | 2023-05-10 | ISSUE | Report | if the primary image is removed and no other image is uploaded, it still shows the removed image on the report |  | SHARAN | COMPLETED | HIGH |  |  | 2023-05-10 | 2023-05-15 |  | reopened on 15/05 the primary images are not shown in the report if cover page image button is enabled
191 | 2023-05-10 | ISSUE | Report | shows many data for Sale History, goes over to the other pages 66, Park Royal, Montpelier Road, Brighton, East Sussex, BN1 3BL |  | SHARAN | COMPLETED | HIGH
192 | 2023-05-10 | ISSUE | 20-20 Campaign | Neighbour Properties list - in some addresses the same line is repeating eg: check the neighour list of Flat 6, Salisbury Court, Salisbury Road, London, Greater London SW19 4HH Flat 4, Queens Court, Meath Street, London, Greater London SW11 4HZ |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-17 | 2023-05-18
193 | 2023-05-10 | ISSUE | 20-20 Campaign | address lines are repeating for some neighbour properties, in edit address there is no issue but when we print it repeats https://prnt.sc/FsSivHA8Ci1Y |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-17 | 2023-05-18
194 | 2023-05-10 | ISSUE | Live campaign | when letters are being sent to many addresses, edit address takes time to load |  | RIJO | COMPLETED | MEDIUM | [5 empty] | we are using getaddress for each address that is in edit address
195 | 2023-05-10 | TASK | Report | Where an underground station or a tram station are more than 40 miles away we should not register it as it looks out of place |  | SHARAN | COMPLETED | HIGH |  |  | 2023-06-12 | 2023-06-13 |  | checking for new method | No195_within_distance_calculator_12_06_2023_Sharan-N-P
196 | 2023-05-10 | ISSUE | Exclude Agent | if the agent has only entered rightmove or zoopla id, when we enable exclude agency in withdrawn, price drop, back to market, sold-under offer listing pages no data is shown |  | SHARAN | COMPLETED | HIGH
197 | 2023-05-10 | ISSUE | Withdrawn | for quite a few addresses the list date and withdrawn date is the same |  | RIJO | COMPLETED | HIGH |  |  | 2023-05-15 | 2023-05-22
198 | 2023-05-10 | ISSUE | Withdrawn | the withdrawn date in the listing and detail page are different |  | RIJO | COMPLETED | HIGH |  |  | 2023-05-15 | 2023-05-22
199 | 2023-05-10 | ISSUE | Targeted Campaign | letters are not being sent credits are deducted from the wallet but doesnt reach stannp |  | SANDEEP | COMPLETED | URGENT
200 | 2023-05-10 | ISSUE | Campaign History | targeted campaign - when letters are sent using bulk mail campaigns are created but in the detail page the addresses arent shown Targeted-Bulk-Campaign-10-05-2023 03:57 Targeted-Bulk-Campaign-10-05-2023 03:54 |  | SANDEEP | COMPLETED | URGENT
201 | 2023-05-10 | ISSUE | Targeted Campaign | shows the preparing preview pdf loader when local printing lots of letters |  | SANDEEP | COMPLETED | MEDIUM
202 | 2023-05-11 | TASK | Dashboard | option to remove properties from quick send list |  | SHARAN | COMPLETED | HIGH |  |  | 2023-05-23 | 2023-06-01 |  | for company owned properties, if we send letters to either company address or property address - in the campaign history both the addresses are shown - 2 credits are deducted from wallet | Remove_properties_quicklist_23_05_2023_Sharan-N-P
203 | 2023-05-11 | ISSUE | Detail Page | back buttons are not working properly sometimes, when we return to the listing page the selected filters are removed |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-05-18 | 2023-05-30 |  | task transferred from Abhijith to Ashik if the user goes to the 2nd/3rd or any page in all properties listing and goes to filter by weeks listing they are still in the last page selected --------------------------- issue transferred to Abhijith on 29/05/2023 when we select weeks filter and then click the back button all the selected filters are cleared ----------------------- will test for few more days | no214_properties_back_button_20_05_2023_ack :::::: no-203-back" new branch
204 | 2023-05-11 | ISSUE | Report | Average Area Price / Sqft is not shown in market analysis page in the reports 6, Farquhar Road, Birmingham, West Midlands, B13 8HH |  | SHARAN | COMPLETED | HIGH |  |  | 2023-05-15 | 2023-05-16 |  | please check and confirm
205 | 2023-05-12 | ISSUE | Listing Page | all properties, filtered by listings - shows a warning pop up if no outcodes are selected and exclude my agencies button is enabled |  | SHARAN | COMPLETED | HIGH |  |  | 2023-05-17 | 2023-05-18 |  | need to implement in the other pages
206 | 2023-05-12 | ISSUE | Dashboard | quick send - properties of agencies that are being excluded are still shown in the quick send list |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-07 | 2023-06-07 |  | if the agent has not added any rightmove/zoopla id's, it shows an error page in the dashboard | No206_Quick_send_excluded_agencies_25_05_2023_Sharan_N_P
207 | 2023-05-12 | ISSUE | Detail Page | the listing activity is not correct, it shows withdrawn in the listing activity but the property is still for sale https://prospectingtool.letsbidproperty.co.uk/properties/p-455722 https://prospectingtool.letsbidproperty.co.uk/properties/p-343122 |  | ABHIJITH | COMPLETED | HIGH
208 | 2023-05-12 | ISSUE | Live campaign | when local printing lots of letters, when we click on print it takes some time for the generating message to show so if the user again clicks on the print button 2 campaigns will be created after the first click of the print button, please disable both the print buttons |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | no208-print-button-need-to-disable-sandeep-29may2023
209 | 2023-05-12 | ISSUE | Report | description overlapping in the last page |  | SHARAN | COMPLETED | HIGH
210 | 2023-05-15 | TASK | Report | report description line height fix |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-06 | 2023-06-07 |  | updated June 20 - once the warning message is shown when the limit exceeds, it remains even if it is reduced | No210_Report_Description_Overlapping_issue_06_06_2023_Sharan-N-P
211 | 2023-05-15 | ISSUE | 20-20 Campaign | 20-20 campaign - when local printing multiple addresses, only the first address is removed from the campaign listing rest of the selected addresses remains (but letters are printed for all the chosen addresses) |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-05-17 |  |  |  | no211-selected-address-remains-sandeep-26may2023
212 | 2023-05-16 | ISSUE | Sold- Under offer | shows 404 page when we click on the back button from sold-under offer detail page |  | ABHIJITH | COMPLETED | URGENT |  |  | 2023-05-16 | 2023-05-16
213 | 2023-05-16 | ISSUE | Listing Page | if agents try to add properties that have already been contacted when exclude my agency is enabled, in the Contacted properties pop up only Add all selected properties button is shown https://prnt.sc/uAMtxEpcZoIb |  | ANISHA | COMPLETED | HIGH | [5 empty] | please check in all properties, withdrawn, price drop, sold/under offer, back to market ---------- remove contacted properties and add the rest to campaign button is not shown in the contacted properties pop up when exclude agency is enabled -------------- updated on 7-Jun - please check when adding to 20-20 campaign as well | no213-excludemyagency-alreadycontacted-anishaJune62023
214 | 2023-05-16 | ISSUE | Listing Page | the text in the pop up shown for exclude my agencies is not correct when it is enabled after the Contacted properties pop up is shown - add properties that have been already contacted to the campaign - after already contacted pop up is shown, enable Exclude Agents button https://prnt.sc/OY3uNDfUn7Le |  | ANISHA | COMPLETED | MEDIUM | [5 empty] | please check in all properties, withdrawn, price drop, sold/under offer, back to market | no-214-excludeagencies-textincorrect-anisha6june2023
215 | 2023-05-16 | ISSUE | Letter management | the preview is too small https://prnt.sc/nY8OeFq-Ltkz |  | ASHIK | COMPLETED | MEDIUM |  |  | 2023-05-17 | 2023-05-25 |  |  | wrong -> no215_letter_management_17_05_2023_ack right -> no214_letter_management_17_05_2023_ack
216 | 2023-05-16 | ISSUE | Live campaign | properties without full addresses in campaign (second instruction and 20-20 campaigns) https://prnt.sc/VAlbggD7hI3Z |  | RIJO | COMPLETED | HIGH |  |  | 2023-05-16 | 2023-05-23 |  | task transferred from Rijo to Sandeep on 19-05-2023 issue in posting, Abhijith cleared and pushed in 26-05-2023 --------------------------------------- updated June 28 - please check 20-20 campaign,there are still incomplete addresses in 20-20 campaign hornchurch@griffingroup.co.uk info@ltproperties.com
217 | 2023-05-17 | SUGGESTION | Listing Page | if none of the outcodes are selected, please make sure no data is shown and the user is asked to select an outcode |  | ANISHA | COMPLETED | LOW |  |  | 2023-05-29 | 2023-05-29 |  | refer back to market and targeted lsiting | no217-outcode-noneselected-nodata-show-anisha25may
218 | 2023-05-17 | ISSUE | Listing Page | estate agent shown in the system is different when compared to the rightmove or zoopla listing please search for: Countrywide UK Sales, when checked in RM/Z the property is listed by Dixons, Moseley Arun Estates, when checked in RM the properties are listed by Douglas Allen, Chadwell Heath eg: Flat 10, Gallagher Court, Wake Green Park, Moseley, Birmingham, West Midlands B13 9XX Flat 33, Bowen Court, Wake Green Park, Moseley, Birmingham, West Midlands B13 9XP in the system it says it's listed by Countrywide UK Sales but when we check in rightmove/zoopla link it shows Dixons, Moseley 10, Roxy Avenue, Romford, London, RM6 4AN in system the agent name is Arun Estate but when we check in rightmove it is listed by Douglas Allen, Chadwell Heath |  | RIJO | COMPLETED | HIGH |  |  | 2023-05-19 | 2023-05-25 |  | need to wait for posting to reflect the changes in live comment updated 23/05/2023 - we have issue in posting code regarding agent creation ------------------- Countrywide UK Sales - the property is listed by Bairstow Eves, Shirley in RM https://prospectingtool.letsbidproperty.co.uk/properties/p-356840 Arun Estates - the property is listed by Cubitt & West, Shirley in RM https://prospectingtool.letsbidproperty.co.uk/properties/p-1266076 ------------------ will clean historical entries with multiple duplicate ids for estate agent
219 | 2023-05-17 |  | Listing Page | there is a difference in the estate agent name shown in the system and rightmove listing eg: in the system agents name is given as Balgores but in Rightmove agent name is Balgores Hayes, Brentwood |  | RIJO | CLOSED | MEDIUM
220 | 2023-05-17 | ISSUE | Profile | agent suggestions - same ids are repeating for different agents there are lots of suggestions for countrywide uk sales, arun estates eg: countrywide uk sales and dixon has the same ids |  | RIJO | COMPLETED | HIGH |  |  | 2023-05-19 | 2023-05-25 |  | connected to task 218 ----------------- countrywide uk has many suggestion but when we check the id in RM it shows different estate agent eg: 4888 https://tinyurl.com/24hywu6g https://tinyurl.com/2y9dupvt
221 | 2023-05-18 | ISSUE | Detail Page | when we click on the property images, for some properties the image goes out of the screen https://prospectingtool.letsbidproperty.co.uk/properties/b-106363 https://prospectingtool.letsbidproperty.co.uk/properties/b-232642 |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-29 | 2024-11-29 | 2024-12-05 |  | No221_Property_image_enlarge_issue_Sharan_N_P_29_11_2024
222 | 2023-05-18 | ISSUE | Local Print | need space between the address and the greeting in second instruction local print letters |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | no223-space-issue-local-print-second-istruction-sandeep-23may2023
223 | 2023-05-18 | ISSUE | Report | when generating reports if we remove the Report Color Theme, the texts on the first page and page numbers in the content page are not shown if there is no default color, not able to generate report |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-06 | 2023-06-08 |  | if the color theme is removed, the texts are still not shown | No223_Report_color_theme_selection_issue_06_06_2023_Sharan-N-P
224 | 2023-05-18 | ISSUE | Detail Page | even if no letter has been sent in the detail page the status is Letter Sent https://prospectingtool.letsbidproperty.co.uk/properties/p-1829286 account - designdirect.rishika@gmail.com |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-05-29 | 2023-05-30 |  | the status in the listing page changes to Letter Sent ------ updated on 8 June - status in the detail pages changes even if no letter has been sent --------------- updated on june 20 - status in the detail page changes even if no letter has been sent | no-224-letter-sent no-224-1-letter-sent
225 | 2023-05-19 | ISSUE | Letter management | when we upload images with transparent background, it shows a black background https://prnt.sc/bNQlLBtG9Kv- |  | ASHIK | COMPLETED | MEDIUM |  |  | 2023-05-24 | 2023-05-25 |  |  | --Same as above-- right -> no214_letter_management_17_05_2023_ack
226 | 2023-05-19 | ISSUE | Letter management | alignment of the image doesnt reflect in the preview and also does not get saved |  | ASHIK | COMPLETED | MEDIUM |  |  | 2023-05-24 | 2023-05-25 |  |  | --Same as above-- no43_letter_image_compress_31_05_2023_ack
227 | 2023-05-23 | ISSUE | Listing Page | please make sure the user returns to the same page, when they click on the back button in the detail page |  | ASHIK | COMPLETED | MEDIUM | [5 empty] | please implement in withdrawn, price drop, back to market, sold/under offer, targeted | no227_back_button_29_05_2023_ack
228 | 2023-05-23 | ISSUE | Report | the alert for custom values are not shown when generating reports |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-05-24 | 2023-05-24 |  |  | 228_Custom_alert_missing_24_05_2023_Sharan-N-P
229 | 2023-05-23 | ISSUE | Campaign History | second instruction - for bulk mail campaigns with company owned property, the preview shown for company address is that of the letter sent to property address itself |  | SANDEEP | COMPLETED | HIGH
230 | 2023-05-23 | ISSUE | Campaign History | when we click on the reload button for an address, the button above disappears and changes to a dot |  | SANDEEP | COMPLETED | HIGH
231 | 2023-05-23 | ISSUE | Campaign History | probate campaign - when we click on view letter sent to executor address, the letter shown is that of property address |  | SANDEEP | COMPLETED | HIGH
232 | 2023-05-23 | ISSUE | Campaign History | when we click on delivery status or view letter for some addresses it shows not available Bulk-Probate-Campaign-23-05-2023 12:52 (account - designdirect.r@gmail.com) Bulk-Probate-Campaign-24-05-2023 05:10 (account - designdirect.r@gmail.com) |  | SANDEEP | COMPLETED | HIGH
233 | 2023-05-23 | ISSUE | Campaign History | probate campaign - address missing from campaign history Bulk-Probate-Campaign-24-05-2023 05:10 (account - designdirect.r@gmail.com) |  | SANDEEP | COMPLETED | HIGH | [5 empty] | tested again, no issues found
234 | 2023-05-23 | ISSUE | Detail Page | withdrawn activity repeating in listing activity |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-05-24 |  | 2023-10-27 | updated jul 28: withdrawn activity repeating for some addresses mostly 16 weeks or more 11, Headcorn Road, Downham, Bromley, BR1 4SQ 65, Durham Hill, Bromley, Kent, BR1 5NF 65, Kings Avenue, Bromley, Kent, BR1 4HL Flat 73b First Floor, Headcorn Road, Bromley, BR1 4SQ 103, College Road, Bromley, BR1 3QG 1, Sundridge Parade, Plaistow Lane, Bromley, BR1 3FZ 11, Wellingley Road, Balby, Doncaster, DN4 8TD 121, Primrose Place, Doncaster, DN4 7DQ 133, Sandford Road, Balby, Doncaster, DN4 8ED ------------------------------------ updated oct 13: assigned to Abhijith ------------------------------------- updated oct 16: withdrawn activity is missing in the listing activity | no-234-withdrawn
235 | 2023-05-25 | ISSUE | Listing Page | the selections are still shown after adding properties to 20-20 campaign success message is not shown after adding properties to 20-20 campaign |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | please correct in Sold-Under Offer listing also please check with abhijith ------------ the selections are still shown when contacted properties pop up and error message is shown | no235-twenty20-selected-week-issue-sandeep-30may2023
236 | 2023-05-25 | ISSUE | 20-20 Campaign | 20-20 campaign - when sending bulk mail to multiple addresses, only the first address is disabled in the campaign listing addresses are removed only when page is refreshed |  | SANDEEP | COMPLETED | HIGH | [6 empty] | no140-auto-refresh-issue-sandeep-12may2023
237 | 2023-05-25 | ISSUE | Live campaign | letters are being sent to the same address multiple times (stannp) |  | SANDEEP | COMPLETED | URGENT | [5 empty] | will continue to monitor stannp for few days | no237-stannp-multiple-address-sandeep-26may2023
238 | 2023-05-25 | ISSUE | Wallet/Credit | for credits that have been refunded, please make sure an appropriate title is given |  | ANISHA | COMPLETED | MEDIUM | [6 empty] | no238-wallet-credit-refund-titlechange-anisha-1june2023
239 | 2023-05-26 | ISSUE | Detail Page | when adding an address to 20-20 campaign, the contacted property pop up does not close after clicking on 'Add this property to campaign' button |  | ANISHA | COMPLETED | MEDIUM | [6 empty] | no239-detailpage-202-20campaign-poupclose-anisha1-06-june2023
240 | 2023-05-29 | ISSUE | Detail Page | the property images and floor plans are not shown in the detail page https://www.prospectingtool.letsbidproperty.co.uk/properties/p-744276 |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-05-30 | 2023-05-30 |  | optimising find image query for listing | no-240-image-missing no-240-2-image-missing(all images)
241 | 2023-05-29 | ISSUE | Export csv | count difference in export data |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-05-29 | 2023-05-31 |  |  | no241-data_count_difference_exportdata-anisha-29may2023
242 | 2023-05-29 | ISSUE | Withdrawn | properties that are not withdrawn are shown in withdrawn listing Flat 65, Ethelburga Tower, Rosenau Road, London, SW11 4AB - https://prospectingtool.letsbidproperty.co.uk/properties/w-383706 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | updated Jul 19: https://prospectingtool.letsbidproperty.co.uk/properties/w-388720 - under offer but still listed in withdrawn listing https://prospectingtool.letsbidproperty.co.uk/properties/w-383706 - still on sale but listed in withdrawn ---------------------------- posting not upto date | no-250-withdrawn-activity-forsale
243 | 2023-05-29 | ISSUE | Detail Page | in the detail page Exclusive tag is given but the property is not exclusive https://www.prospectingtool.letsbidproperty.co.uk/properties/w-340796 https://www.prospectingtool.letsbidproperty.co.uk/properties/w-337652 |  | ANISHA | COMPLETED | MEDIUM | [6 empty] | no243-detailpage-exclusivetagissue-anisha1june2023
244 | 2023-05-29 | ISSUE | Probate properties | care home tag is not shown for some care home addresses |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-05-29 | 2023-05-29 |  |  | temp-probate-issue-29may2023
245 | 2023-05-30 | ISSUE | Live campaign | showing Exclusive tag for properties in campaign listing even if it is not an exclusive property 64, Stuart Road, Halesowen, West Midlands B62 0EB |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | please check in 20-20 campaign as well | no245-exclusive-tag-issue-sandeep-01jun2023
246 | 2023-05-30 | ISSUE | Withdrawn | not able to sort by withdrawn date |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | not able to sort by withdrawn date also look if its sortable by listed date --------- | no-246-withdrawn
247 | 2023-05-30 | ISSUE | Detail Page | detail pages takes some time to load |  | RIJO | COMPLETED | MEDIUM
248 | 2023-05-30 | ISSUE | Listing Page | the contacted properties pop up does not close when we click on Yes Add all properties button |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | can't reproduce the issue
249 | 2023-05-30 | ISSUE | Listing Page | filter by weeks listing - if we remove the week filter by clicking on x button, the week filter is still shown when we return to the listing page by clicking on the back button after removing the week filter week by clicking on x button and the user goes into a detail page and then clicks on the back button if the filtered listing dint have those many pages it shows no data https://tinyurl.com/2zsf2bqe |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-05-31 | 2023-05-31 |  |  | 224-week-remove
250 | 2023-05-31 | ISSUE | Detail Page | the listing activity is not correct, it shows withdrawn in the listing activity but the property is still for sale |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-06-07 | 2023-06-09 | 2023-08-25 | updated Aug 15: 81, Woodlands Park Drive, Dunmow, Essex CM6 1WT | no-250-withdrawn-activity-forsale
251 | 2023-05-31 | ISSUE | Letter management | please make sure the preview in letter management and the preview shown while sending letters are the same https://tinyurl.com/2mklwqpx |  | UNASSIGNED | CLOSED | MEDIUM | [5 empty] | same as 176
252 | 2023-05-31 | ISSUE | Listing Page | from the detail page if we click on the browser back button, all the filters selected are removed the filters selected are shown but data shown is not correct https://tinyurl.com/2jyoyn3b |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-06-06 | 2023-06-13 |  | issue only in edge page title fixed for all browsers -------------------- implemented only in All properties listing, please implement in rest of the pages ------ comment updated on 16 june - not implemented in probate and targeted listing | no-252-detail-back
253 | 2023-05-31 | ISSUE | Letter management | even if we upload an image with transparent background, the image has a white background |  | ASHIK | COMPLETED | MEDIUM | [5 empty] | updated june 26 - works but please speak to Ashik before making it live as there are other tasks in the same branch | no254_image_align_center_19_06_2023_ack
254 | 2023-05-31 | ISSUE | Letter management | if the image is center aligned it does not reflect in the preview and does not get saved, works for left and right |  | ASHIK | COMPLETED | MEDIUM | [5 empty] | #44, 253, 254 are in same branch --------------- | no254_image_align_center_19_06_2023_ack
255 | 2023-06-01 | ISSUE | Live campaign | the letter preview is zoomed out in Edge |  | ASHIK | COMPLETED | MEDIUM | [5 empty] | In staging for testing | no255_preview_zoom_05_06_2023_ack
256 | 2023-06-02 | ISSUE | Report | confirm button click and typing delay for report generation |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-06 | 2023-06-06 |  | eg : check in preview of letter management | No256_Confirm_buton_typing_delay_report_02_06_2023_Sharan_N-P
257 | 2023-06-02 | ISSUE | Probate properties | postcode not correct, takes the postcode after formerly |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-06-02
258 | 2023-06-05 | ISSUE | Export csv | Whenever LT properties export a screen from the platform, for example this one is 16 weeks or more, there are a number of blank addresses and the number doesnt match up with the amount of properties. So this was from 16 weeks or more in LU1 and LU2. They are asking why the excel deosnt match the system |  | ANISHA | COMPLETED | HIGH | [5 empty] | related to 241 task
259 | 2023-06-05 | ISSUE | General | More triggers for the agents : Second instruction -General letters 3 and 4 -Company owned -Back to Market Probate -Family executor trigger follow-up 20/20 -Trigger 3 and 4 please |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-06-05 | 2023-06-06 |  | After adding new triggeers the hardcocded array will be tranfered and used from DB using table letter_triggers | no259_trigger_from_db_update
260 | 2023-06-06 | ISSUE | Probate properties | different postcodes are shown in some of the addresses https://tinyurl.com/2zyla8rt Chelsea Court Place, 234a Kings Road, London Sw3 5ua, SW11 4DA Old Manor, Littlehempston, Devon Tq9 6na Also Of, Parkgate Road, London, SW11 4NP Nakom Ping Condominium, Room Number 1002 Chang Puak Sub-district, Chaing Mai Province 50300, SW11 3ER - https://www.thegazette.co.uk/notice/3920347 |  | SANDEEP | COMPLETED | [6 empty] | the addresses received from the api are like this
261 | 2023-06-06 | ISSUE | Probate properties | 12-13 Ryders Terrace, London, Nw8 0ee Also Of 43 Blenheim Terrace, NW8 0EJ Old Manor, Littlehempston, Devon Tq9 6na Also Of, Parkgate Road, London, SW11 4NP The Sandgate Hotel, 8-9 Wellington Terrace, The Esplanade, Sandgate, Folkestone, Ct20 3dy, Also Of Flat 38, Ambleside, Albert Drive, London, SW19 6JY there are few addresses like this, when we add them to campaign in edit address only till the first postcode is shown |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-06-02 | 2023-06-10 |  | stop at the first instance of a postcode in the address string ------ will run and test in weekend ----------- updated 20 June - one address with also of in the listing https://www.prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6Ik1CVXRFOStxRHVwajk4RkxzdjdwUHc9PSIsInZhbHVlIjoidlNXdkhkOFl5QXgxMW0rVytuOVZMUT09IiwibWFjIjoiYmQ2YjRhOTI3ZGMwNTFjZmUzYWZjMDA3ZWQ5ODM1YTRkNWI3NTBlNjNlOTAyOTE3MzE3NTc3NjUxY2FlMmE5NCIsInRhZyI6IiJ9
262 | 2023-06-06 | ISSUE | Probate properties | for some addresses the postcode is repeating Flat B 237 Balham High Road London, Sw19 7bg, SW19 7BG Flat 30 Elmwood Court 38 Battersea Park London Sw11 4je, SW11 4JE https://tinyurl.com/2dunqvym |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-06-02 | 2023-06-10 |  | stop at the first instance of a postcode in the address string ------ will run and test in weekend
263 | 2023-06-06 | ISSUE | Listing Page | withdrawn, back to market, price drop, sold/under-offer listings - the contacted properties pop up does not close when we click on Yes, add all the selected properties button |  | ANISHA | COMPLETED | HIGH | [6 empty] | no-263-popupnotclose-contactedpropertiese-anishaJune72023
264 | 2023-06-06 | ISSUE | Listing Page | withdrawn, back to market, price drop, sold/under-offer listings - the in campaign tag is shown only when the page is refreshed - the success message is not shown when properties are added to campaign |  | ANISHA | COMPLETED | HIGH | [6 empty] | no-263-popupnotclose-contactedpropertiese-anishaJune72023
265 | 2023-06-07 | SUGGESTION | Dashboard | in bulk mail address list please show company owned and company address tags for company owned properties (similar to campaign history) |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-08 | 2023-06-08 |  |  | No265_Comapny_owned_tag_08_06_2023_Sharan-N-P
266 | 2023-06-07 | SUGGESTION | Dashboard | in already contacted properties list please show company owned and company address tags for company owned properties (similar to campaign history) |  | SHARAN | COMPLETED | MEDIUM | [6 empty] | No265_Comapny_owned_tag_08_06_2023_Sharan-N-P
267 | 2023-06-07 | SUGGESTION | Detail Page | for company owned properties, please add the option to remove addresses from the list when doing quick send |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-07 | 2023-06-07
268 | 2023-06-07 | ISSUE | Listing Page | in the listing page, in campaign tag is shown for all the properties which were in the quick send list even after letters have been sent, but the properties are not in campaign this happens when we preview the pdf |  | ANISHA | COMPLETED | HIGH | [5 empty] | git branch not found | no-268-quicksend-listpage-incampaigntagissue-anisha7June2023
269 | 2023-06-07 | ISSUE | Detail Page | quick send in detail page doesnt work, shows something went wrong when we click on print preview and also when we send using bulk mail or local print |  | SHARAN | COMPLETED | URGENT | [6 empty] | Property_detail_Quick_send_07_06_2023_Sharan-N-P
270 | 2023-06-07 | ISSUE | Export csv | exported file for price drop: - price drop field is blank - price drop date is the same as list date |  | ANISHA | COMPLETED | HIGH |  |  | 2023-06-08 | 2023-06-08 |  |  | no270-exportedfile-pricedrop-date-price-anisha8June2023
271 | 2023-06-07 | ISSUE | Sold- Under offer | the STC/Offer Date in the listing and detail page is different https://tinyurl.com/2gq4g2ax 21, Lighthorne Rise, Luton LU3 3XG - https://prospectingtool.letsbidproperty.co.uk/properties/s-1327205 9, Westfield Close, Enfield, London, EN3 7RU - https://prospectingtool.letsbidproperty.co.uk/properties/s-1822034 https://prospectingtool.letsbidproperty.co.uk/properties/s-1261851 https://prospectingtool.letsbidproperty.co.uk/properties/s-430529 https://prospectingtool.letsbidproperty.co.uk/properties/s-1397368 |  | ANISHA | COMPLETED | HIGH |  |  | 2023-06-09 | 2023-06-09 |  |  | no-271-stc-listdetaildateissue-anisha8JUne20223
272 | 2023-06-08 | ISSUE | Dashboard | shows balance low even if there are enough credits in the account even if only few letters are selected it considers total number of properties in the quick send list |  | SHARAN | COMPLETED | URGENT |  |  | 2023-06-08 | 2023-06-08 |  |  | No272_QuickSend_balance_low_08_06_2023-Sharan-N-P
273 | 2023-06-09 | TASK | General | code optimisation |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-06-15 |  |  | https://hashwide-my.sharepoint.com/:x:/g/personal/ashik_designdirect_io/EWwbQfFWfD9BpYGQ4LsL4-wBjYNyiUnwcgfK1d7NT8lCNQ?rtime=kwTbNZp320g -------------------
274 | 2023-06-09 | SUGGESTION |  | cookie consent | Web | RIJO | HOLD | MEDIUM | [6 empty] | laravel-cookie-consent_Rijo_18May2023
275 | 2023-06-12 | ISSUE | Probate properties | address issue in probate, missing postcodes |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-06-13 | 2023-06-28 |  | running cron everyday to finish cleaning ----------------------------- updated 20 June - for some addresses the postcode is missing, only postcode is shown in the listing https://www.prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6IkFWS2hmaDNDaTJHaUlUN0RqMVRsQ3c9PSIsInZhbHVlIjoiSXJZUG9BdzNYcVdobTR5MUpWQ01GZz09IiwibWFjIjoiOWViNTFmZTdjY2Y1ZTAwNTVmMzNhYzY1YTUwMGMzYjkwZWQ2MGZlZjY1MGEzOTkxMjhmMDQwNTljNGFiMDdhOSIsInRhZyI6IiJ9 https://www.prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6IjN0VE9MNkRGQUx0ZWNoZmpxMzhOTnc9PSIsInZhbHVlIjoiTnlHUW1SYWVzTmpuTStFWS9oQ0NFdz09IiwibWFjIjoiMjljOTBlNGFjY2UxMzBiNGFlMjk5YWVjOGJjYmQyMmNiYTYzMWZiMjFmZWNjYzNkZDViMDBjMmE5OWE4YzhiNCIsInRhZyI6IiJ9 ----------------------------------- updated 26 June: LS16 - postcode missing SK8 ---------------------------------- updated 29 June: LS16 BR1 SK8 | temp-probate-formerly-outcode-issue-sandeep-02jun2023
276 | 2023-06-14 | ISSUE | Report | have to click on confirm address button twice to continue |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-16 | 2023-06-16 |  |  | No276_Confirm_button_double_click_14_06_2023_Sharan-N-P
277 | 2023-06-14 | ISSUE | Report | floor plans are not shown in the report |  | SHARAN | COMPLETED | HIGH |  |  | 2023-06-15 | 2023-06-19 |  | 17, Avon Close, Sutton, Surrey, SM1 4PT https://www.rightmove.co.uk/properties/130614248#/?channel=RES_BUY -------------------- * properties have floor plan but it's not shown when generating the report - 20, Nightingale Close, Matlock, Derbyshire, DE4 5AJ 77, Yokecliffe Drive, Wirksworth, Matlock, Derbyshire DE4 4PF | No277_Floorplan_missing_15_06_2023_Sharan-N-P
278 | 2023-06-14 | ISSUE | Sold- Under offer | on the market tag is shown for a property that is sold stc https://prospectingtool.letsbidproperty.co.uk/properties/s-444487 |  | ABHIJITH | COMPLETED | MEDIUM
279 | 2023-06-14 | TASK | Detail Page | hide registration number of company address if it's not correct |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | updated on June 20 - reg no is given as Not Available but it's still clickable, if registration number is not available does it need to be displayed there? https://devidiamober.com/properties/p-646086 https://devidiamober.com/properties/p-233586 | no279-reg-number-of-company-address-sandeep-15jun2023
280 | 2023-06-14 | TASK | Report | by default disable the satellite image in the first page of report |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-14 | 2023-06-14 |  | change the text to: Click here to add the satellite image on the front page | No265_Comapny_owned_tag_08_06_2023_Sharan-N-P
281 | 2023-06-15 | ISSUE | Report | not able to generate report for some addresses Wynbrook Lodge Old Melton Road, Keyworth, NG12 5NN |  | SHARAN | COMPLETED | HIGH |  |  | 2023-06-15 | 2023-06-15 |  | Wynbrook Lodge Old Melton Road, Keyworth, NG12 5NN ------------ speak to Rahul about the fix done in Letsbid | Report_Generating_Issue_15_06_2023_Sharan-N-P
282 | 2023-06-15 | ISSUE | Outcodes | not able to add outcodes |  | RIJO | COMPLETED | HIGH |  |  | 2023-06-15 | 2023-06-15
283 |  | ISSUE | Report | universities are pinned in the sea |  | SHARAN | COMPLETED | HIGH
284 | 2023-06-16 | ISSUE | Report | property images are not shown in the report https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4392_160620230648417896.pdf |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-16 | 2023-06-19 |  | not able to generate report for some addresses Wynbrook Lodge Old Melton Road, Keyworth, NG12 5NN | No284_Property_images_issue_report_19_06_Sharan-N-P
285 | 2023-06-16 | ISSUE | Live campaign | property was added to campaign but address is not found in campaign listing |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-06-16 |  |  | when we preview and then cancel, in the property listing the added to campaign tag is missing (property is still in the campaign) the tag is not shown even if we try adding it to the campaign again | no285-added-to-campaign-sandeep-19jun2023
286 | 2023-06-19 | TASK | Report | lettings page in report Date listed Rent Name of agent Full address of property Bedrooms Property type |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | * shows withdrawn and let agreed properties in rental comparable list * rental comparable pop up is not shown like the other comparable * change column name to Bed ----------------------------------- updated jul 20: shows withdrawn and let agreed properties in rental comparable list - need to confirm if this is ok | No286_Lettings_page_report_12_07_2023_Sharan-N-P
287 | 2023-06-19 | ISSUE | Export csv | probate - in some of the exported file, postcodes are missing for some addresses and also few addresses are incomplete PR9, SW19, EN3 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-06-22
288 | 2023-06-19 | ISSUE | Exclude Agent | in withdrawn, price drop, back to market, sold-under offer listings, if the property is listed by multiple agents only if the agents has added all agents name the property is excluded |  | SHARAN | COMPLETED | HIGH | [6 empty] | No288_Exclude_agent_20_06_2023_Sharan-N-P
289 | 2023-06-19 | ISSUE | Report | reports not working properly, have to click on confirm button multiple times |  | SHARAN | COMPLETED | URGENT | [6 empty] | No289_Report_issue_19_06_2023_Sharan-N-P
290 | 2023-06-19 | ISSUE |  | system is a bit slow |  |  | COMPLETED | HIGH
291 | 2023-06-19 | ISSUE | Dashboard | if the user's credit is low while attempting a quick send, a notification is displayed. However, if the user then selects fewer letters and sends, letters are sent to all the addresses in the quick send list even thought the balance is low |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-09-07 | 2023-09-07 | 2023-09-11
292 | 2023-06-20 | ISSUE | Report | property has planning application but it's not shown in the report Mulberry House, Normanton On The Wolds, Nottingham, Nottinghamshire, NG12 5NN Willow Cottage, Normanton-on-the-Wolds, Nottingham, Nottinghamshire, NG12 5NP |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | will confirm on 30-jun
293 | 2023-06-20 | ISSUE | Report | when generating a report for properties that are on the market, it shows off market https://www.prospectingtool.letsbidproperty.co.uk/properties/p-473480 |  | SHARAN | COMPLETED | URGENT |  |  | 2023-06-20 | 2023-06-20 |  | updated on june 20 - working for majority of the addresses but in case of some flats it still shows off the market even if it's on market | No293_PortalId_updation_report_20_06_2023_Sharan-N-P
294 | 2023-06-20 | ISSUE | Detail Page | comparables are not shown in the detail page but there are comparables in the report https://www.prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6InBwYnE5TURrY21Ta0Z3VzNvYVRCN3c9PSIsInZhbHVlIjoiejQ3S1VURWQ1Zzl2UHlmTlVvdkxLZz09IiwibWFjIjoiZmFiZDQ1MzczZmJiZDY2M2Y3NGI5NzMwZGNlZWE4ZGNmMTJiZWFlYjgxODk0NjhjODA5MjUxODI1OTE3M2VjOSIsInRhZyI6IiJ9 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-1412157 |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | if there are comparables when generating report, can it not be shown in the detail page? | Property_Type_Trait_07_08_2023_Sharan-N-P
295 | 2023-06-20 | ISSUE |  | there are comparables in the detail page but it's not shown when generating the report 94 old church road E1 0QB 1, Mead Close, Romford, London, RM2 5NX: https://prospectingtool.letsbidproperty.co.uk/properties/p-2025346 |  | SHARAN | COMPLETED | HIGH | [6 empty] | No295_Comparables_report_20_06_2023_Sharan_N_P
296 | 2023-06-20 | ISSUE | Report | comparables in the detail page and report are different https://www.prospectingtool.letsbidproperty.co.uk/properties/p-1412157 |  | SHARAN | COMPLETED | HIGH |  |  | 2023-06-28 | 2023-06-28 |  | 413, Brook Lane, Kings Heath, Birmingham, West Midlands B13 0DJ 98, Chapel Farm Road, London, SE9 3NQ | No296_Comparable_missing_28_06_2023_Sharan-N-P
297 | 2023-06-20 | ISSUE | Report | content in Neighbouring Planning History page goes to the next page https://www.prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4499_200620231133610706.pdf https://www.prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4505_200620231229792776.pdf |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-22 | 2023-06-23 |  |  | No297_Remove_Ltd_plannings_report_22_06_2023_Sharan-N-P
298 | 2023-06-20 | TASK | Report | passing property id when generating report |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-29 |  |  | 9, Walesby Court, Leeds, West Yorkshire LS16 6RX 625a, High Road Leyton, London E10 6RF - shows on the market but the type and images are not givne when generating report (works properly in live) 39A, Freelands Road, Bromley, Kent, BR1 3HZ 1, Baxter Court, 96 School Road, Moseley, Birmingham, B13 9TP 150, Mosquito Way, Hatfield, Hertfordshire AL10 9AY | No298_Report_portal_id_29_06_2023_Sharan-N-P
299 | 2023-06-20 | TASK | Report | market analysis - change to Current Average Area Price |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-26 | 2023-06-26 |  | need to confirm with Milton | No299_Market_analysis_text_change_26_06_2023_Sharan-N-P
300 | 2023-06-20 | ISSUE | Report | some properties are missing in Sold Prices on Street |  | SHARAN | COMPLETED | [6 empty] | Address?? ---- do nearby with road instead of just postcode as per Milton and Roys
301 | 2023-06-20 | ISSUE | Report | the property type is end of terrace but when generating report the comparables shown is of semi detached 63, Whitney Road, London, E10 7HG - https://prospectingtool.letsbidproperty.co.uk/properties/p-1412157 2, Amery Gardens, Romford, London, RM2 6RU - https://prospectingtool.letsbidproperty.co.uk/properties/p-2036270 |  | SHARAN | COMPLETED |  |  |  | 2023-06-28 | 2023-06-28 |  | 2, Amery Gardens, Romford, Essex, RM2 6RU - https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4509_280620231439126236.pdf 63, Whitney Road, London, E10 7HG - https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4491_280620231445010417.pdf
302 | 2023-06-21 | ISSUE | General | search in the header - shows an error page when we search https://tinyurl.com/29ef8atl |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-06-26 |  |  |  | no-302-search
303 | 2023-06-21 | ISSUE | Report | for some properties the floor plan is shown in the detail page but not when generating report Flat 14, Waterford Court, Elworthy Close, Stafford, Staffordshire ST16 3QT - https://prospectingtool.letsbidproperty.co.uk/properties/w-1526347 |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-08 | 2023-09-08 | 2023-09-12 | Getaddress, Portal address both formats are different
304 | 2023-06-21 | ISSUE | Report | in case of some flats and addresses with house name, when generating reports it shows off the market even if it's on market Haddon House, Lincoln Road, East Markham, Newark, Nottinghamshire NG22 0SH |  | SHARAN | COMPLETED | MEDIUM
305 | 2023-06-22 | SUGGESTION | Letter management | custom triggers for letter management |  | RIJO | COMPLETED | MEDIUM | [5 empty] | need to confirm the task with Vipin ------------------------------ will be difficult to track the letter types if each agent creates their own trigger, can create triggers generally
306 | 2023-06-22 | TASK | Report | update toggle for satellite image in front page of report - markers for map when the toggle is off, no markers will be shown on the map when the toggle is turned on, markers will be shown on the map |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-26 | 2023-06-28 |  |  | No306_Map_marker_toggle_26_06_2023_Sharan-N-p
307 | 2023-06-22 | ISSUE | Detail Page | floor plan is not shown in the detail page but when we check in RM/Z listing there is floorplan 71, Crabtree Road, Birmingham, West Midlands B18 7HS - https://prospectingtool.letsbidproperty.co.uk/properties/p-741889 |  | ABHIJITH | COMPLETED | MEDIUM | [6 empty] | no-307-floor-plan
308 | 2023-06-22 | ISSUE | Probate properties | showing probate addresses of outcodes which are not subscribed E1, EC1, |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-06-27 | 2023-06-28 |  |  | temp-probate-formerly-outcode-issue-sandeep-02jun2023
309 | 2023-06-22 | ISSUE | Probate properties | few properties are missing from the listing but those properties are shown under a different postcode E1W |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-06-27 | 2023-06-28 |  |  | temp-probate-formerly-outcode-issue-sandeep-02jun2023
310 | 2023-06-22 | ISSUE | Probate properties | Nakom Ping Condominium, Room Number 1002 Chang Puak Sub-district, Muang Chiang Mai District, Chaing Mai Province 50300, THAILAND; this address is listed under SW11 |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-06-27 | 2023-06-28 |  |  | temp-probate-formerly-outcode-issue-sandeep-02jun2023
311 | 2023-06-22 | ISSUE | Probate properties | not receiving probate texts last received by Rosie is on June 15 |  | RIJO | COMPLETED | HIGH | [5 empty] | checking with Sharan on vonage ------------ Updated to Rosie new messages have gone out after 15th | Resend_Message_23_06_2023_Sharan-N-P
312 | 2023-06-22 | ISSUE | Report | the property address is shown in the comparables list Flat 24, 74, Wapping High Street, London, E1W 2NP |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-28 | 2023-06-28 |  |  | No312_comparable_address_28_06_2023_Sharan-N-P
313 | 2023-06-22 | ISSUE |  | EC1 - the addresses shown are in the outcode PE19 |  | ASHIK | COMPLETED | HIGH
314 | 2023-06-23 | TASK | Dashboard | change text in the dashboard |  | VIPIN | COMPLETED | MEDIUM
315 | 2023-06-23 | ISSUE | Listing Page | the listing price in the listing page and detail page is different 40, Gough Close, Stafford, Staffordshire ST16 1QF - https://prospectingtool.letsbidproperty.co.uk/properties/p-1526548 51, Sutherland Road, London, N17 0BN - https://prospectingtool.letsbidproperty.co.uk/properties/p-26593 |  | ABHIJITH | COMPLETED | HIGH
316 | 2023-06-23 | ISSUE | Report | company owned properties are not marked in the report for some properties 13, Norton Road, Luton LU3 2NX - https://prospectingtool.letsbidproperty.co.uk/properties/p-416806 |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-06-28 | 2023-06-28 |  |  | No316_Company_owned_tag_missing_28_06_2023_Sharan-N-P
317 | 2023-06-23 | ISSUE | Listing Page | few properties are marked as exclusive in the listing page but not in the detail page 51, Sutherland Road, London, N17 0BN - https://prospectingtool.letsbidproperty.co.uk/properties/p-26593 90, Heath Road, Romford, London, RM6 6LH - https://prospectingtool.letsbidproperty.co.uk/properties/p-574481 28, Talbot Road, Luton, LU2 7RW 20, Cromwell Crescent, Market Harborough, Leicestershire, LE16 9JP 20, Stirling Road, London, N22 5BU |  | ANISHA | COMPLETED | LOW |  |  |  |  | 2023-09-11 | most listings are created by data entry - specifically Binju ------------------------- this property is tagged as exclusive only in the listing page, same property is in price drop but not tagged as exclusive | no-317-exclusivetag-ssie-anishaAugust11
318 | 2023-06-23 | ISSUE | Price Drop | in price drop listing there is a property with the postcode as unknown https://tinyurl.com/2oajlgc4 |  | RIJO | COMPLETED | MEDIUM
319 | 2023-06-23 | ISSUE | Exclude Agent | if the exclude agent button is enabled, it should be enabled in all the pages |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-06-26 | 2023-06-26 |  |  | no-319-exclude-agent
320 | 2023-06-26 | TASK | Report | on the market comparable page in report option to remove page when generating report on market comparables list where user can select properties (similar to comparable) |  | SHARAN | COMPLETED | HIGH |  |  | 2023-06-30 |  |  | in live --------------------------- optimisation: check epc for property type if property type is semi detached bungalow, the comparables should include bungalow | No320_Online_Comparable_29_06_2023_Sharan-N-P
322 | 2023-06-26 | TASK | General | postcards - 2 credits for postcards - user will have the option to do either postcard or letters |  | RIJO | COMPLETED | HIGH |  |  | 2024-04-26 |  |  | task on hold - will resume after lettings report Postcards Pending ================ Toggle for letter and postcard sending Update and Test bulk mail sending | no322_postcard_feature_Nikila_26Apr24
323 | 2023-06-27 | TASK | Withdrawn | if the property is removed after STC, it should not go in withdrawn section it should be removed from our data 6, Park Crescent, Sleaford, Lincolnshire NG34 7HY 143, Shenstone Road, Edgbaston, Birmingham, West Midlands B16 0PF 222, Oval Road, Croydon, London, CR0 6BP 15, Broomfield Court, Hatfield, Hertfordshire AL10 0NA 148, Hykeham Road, Lincoln, Lincolnshire LN6 8AW 140, Hykeham Road, Lincoln, Lincolnshire, LN6 8AW 11, The Old Rectory, Rectory Lane, Market Harborough, Leicestershire, LE16 8AS Coach House, The Old Rectory, Rectory Lane, Market Harborough, Leicestershire, LE16 8AS |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-06-28 |  |  | made live ----------------------------- optimise: stc then multiple withdrawn case ----------------------------- 17 july withdrawn cron restarted | no322_postcard_feature_Nikila_26Apr24
324 | 2023-06-27 | ISSUE | Dashboard | quick send is limited to around 900 properties if there are more than 900 properties in the quick send list, when we click on quick send button nothing happens | Web | RIJO | NOT STARTED | MEDIUM | [5 empty] | need to check if it's related to limit or address format -------------------------------- updated july 11: if there are lots of letters when we click on preview it shows something went wrong ------------ Property selection error- forward to SHARAN ------------------- limited to 300 address in getaddress getaddress limitation | no324_quicksend_limit_09_07_2023_ack
325 | 2023-06-28 | ISSUE |  | search in the header - no results are shown when we search with full address |  | ABHIJITH | COMPLETED | [6 empty] | works in staging when searching with full address
326 | 2023-06-28 | SUGGESTION | Listing Page | add a button in the listing page for letter history, on clicking the button a pop up will be shown with the campaign history of the property |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | difficult to understand that it is clickable, please add a button ----------------------- updated jul 20: * nothing happens when we click on View button after sending 20-20 campaign * please make the first letter of View button capital * in the campaign history pop up, please show the latest campaign first * if the user selects a campaign and then click on the back button, they are redirected to the detail page of the property which was last opened by them ----------------------- updated jul 24: * after sending 20-20 campaign, please show the latest campaign first | no-326-letter-send-popup
327 | 2023-06-28 | ISSUE | Outcodes | the text 'blank' is shown in the suggestion dropdown search with 'a' |  | RIJO | COMPLETED | MEDIUM
328 | 2023-06-28 | ISSUE | Outcodes | if we add multiple outcodes and remove the first outcode, no data will be shown for the last selected outcode |  | ASHIK | COMPLETED | LOW | [6 empty] | no328_outcode_remove_issue_05_07_2023_ack
329 | 2023-06-29 | ISSUE | Listing Page | please make sure the correct estate agents are shown in the listing sometimes even if the agents have withdrawn their listing on the platform it shows that agent (correct in the detail page) 166, Aldykes, AL10 8EE |  | ABHIJITH | COMPLETED | HIGH | [5 empty] | whatever logic is applied in the detail page should be applied in the listing as well --------------------------------- updated 7 jul: name of the agent that has withdrawn their listing is shown
330 | 2023-06-29 | ISSUE | Report | property type is given but in the market analysis page the type is blank 2, Amery Gardens, Romford, Essex, RM2 6RU https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4509_290620231159949136.pdf |  | SHARAN | COMPLETED | [7 empty] | Property_Type_Trait_07_08_2023_Sharan-N-P
331 | 2023-07-03 | ISSUE | Detail Page | no comparables are shown in the detail page but while generating report there are comparables this happens when the property type is given as End_Terrace, property type is different in detail page and report (sometimes it's given as House on the platform but when generating report the correct type is given |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | please speak to Sharan -------------------------- will also check epc | no-376-soldhistroy-propertytype
332 | 2023-07-03 | ISSUE | Listing Page | after searching for properties using the search in the header or in the listing page, if the user goes to the detail page and return to the listing % is shown between the searched keywords once we return to the listing page no data will be shown https://tinyurl.com/28cmdoz9 |  | ABHIJITH | COMPLETED | LOW |  |  | 2023-08-01 | 2023-08-02 |  |  | no-332-search
333 | 2023-07-03 | ISSUE | Properties | the property type in the listing page and detail page is different 33, Hogarth Hill, London, NW11 6AY - https://prospectingtool.letsbidproperty.co.uk/properties/p-1883668 63, Whitney Road, London, E10 7HG - https://prospectingtool.letsbidproperty.co.uk/properties/p-1412157 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | whatever logic is applied in the detail page should be applied in the listing as well ---------------------------------- will implement in optimisation
334 | 2023-07-03 | ISSUE | Listing Page | the searched keyword does not get cleared when we return to the listing page from the detail page, even if the user has cleared it |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-08-09 |  |  | updated Aug 16: * if we search and then return to the listing page, the keyword is cleared even if the user has not cleared it * search in the header does not work - the results are not shown according to the keyword searched | New-Taskno-334-searchkeyword-notcleared-9August2023
335 | 2023-07-03 | ISSUE | Report | the property has floorplan in the detail page but when generating report the floorplan is not shown 90, Heath Road, Romford, London, RM6 6LH - https://prospectingtool.letsbidproperty.co.uk/properties/p-574481 |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-08 | 2023-09-08 | 2023-09-12 | moved to abhijith on Sep 7 | no-335-floor-plan
336 | 2023-07-03 | ISSUE | Live campaign | addresses are repeating in stannp |  | SANDEEP | COMPLETED | HIGH | [5 empty] | cannot check in staging | no336-address-repeating-sandeep-05july2023
337 | 2023-07-03 | TASK | General | outcode_id in postcode table correction |  | SANDEEP | COMPLETED | [6 empty] | EC1
338 | 2023-07-04 | ISSUE | Properties | only the house number is shown https://www.prospectingtool.letsbidproperty.co.uk/properties/p-513088 |  | ABHIJITH | COMPLETED | HIGH | [6 empty] | no-338-house-number-only
339 | 2023-07-04 | ISSUE | Properties | if the user selects an outcode and goes to different page and then returns to the previous listing it remains in the last selected page, so if the default outcode doesnt have those many pages it shows no data https://tinyurl.com/2bjuoth8 eg: if in 0-4 weeks listing we are in the second page and then go to the 12-16 weeks listing and then return to 0-4 weeks no data will be shown as we are still in the second page |  | UNASSIGNED | CLOSED | LOW
340 | 2023-07-06 | ISSUE | Detail Page | floor plan is not shown in the detail page but when we check in RM/Z listing there is floorplan 15, Easmore Close, Birmingham, West Midlands B14 5UW - https://prospectingtool.letsbidproperty.co.uk/properties/p-2053284 |  | ABHIJITH | COMPLETED | MEDIUM
341 | 2023-07-06 | ISSUE | Report | property has epc but it's not shown in the report Flat B, 39, Frognal, London, NW3 6YD - https://prospectingtool.letsbidproperty.co.uk/properties/p-2071665 |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | 10/07/2023 - No Epc for this property https://find-energy-certificate.service.gov.uk/energy-certificate/1020-9567-0099-1009-0763 ----------------------------- not getting the epc from the api ------------------------------ was a recently assessed property when report was generated
342 | 2023-07-06 | ISSUE | Report | the property type is different in the market analysis page 41, Sydner Road, London, N16 7UF - the type is end of terrace but in market analysis page it is given as Detached https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4842_060720231211337200.pdf 12, Averil Road, Leicester, Leicestershire, LE5 2DA - type is semi detached but in market analysis page it's detached https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_5243_210720230953837486.pdf |  | SHARAN | COMPLETED | [7 empty] | Property_Type_Trait_07_08_2023_Sharan-N-P
343 | 2023-07-07 | ISSUE | Properties | the property is withdrawn but on the platform it is still marked as For Sale Flat, 130, Wordsworth Court, Hatfield, Hertfordshire AL10 0EQ |  | ABHIJITH | COMPLETED
344 | 2023-07-07 | ISSUE | Report | on market comparable - if the same property is listed by multiple different agents, it is listed multiple times in the comparable listing 4, Cornflower Way, Hatfield, Hertfordshire, AL10 9FY 150, Mosquito Way, Hatfield, Hertfordshire AL10 9AY 7, Colesdale, Potters Bar, Hertfordshire, EN6 4LQ |  | SHARAN | COMPLETED | [6 empty] | got this issue when testing in staging: not getting comparables and on market comparables for flats 50, New Street, Dunmow, Essex, CM6 1BH 7, Harmans Yard, Dunmow, Essex, CM6 1AS ---------------------------------------------- on market comparables - data shown when we compare to live is different 5, Rofant Road, Northwood, Greater London, HA6 3BD | No320_Online_Comparable_29_06_2023_Sharan-N-P
345 | 2023-07-07 | ISSUE | Report | in on market comparable list, properties which are withdrawn or sold stc/under offer are also shown 76, Wroxham Gardens, Potters Bar, Hertfordshire, EN6 3DL 12, Borough Way, Potters Bar, Hertfordshire, EN6 3HB |  | SHARAN | COMPLETED | HIGH
346 | 2023-07-10 | TASK |  | sending sms per day 3 messages only |  | SHARAN | COMPLETED | [6 empty] | monitoring in vonage for few days | Text_messages_limit_10_07_2023_Sharan-N-P
347 | 2023-07-11 | ISSUE | Report | on market comparable - if only the property type is available and there is no sqft, the on market comparable pop up keeps loading Flat 3, Fursecroft, George Street, London, W1H 5LF 2, Warley Hill, Brentwood, Essex, CM14 5EZ |  | SHARAN | COMPLETED | MEDIUM | [6 empty] | Property_Type_Trait_07_08_2023_Sharan-N-P
348 | 2023-06-11 | ISSUE |  | probate sms country code input field check 07 numbers are not being added - append 44 instead of 0, so number becomes 447-- |  | ANISHA | COMPLETED | HIGH |  |  | 2023-08-09 |  |  | take 10 digits from the end and append 44 | no348-probate-sms-countrycodecheck-07-anisha-9August2023
349 | 2023-07-12 | ISSUE | Properties | getting a warning pop up when we click on filtered by weeks from the menu and also when we select week filter |  |  | COMPLETED | URGENT
350 | 2023-07-12 | ISSUE |  | comparables in detail page - if the property type is semi detached bungalow, the comparables should include bungalow (similar to on market comparable) in detail page and report also |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | http://demo.devidiamober.com/properties/p-2171191 - 7, Connaught Avenue, East Barnet, Barnet, London EN4 8PJ -> when we check in epc the type is semi detached bungalow but in the detail page the comparables shown are for terraced 75, Cloverly Road, Ongar, Essex CM5 9BX - http://demo.devidiamober.com/properties/p-1921030 -> when we check in epc the type is detached bungalow but in the detail page the comparables shown are for terraced | no-376-soldhistroy-propertytype
351 | 2023-07-12 | ISSUE | Report | on market comparable - few addresses are given with only the house number and postcode https://tinyurl.com/2c3o3kyb if the address is below 20 characters hide the address 24, Southampton Gardens, Luton, Bedfordshire, LU3 3UA |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | 19/07/2023 - Sharan Is it error?? ----------------------- if the address is below 20 characters hide the address ----------------------- updated Aug 16: still shows addresses with just house number and postcode 12, Belgrave Avenue, Romford, Essex, RM2 6QD 29, Chalforde Gardens, Romford, Essex, RM2 6BU | No351_Address_correction_on_comparables_16_08_2023_Sharan-N-P
352 | 2023-07-12 | ISSUE | Report | when generating report for some addresses it shows on the market but the type and property images/floor plans are not shown 9, Walesby Court, Leeds, West Yorkshire, LS16 6RX 625a, High Road Leyton, London E10 6RF |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | Sharan 14/08/2023 ================== 9, Walesby Court, Leeds, West Yorkshire, LS16 6RX - https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_5672_140820231223450722.pdf 625a, High Road Leyton, London E10 6RF - https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_4769_140820231236559130.pdf
353 | 2023-07-14 | TASK | Live campaign | estate agent name in campaign and campaign history |  | ABHIJITH | COMPLETED | HIGH
354 | 2023-07-14 | ISSUE | Report | the type of comparables shown in report is different 6, Williams Grove, London, N22 5NR - https://prospectingtool.letsbidproperty.co.uk/properties/p-111843 type is end terrace but in the report the comparables shown are for detached properties 15, Hidcote Gardens, London, SW20 0UG - https://prospectingtool.letsbidproperty.co.uk/properties/p-2057615 |  | SHARAN | COMPLETED | MEDIUM | [6 empty] | Property_Type_Trait_07_08_2023_Sharan-N-P
355 | 2023-07-14 | TASK | Targeted Properties | targeted filter - add min & max price filter |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-07-20 | 2023-08-08 |  | updated Aug 8: * when we click on clear filter Max Price field is not cleared * after clicking on clear filter button, in the filtered by section the filters which were previously selected is still shown https://tinyurl.com/26nze6hm | no355-add-min-max-targeted-sandeep-19july2023
356 | 2023-07-14 | SUGGESTION | Probate properties | if the property has epc can we not get comparables? check if the property has epc |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-07-19 |  |  | * if there are no comparables, the comparable section keeps loading | no-357-probate-comparable
357 | 2023-07-17 | SUGGESTION | Detail Page | campaign history section - show the latest campaign first |  | ABHIJITH | COMPLETED | LOW | [5 empty] | updated jul 20: still shows the oldest campaign first | no-357-campaign-order
358 | 2023-07-17 | TASK |  | remove land registry title number calls |  | RIJO | COMPLETED | MEDIUM
359 | 2023-07-17 | ISSUE | Price Drop | listing activity not correct, it shows price increased but when checked with RM/Z listing the price is reduced |  | UNASSIGNED | CLOSED | MEDIUM |  |  | 2023-08-31 | 2023-09-07 | 2023-09-07 | updated Sep 7: 21, Thistle Way, Witham St Hughs, Lincoln, Lincolnshire LN6 9XJ Flat 13, Victoria Court, Cartwright Street, London, E1 8LZ ------------------------- updated Sep 8: new patterns found
360 | 2023-07-18 | TASK | Report | 1. change title to On Market Rental Comparable 2. remove text below title - On Market Rental Comparable page 3. columns should be spaced properly 4. remove furnish type from rental comparable 5. remove text below title - on market comparable page ⁠6. on market comparable page - portal icons add color |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-18 | 2023-07-18 |  | linked to task 286 | No286_Lettings_page_report_12_07_2023_Sharan-N-P
361 | 2023-07-18 | ISSUE | Probate properties | E1W is shown under E1 |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | updated jul 25: still shows 1 property under E1W in E1
362 | 2023-07-18 | ISSUE | Live campaign | Calum Partridge - live campaign issue |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-07-18 | 2023-07-18 |  | Monitoring pending in jobs
363 | 2023-07-18 | ISSUE | Wallet/Credit | amount debited from wallet is not correct, sometimes even if only 1 campaign has been sent from the wallet credits are debited more than once Aaran Rathod - aaran@bmestates.com |  | RIJO | COMPLETED | HIGH | [5 empty] | side panel code issue - fixed
364 | 2023-07-19 | TASK | Report | in custom values there should be an option to add bedrooms (this will be only for lettings) dropdown with options 1, 2, 3, 4, 5 or more This value will only affect Rental comparable |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-19 | 2023-07-20 |  | linked to task 286 | No286_Lettings_page_report_12_07_2023_Sharan-N-P
365 | 2023-07-19 | ISSUE | Live campaign | all the campaigns have issue, none of the letters are reaching stannp multiple debits from wallet for probate, 20-20, targeted addresses are greyed out but not removed from campaign for probate, 20-20, targeted |  | SANDEEP | COMPLETED | URGENT
366 | 2023-07-19 | ISSUE | Report | data goes to the on market comparable page, it shows 15 comparables in the report |  | SHARAN | COMPLETED | HIGH |  |  | 2023-07-19 | 2023-07-19 |  |  | Comparables_overflow_19_07_2023_Sharan-N-P
368 | 2023-07-19 | TASK |  | remove length checking code in full address for posting |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-07-19 | 2023-07-19
369 | 2023-07-20 | ISSUE | Live campaign | few addresses are repeating in stannp |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | will monitor stannp for few days
370 | 2023-07-20 | TASK | Report | on market comparable page: add list date on report add a small image of the properties |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-26 | 2023-08-04 |  | designing of page started - Abhay ----------------- Abhay work completed, sharan will start July 31 ----------------- updated Aug 7: * please change the text for price to Listing Price - https://tinyurl.com/27l4gxk6 * listing spelling error - https://tinyurl.com/2dm7lnwk | abhay-july25 No370_Design_change_Onmarket_report_page_31_07_2023_Sharan-N-P
371 | 2023-07-20 | ISSUE | Live campaign | edit address - when we click on remove and then uncheck it shows please enter valid postcode message even if there is no issue |  | SANDEEP | COMPLETED | URGENT
372 | 2023-07-21 | DISCUSS | Price Drop | when we look at the listing activity it deviates from the back to market logic Flat 2, 260, Holloway Road, London, N7 6NE 73, Bride Street, London, N7 8RN |  | RIJO | COMPLETED | [6 empty] | monitoring in live
373 | 2023-07-22 | ISSUE | Detail Page | already contacted pop up when we click on Add to campaign button does not close when we Yes, Add to campaign button (the property gets added to campaign but the pop up doesnt close) https://tinyurl.com/2kx8mgzm |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | no373-addtocampaign-sandeep-25july2023
374 | 2023-07-22 | ISSUE | Live campaign | second instruction - when removing properties the pop up doesnt close after clicking on Remove properties button in the pop up |  | SANDEEP | COMPLETED | MEDIUM
375 | 2023-07-22 | ISSUE | Detail Page | add to campaign button doesnt change to Added to campaign after adding the property to campaign, only if we refresh the button changes All properties, withdrawn, back to market, price drop, sold/under offer |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | no373-addtocampaign-sandeep-25july2023
376 | 2023-07-22 | ISSUE | Export csv | export file - there is a count mismatch withdrawn, probate, back to market |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-07-31 |  | 2023-08-25 | reopened on Aug 22: 1. withdrawn, probate, back to market - count in export file is not correct 2. in back to market export file the address field is blank for some | no376-export-csv-issue-sandeep-31july2023 no376-2-export-targeted-sandeep-10aug2023
377 | 2023-07-24 | ISSUE | Listing Page | in the property type column, the sqft is shown 72, Gunner Lane, Rubery, Birmingham, Worcestershire B45 9EX |  |  | COMPLETED
378 | 2023-07-24 | ISSUE | Detail Page | sold history section is missing in the detail page, properties have sold history but it is not shown in the detail page |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | updated Aug 1: sold history is missing for some addresses 22a, Lancelot Road, Wembley, London, HA0 2BP Flat 6, 77, London Road, High Wycombe, Buckinghamshire HP11 1BN Apartment 31, Alexandra House, 47, Rutland Street, Leicester LE1 1SE these are only few examples, there are many other properties with sold history missing ------------------------------------- updated Aug 15: sold section is missing for few properties | no-378-sold-history
379 | 2023-07-25 | ISSUE | Report | even if we select the property type in market analysis page and in the text below comparable page it is blank 10 Creskeld Garth, Leeds, LS16 9EW |  | SHARAN | COMPLETED | MEDIUM | [6 empty] | Property_Type_Trait_07_08_2023_Sharan-N-P
380 | 2023-07-25 | ISSUE | Dashboard | price drop count is not correct |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-08-02 |  |  | please speak to Ashik for help | no-380-price-drop-count-2
381 | 2023-07-26 | ISSUE | Listing Page | campaign history pop up: if the user selects a campaign and then click on the back button, they are redirected to the detail page of the property which was last opened by them all properties, withdrawn, back to market, price drop, sold/under offer |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-07-31 |  |  |  | no-381-campaign-popup
382 | 2023-07-26 | SUGGESTION | Listing Page | remove info icon beside View button in listing page |  | ABHIJITH | COMPLETED | LOW | [6 empty] | no-382-icon
383 | 2023-07-26 | ISSUE | Detail Page | property type of comparables shown in the detail page is not correct 63, Whitney Road, London, E10 7HG - end of terrace house but in detail page comparables shown are for semi detached |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | discuss with Jinto on the code | no-376-soldhistroy-propertytype
384 | 2023-07-26 | ISSUE | Detail Page | the property type, price and Days on Market in the detail page is different than the listing page 5, Peary Place, London, E2 0QW - https://prospectingtool.letsbidproperty.co.uk/properties/p-95407 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | will be corrected only when the cron is completed
385 | 2023-07-26 | DISCUSS | Detail Page | the property type in the listing and detail page are different 5, Derbyshire Street, London, E2 6HQ - https://prospectingtool.letsbidproperty.co.uk/properties/w-422969 4, Virginia Road, London, E2 7NQ - https://prospectingtool.letsbidproperty.co.uk/properties/w-1879883 |  | RIJO | CLOSED | [6 empty] | will be looking at this issue from the posting end because of large data
386 | 2023-07-28 | SUGGESTION | Dashboard | pop up: 1.warning pop up shown if we dont check the print preview option is in old format - quick send in dashboard and quick send in detail page 2. probate detail page - delete message for comment is still the old format 3. low balance message in dashboard |  | SANDEEP | COMPLETED | LOW |  |  | 2023-10-02 |  | 2023-10-09 |  | no386-old-format-issues-sandeep-02oct2023
387 | 2023-07-31 | ISSUE | Probate properties | foreign language names need to be recognised https://prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6IjJFNkFoa21LN2NpNUVJZGlrbEU0VlE9PSIsInZhbHVlIjoiMTJpbmcvSjNURUVSMkswK0g1a1pCZz09IiwibWFjIjoiYjVjMTBkOTkzM2U5MTQyM2EyZDMzNGExMzgyMTA4M2UyMDU0MWViZGFmMDA5OGMwOTE2NmEyOWM4ZDk5YmZmZSIsInRhZyI6IiJ9 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-08-02 | 2023-08-03
387 | - |  | Listing Page | listing page |  |  | CLOSED | MEDIUM
388 | 2023-07-31 | TASK | Targeted Properties | 20-20 button on targeted |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-18 |  |  | updated Nov 8: please check this https://docs.google.com/spreadsheets/d/1WjnUjBmxpyUdjSZ_jo_ebfFABn2g78Pkl4hRvaLRBlg/edit?pli=1#gid=51567162&range=546:553
389 | 2023-07-31 | TASK | Probate properties | Quick send on probate |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-09-22 | 2023-10-06 | 2023-10-31 | updated oct 23: 1. when we click on print preview the loader is not shown - cleared 2. addresses are shown in a single line in the letter - this happens when the address is given like Executor/Administrator Address in the detail page and also when it is given as Company Name and Address eg: 24 Oving Close, Luton, LU2 9RN 52 Marina Place, Kingston Upon Thames, KT1 4BH - cleared 3. locality is not shown in the address when doing quick send (please refer to edit address in live campaign - probate) - cleared 4. texts in the bracket doesnt need to be shown in the letter (please refer to edit address in live campaign - probate) - cleared 5. quick send pop up - spelling error in the tag, please change to Executor Address - cleared 6. probate detail page - 2 campaigns are shown in the campaign history section in the detail page when we do quick send local print/bulk mail | no_389_quiksend_probate_22septanisha
390 | 2023-07-31 | TASK | Probate properties | last sold date and last sold price on probate listing and detail page also add flag if the property was sold in the last 6 months |  | SANDEEP | COMPLETED | URGENT |  |  | 2023-08-16 | 2023-08-31 | 2023-09-01 | updated Aug 25: * property has sold history but it's not shown in probate listing 28 Elms Park Avenue, Sodbury, Wembley, HA0 2RS - https://www.rightmove.co.uk/house-prices/details/england-15870406?s=57bac087538c65048baa868ecf619f690267183aba9217f9c32c5b79135ffbba#/ 88b Rugby Avenue, Wembley, HA0 3DJ - https://www.rightmove.co.uk/house-prices/details/england-125663249-45722028?s=ecfbec465ce87547c7b20c6c715cbc02dcc5733eb74013144a46840edb27f511#/ * if the property has multiple sold data, should all the sold history be shown? - show only the last sold date and last sold price, no need to show the rest * tag - Sold this year | no390-probate-sold-date-sandeep-09aug2023
391 | 2023-08-01 | ISSUE | Report | 7, Connaught Avenue, East Barnet, Barnet, London EN4 8PJ -> when we check in epc the type is semi detached bungalow but in report the comparables shown are for terraced 67, Stuart Road, Market Harborough, Leicestershire LE16 9PJ |  | SHARAN | COMPLETED | MEDIUM |  |  |  | 2023-08-21 | 2023-08-25 | Aug 16: comparable property - properties shown are terraced | No391_Comparable_uv_source_disconnected_17_08_2023_Sharan-N-P
392 | 2023-08-01 | ISSUE | Detail Page | property type is given in the listing page but in the detail page it's blank Apartment 4, 5, Rotton Park Road, Birmingham, West Midlands B16 9JH - https://prospectingtool.letsbidproperty.co.uk/properties/w-1686757 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | updated Aug 3: property type is blank in detail page | no-392-no-property-type
393 | 2023-08-01 | ISSUE | Detail Page | in the detail page for some properties the type is given as NO DATA! https://prospectingtool.letsbidproperty.co.uk/properties/p-95407 |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-08-01 |  |  | updated Aug 2: still shows NO DATA! | no-392-nodata-ptype
394 | 2023-08-01 | ISSUE | Properties | different listings are shown for the address 135, Woodbridge Road, Barking, London, IG11 9BB - https://prospectingtool.letsbidproperty.co.uk/properties/w-471662 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | listing data provided the property type
395 | 2023-08-01 | ISSUE | Report | crime rate data not correct |  | SHARAN | COMPLETED | HIGH |  |  | 2023-08-01 | 2023-08-01 |  |  | No_395_Crime_rate_graph_01_08_2023_Sharan-N-P
396 | 2023-08-01 | ISSUE | Properties | postcode is not shown with the address Flat 4, Northfield House, 142 |  | ABHIJITH | COMPLETED | MEDIUM
397 | 2023-08-02 | ISSUE | Properties | tagged as exclusive but it is not shown in the detail page |  | ANISHA | COMPLETED | MEDIUM
398 | 2023-08-02 | ISSUE | Live campaign | local print - the preview and letter generated is not same |  | UNASSIGNED | CLOSED | MEDIUM
399 | 2023-08-02 | ISSUE | Live campaign | probate campaign - in the preview for local print, the preview is shown only for executor address |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-08-07 | 2023-08-25 | 2023-09-01 | updated Aug 8: if we remove any address, when we preview the letter it shows both the letters and then when we try again it shows the correct letter preview (only for local print) ---------------------------------------------- reopened Aug 22: preview is shown only for executor address | no399-probate-campaign-preview-sandeep-07aug2023 no399-2-probate-preview-sandeep-11aug2023 no399-3-probate-preview-sandeep-15aug2023 ------------- no399-4-probate-preview-sandeep-24aug2023
400 | 2023-08-02 | ISSUE | Live campaign | quick send - for company owned properties the preview is shown only for company address |  | UNASSIGNED | CLOSED | MEDIUM
401 | 2023-08-03 | ISSUE | Listing Page | properties that have already been contacted doesnt get added to the campaign, even if we click on Yes add all properties only the property that hasnt been contacted gets added to campaign |  |  | COMPLETED | [6 empty] | need to check again,
402 | 2023-08-04 | ISSUE | Live campaign | the list date shown in the live campaign is not correct - second instruction marketing and 20-20 campaign please check in live campaign and campaign history |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-11 | 2023-09-11 | 2023-09-12 |  | no-402-listed-date
403 | 2023-08-04 | ISSUE | Report | Please look into reports section for properties where agents have to input own custom values Even when agents input the values it sometimes doesnt show comparables please can we make sure that comprables are shown always Agents have to redo the report and the second time they input values the comparbales then show please test this throughly as alot of agents still end up doing best price guides on rightmove as the comprables dont show |  | SHARAN | COMPLETED | MEDIUM |  |  |  |  | 2023-08-25
404 | 2023-08-08 | ISSUE | Report | in on market comparable page, the report logo is not shown |  | SHARAN | COMPLETED | LOW |  |  | 2023-08-08 | 2023-08-08 |  |  | No404_Report_logo_missing_08_08_2023_Sharan-N-P
405 | 2023-08-08 | TASK |  | to fetch property type in a uniform logic |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-08-08 |  |  |  | Property_Type_Trait_07_08_2023_Sharan-N-P
406 | 2023-08-11 | TASK | Report | after report is generated the agent can email report and also a link which they can send to the customer and once the customer opens the report the agents will be notified. |  | ANISHA | COMPLETED | HIGH |  |  | 2023-10-09 |  |  |  | no406-new-report-copylink-openupdate_anisha09oct
407 | 2023-08-11 | ISSUE - DEMO | Letter management | letter management - the file name after uploading letterhead https://tinyurl.com/2dbojofw https://tinyurl.com/24cupy5t |  | ANISHA | COMPLETED |  |  |  | 2023-09-21 | 2023-09-21 | 2023-09-22 |  | no407-filename-uploadingletterhead-anisha20September
408 | 2023-08-11 | ISSUE - DEMO | Targeted Campaign | local print is not working, shows something went wrong |  | ANISHA | COMPLETED | MEDIUM | [5 empty] | updated sep 21: local print is not working for targeted campaign in demo, it's shows letterhead does not exist -------------------------------------- updated sep 29: still shows letterhead does not exist when we click on print letterhead and content, not working -------------------------------------- Update Oct 16: please create a new branch and push changes to the branch | n0408-localprint_targettedcampaign_issue_anisha21sept
409 | 2023-08-11 | ISSUE - DEMO | Campaign History | Second Instruction marketing - shows a warning pop up when we click on bulk mail campaign history |  | ANISHA | COMPLETED | MEDIUM | [5 empty] | 26 sep: ======= Add new branch to merge to live current branch has 56 commits | no409secondinstructionmarketting-bulkmail-issue-21SeptAnisha
410 | 2023-08-14 | SUGGESTION | Dashboard | even if the agent has selected only few addresses, when we select a trigger it changes for all addresses |  | UNASSIGNED | COMPLETED | LOW
411 | 2023-08-14 | ISSUE | Listing Page | bedroom count is different in the listing and detail page 21, Donne Place, London, SW3 2NG 63, Judge Street, Watford, Hertfordshire WD24 5AN |  | ABHIJITH | COMPLETED | LOW |  |  | 2023-09-13 | 2023-09-14 |  |  | no-411-bedrooms
412 | 2023-08-14 | ISSUE | Sold- Under offer | on market tag is shown for a listing https://prospectingtool.letsbidproperty.co.uk/properties/s-1882997 - 126, Florence Road, London, SW19 8TN |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-13 | 2023-09-13 |  | zoopla stc update not received/Please check other postcodes this post code has been uopdated
413 | 2023-08-15 | SUGGESTION | Report | on market comparable and on market rental pages - sort the list by latest listed first |  | SHARAN | COMPLETED | [7 empty] | No413_On_market_rental_page_sort_listed_date
414 | 2023-08-15 | TASK | Report | when generating reports for targeted properties, the property type is already mentioned for most of the properties can we not display it as Current Property Type |  | SHARAN | COMPLETED
415 | 2023-08-15 | ISSUE | Targeted Properties | If the listing was filtered using minimum and maximum price, upon returning to the listing page from the detail page, the minimum/maximum filters will be cleared. |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-08-30 | 2023-08-30 | 2023-09-01 | if a user is on a page other than the first one and clicks the back button, they will be directed back to the first page when the listing is filtered using min and max filter | no415-min-max-filter-cleared-sandeep-30aug023
416 | 2023-08-15 | SUGGESTION | Quick Send | quick send in dashboard and detail page - after clicking on local print buttons the pop up doesn't close and also the buttons are not disabled agent can click on local print multiple times |  | SHARAN | COMPLETED | LOW |  |  | 2024-02-26 | 2024-03-07 | 2024-03-20 | updated Mar 1: in the dashboard when doing quick send bulk mail it keeps loading, local print works | No416_quick_send_button_inactive_07_03_2024_Sharan_N_P
417 |  | ISSUE |  | -- |  |  | CLOSED
418 | 2023-08-17 | TASK | Planning Application | planning application (similar to propmarker) option to send letters |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-12-04
419 | 2023-08-17 | ISSUE | Report | Flat 2, Belgravia Mansions, Frimley Road, Camberley, Surrey, GU15 3BA 409, London Road, Camberley, Surrey, GU15 3HL 130, Old Street, Camberley, Surrey, GU15 3HL in the report for this address, data in Neighbouring Planning History goes into the Market analysis page https://tinyurl.com/25bbeepa |  | SHARAN | COMPLETED | URGENT | [6 empty] | No419_Planning_data_overlapping_pages_17_08_2023_Sharan-N-P
420 | 2023-08-17 | TASK | Live campaign | add locality line and also remove any duplicate data in edit address popup |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-08-30 | 2023-08-30 | 2023-09-01 |  | no420-add-locality-sandeep-23aug2023
421 | 2023-08-21 | TASK | Website | update the sample property report on the website to show the new changes e.g images for comps and letting comps please https://prospectingtool.letsbidproperty.co.uk/report/report_storage/report_2271_210820230443108342.pdf |  | RIJO | COMPLETED | HIGH
422 | 2023-08-21 | ISSUE | Profile | after editing someones profile the address then changes on the reports and comes out in one line |  | SANDEEP | COMPLETED | HIGH | [6 empty] | no422-profile-address-sandeep-19sep2023
423 | 2023-08-21 | ISSUE | 20-20 Campaign | address repeating in neighbor properties list 35a, Leconfield Road, London, Greater London N5 2RZ Flat 3, Liberty Court, 141, Great North Way, London, Greater London NW4 1PR https://tinyurl.com/25zyc4p3 |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | update Sep 11: in the neighbor properties list, some addresses are repeating
424 | 2023-08-21 | TASK | Report | report - option to remove estate agents name if the customer wants to - just blank it out if it's not required (comparables) |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-19 | 2023-09-20 | 2023-09-22 |  | no-424-estate-agent
425 | 2023-08-21 | ISSUE | Profile | mobile number to send notification field - if the user clears the number and saves it, save it as NULL |  | ANISHA | COMPLETED | MEDIUM | [5 empty] | please speak to Sharan if any doubt | 425_temp_anisha
426 | 2023-08-21 | ISSUE | Company Owned | property is tagged as Company owned in report but not in the listing 30a, Chiswick High Road, London, W4 1TE 5, Portman Road, Kingston Upon Thames, London, KT1 3DY 6, Birinus Close, High Wycombe, Buckinghamshire HP12 3LZ |  | ABHIJITH | COMPLETED | LOW |  |  | 2023-09-14 |  | 2023-10-02 | updated oct 2: in the listing these properties are not tagged as company owned | no-426-company-ownd
427 | 2023-08-21 | ISSUE | Report | upload image - if the image size exceeds 1mb, please show a warning message and also mention the maximum size beside the upload functionalities |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-08-25 | 2023-08-25 | 2023-08-25
428 | 2023-08-21 | ISSUE | Report | on market comparable - should the property type be mentioned with the addresses? |  | RIJO | COMPLETED
429 | 2023-08-22 | ISSUE | Report | property has floor plan but it's not shown when generating the report https://www.prospectingtool.letsbidproperty.co.uk/properties/b-687727 https://www.prospectingtool.letsbidproperty.co.uk/properties/b-722754 |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-08 | 2023-09-08 | 2023-09-12 | same as 335
430 | 2023-08-23 | ISSUE | Local Print | the house number is not on the same line as the road name |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-09-01 | 2023-09-01 | 2023-09-12 |  | no431-twenty20-edit-address-sandeep-31aug2023
431 | 2023-08-23 | ISSUE | Local Print | 20-20 edit address is not working properly, the changes made are not reflected on the letters |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-08-31 | 2023-09-01 | 2023-09-12 | updated Sep 4: if we edit the address when we print all the letters are not shown ---------------------------------------------- updated Sep 6: in campaign history the changes made are only reflected for the neighboring properties of the first address shows a warning pop up when we open the campaign in campaign history, happens when we select 2 addresses ---------------------------------------------- updated sep 7: - postcodes are not shown in campaign history - when we preview the letter, in campaign history listing a campaign is created with status as Sending - in edit address even if the address is in 2 lines, it shows a warning message - show the warning message in red ---------------------------------------------- updated sep 8: - preview is not shown when sending bulk mail, it just keeps loading - in local print preview the first line is not aligned with the rest (only in the preview) - shows server error when we do 20-20 bulk mail ---------------------------------------------- updated sep 11: - in the campaign history of 20-20 bulk mail the status of some properties are pending and for some are success ---------------------------------------------- updated sep 12: if we select different triggers, in campaign history the same trigger is shown for all address | no431-twenty20-edit-address-sandeep-31aug2023
432 | 2023-08-24 | ISSUE | Local Print | when we remove the first address and view pdf preview, the campaign listing is shown in the preview pop up for second instruction and probate |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-08-31 | 2023-09-01 | 2023-09-01 |  | no399-4-probate-preview-sandeep-24aug2023
433 | 2023-08-24 | ISSUE | Report | property has epc but it's not shown in the report 92, Turkey Street, Enfield, Greater London, EN1 4PT |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-20 | 2023-09-21
434 | 2023-08-24 | SUGGESTION | Sold- Under offer | in the detail page Add to 20-20 campaign button is not given |  | SANDEEP | COMPLETED | LOW |  |  |  |  | 2023-10-16 | updated Oct 4: Add to 20-20 campaign button is not shown in the detail page of Sold/under offer property -------------------------- updated oct 5: The "Add to 20-20 Campaign" button should not be displayed on the withdrawn, price drop, and back-to-market detail pages. It is only necessary on the "sold under offer" detail page. | no434-twenty20-button-sold-under-offer-sandeep-03oct2023
435 | 2023-08-25 | ISSUE | Export csv | withdrawn, back to market, price drop, sold/under offer: if we enable exclude agencies and export, in the exported file the agencies are not excluded |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-07 | 2023-09-08 | 2023-09-11 |  | no435-export-csv-sandeep-07sep2023
436 | 2023-08-25 | ISSUE | Profile | when we upload any image for profile image and company icon and submit it shows server error |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-13 | 2023-09-13 | 2023-09-13
437 | 2023-08-30 | ISSUE | Report | we need to make sure we're getting the current property images, we are getting the old images for some addresses 94, Morley Road, London, E10 6LL 15, Hewison Street, London, E3 2HZ |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-09-08 | 2023-09-08 | 2023-09-12 |  | no-437-report-image
438 | 2023-08-30 | TASK | Report | remove the satellite image feature (cover image) |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-09-06 | 2023-09-06 | 2023-09-06
439 | 2023-08-30 | ISSUE | Report | Planning Data on Property - the date is not correct 2 Berkshire Gardens London N13 6AB Cator Lodge, South Row, London, SE3 0NU - https://planning.royalgreenwich.gov.uk/online-applications/applicationDetails.do?keyVal=_GRNW_DCAPR_116745&activeTab=summary |  | ABHIJITH | COMPLETED | MEDIUM |  |  |  |  | 2023-10-02 |  | no-439-planning-date
440 | 2023-08-30 | ISSUE | Report | Planning Data on Property - if decision issued date is not available should it be 01-01-1970? |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-21 |  | 2023-10-02 | update 2 oct 2023: ------------------------ changes to be commited to new branch and pushed in stagging and live | no-440-planning-date , no-440-planning-date-new
441 | 2023-09-01 | ISSUE | Properties | random character is shown with the estate agent name if it has a registered trademark symbol LV PROPERTY Â® - http://tinyurl.com/29rgtvww Love Your Postcode https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2343436 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-1043980 |  | SANDEEP | COMPLETED | LOW |  |  | 2023-10-04 |  |  | updated oct 10: check after next run -------------------------------- updated oct 12: transferred to Vishnu ----------------------------- updated oct 18: B1, B17, B15 Updated on 07 Aug 2024 ------------------------------- Current issue fixed. Need to find agent name with special character in db and fix it by query with regex.
442 | 2023-09-01 | TASK | Live campaign | show the total campaign count in all 4 tabs |  | SANDEEP | COMPLETED | HIGH |  |  |  |  | 2023-09-22 |  | no442-campaign-count-sandeep-18sep2023
443 | 2023-09-01 | ISSUE | Listing Page | if any of the address selected does not have neighbouring properties, the contacted properties pop up does not close even when we click on Add all selected properties |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | updated sep 27: - shows success message for 20-20 and "No neighbours found" pop up is shown when we add properties to 2nd instruction campaign | no442-campaign-count-sandeep-18sep2023
444 | 2023-09-01 | ISSUE | Live campaign | for company owned properties, even if we remove either the property or executor address in the local print preview both addresses are shown |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-04 | 2023-09-06 | 2023-09-11 |  | no444-local-print-preview-sandeep-04sep2023
445 | 2023-09-01 | ISSUE | Probate properties | few of the addresses have sold history but it's not shown in the probate listing |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-11 | 2023-09-29 | 2023-10-09 | updated sep 28: 9 Craigmur Park Wembly Middlesex, HA0 1NY Flat 5, 249 Goldhurst Terrace, London, NW6 3EP Flat 1, 66 Aberdare Gardens, London, NW6 3QD | no445-sold-history-for-probate-sandeep-08sep2023
446 | 2023-09-01 | ISSUE | Probate properties | sold this year tag and in campaign tags are not spaced properly https://tinyurl.com/26jd2qyn |  | SANDEEP | COMPLETED | LOW |  |  | 2023-09-08 | 2023-09-08 | 2023-09-11 |  | no446-sold-tag-space-issue-sandeep-07sep2023
447 | 2023-09-01 | TASK | Website | add video to the website - video sent in mail |  | ABHAY | COMPLETED | URGENT
448 | 2023-09-01 | TASK | Website | a separate tab/section where agents can click to look at our testimonials/reviews. |  | ABHAY | COMPLETED | MEDIUM
449 | 2023-09-04 | ISSUE | Probate properties | if the executor address has - or ", it is shown as ? in the detail page and in edit address http://tinyurl.com/2ann5h66 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-13 |  |  | forwarded to data entry team on Sep 13
450 | 2023-09-04 | ISSUE | Campaign History | probate campaign history and second instruction campaign history - when sending letters to multiple address, even if an address fails the delivery status of that address is the same as the rest http://tinyurl.com/23q6xvox |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-26 | 2023-09-27 | 2023-09-27 | updated sep 27: shows a letter for failed address | no450-fails-the-delivery-status-26sep2023
451 | 2023-09-05 | ISSUE | Properties | same addresses are not merged 57, West Road, Sawbridgeworth, Hertfordshire CM21 0BL 140, Derby Road, Melbourne, Derby, Derbyshire DE73 8FL 43, Danbrook Road, London, SW16 5JY 31, Gullick Way, Burntwood, Staffordshire WS7 1FH 10, Eton Close, Burton-on-trent, Staffordshire DE14 2SU |  | ABHIJITH | COMPLETED | LOW | [5 empty] | 140, Derby Road, Melbourne, DE73 8FL 140, Derby Road, Melbourne, Derby, Derbyshire DE73 8FL - This type not work
452 | 2023-09-06 | ISSUE | Report | the map on the front page is missing when the toggle is enabled |  | RIJO | COMPLETED | HIGH |  |  | 2023-09-07 | 2023-09-07 | 2023-09-07
453 | 2023-09-06 | TASK | Report | there should be an option for the user to choose the primary image multiple images of the property will be listed and the agent can select from those |  | UNASSIGNED | DUPLICATE TASK | MEDIUM | [5 empty] | need Abhay's help
454 | 2023-09-07 | TASK | Report | report typing interval |  | RIJO | COMPLETED | MEDIUM
455 | 2023-09-07 | ISSUE | Probate properties | by default sort the listing by latest publication date |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-09-07 | 2023-09-08 | 2023-09-11 |  | no446-sold-tag-space-issue-sandeep-07sep2023
456 | 2023-09-07 | TASK | Report | change the wording and title for satellite image section to Title - Map Marker wording - Click here to add markers on the map page |  | RIJO | COMPLETED | MEDIUM | [5 empty] | updated sep 14: please change the title of that section
457 | 2023-09-07 | ISSUE | Price Drop | property is listed under price drop but in the detail page price reduced activity not shown Flat 13, Vaynor House, Williamson Street, London, N7 0ST 21, Gregories Close, Luton LU3 1DL 18, Devonshire Road, London, E16 3NB 7, Connaught Avenue, East Barnet, Barnet, London, EN4 8PJ 23, Daneland, Barnet, London, EN4 8PX 8, Latymer Close, Braybrooke, Market Harborough, Northamptonshire LE16 8LN 213, Anstey Lane, Leicester LE4 0FH 160, Hykeham Road, Lincoln, Lincolnshire LN6 8AW |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-09-08 | 2023-09-08 | 2023-09-11 |  | no-457-pricedrop
458 | 2023-09-07 | ISSUE | Live campaign | not able to send bulk mail all the letters are shown as failed |  | RIJO | COMPLETED | URGENT | [5 empty] | stannp balance was low
459 | 2023-09-07 | ISSUE | Campaign History | publication date is not correct, it shows the current date |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-08 | 2023-09-08 | 2023-09-11 |  | no459-publication-date-sandeep-08sep2023
460 | 2023-09-04 | TASK | Website | brochure for agents |  | ABHAY | COMPLETED | URGENT |  |  | 2023-09-07
461 | 2023-09-08 | TASK |  | negative balance checking in master job |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-09-14 | 2023-09-18 |  | updated sep 18: showing server error when doing 20-20 bulk mail
462 | 2023-09-09 | ISSUE | Properties | 94, Camlet Way, Barnet, London, EN4 0NX different properties are shown, 1 is 7 bedroom the other is 6 bedroom it doesnt show reduced on date and the added date is different |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-02 |  | 2023-10-09 | updated Oct 4: it's still the same | no-462-bedroom no-462-bedroom-2
463 | 2023-09-09 | ISSUE | Probate properties | 2/31 Mountain Ash Circuit, Robina Qld 4226, Address On The Will 12 Deerswood Avenue, Hatfield, HERTFORDSHIRE AL10 8RX please check if there are other addresses with the text "Address on the will" |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-13 | 2023-09-13 | 2023-09-13
464 | 2023-09-09 | ISSUE | Price Drop | the sale price for the first activity is not correct and also it shows 0 as the price for reduced activity 1, Lambe Close, Fairford, Gloucestershire GL7 4FL 39, Bettertons Close, Fairford, Gloucestershire GL7 4HY 12, Rose Villas, Lechlade, Gloucestershire GL7 3BE 66, Valley Road, Welwyn Garden City, Hertfordshire AL8 7DN |  | UNASSIGNED | CLOSED | MEDIUM | [5 empty] | updated sep 14: found new patterns
465 | 2023-09-09 | ISSUE | Price Drop | price has not been reduced for the property but it is listed under price drop and also has reduced activity 8, Birches Rise, High Wycombe, Buckinghamshire HP12 3AQ |  | ABHIJITH | CLOSED | MEDIUM |  |  | 2023-09-11 |  |  | updated sep 14: found new patterns
466 | 2023-09-09 | ISSUE | Wallet/Credit | Alistair Wiltshire - wm-sales@cjames.co.uk this account has negative credit, please make the balance 0 |  | RIJO | COMPLETED | HIGH
467 | 2023-09-09 | ISSUE | Properties | property is not withdrawn but it shows the withdrawn activity as the last activity 160, Hykeham Road, Lincoln, Lincolnshire LN6 8AW 5, Herdsmans Close, Littlethorpe, Leicester, Leicestershire LE19 2AE 8, Latymer Close, Braybrooke, Market Harborough, Northamptonshire LE16 8LN 7, Connaught Avenue, East Barnet, Barnet, London, EN4 8PJ |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-10 |  | 2023-11-27 | updated oct 17: other activites are not shown in listing activity ------- updated oct 18: still has withdrawn as last activity 160, Hykeham Road, Lincoln, Lincolnshire LN6 8AW --------------------------------------------- updated nov 13: 118, Stoneleigh Street, Oldham, Greater Manchester OL1 4LF 10, Pierce Street, Oldham, Greater Manchester OL1 4JH
468 | 2023-09-09 | ISSUE | Report | company owned property not tagged in report 10a, Austin Avenue, Bromley, Kent, BR2 8AJ |  | ABHIJITH | COMPLETED | LOW |  |  | 2023-09-23 | 2023-09-23
469 | 2023-09-15 | TASK | Direct Mail Anywhere | Direct Mail Anywhere - targeted on road (Send anywhere) |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-10-31 |  |  |  | no469_sendanywhere_module_anisha31oct
470 | 2023-09-13 | ISSUE | 20-20 Campaign | adding locality in Neighbour Properties list and removing county |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-09-13 | 2023-09-13 | 2023-09-13
471 | 2023-09-18 | ISSUE | Properties | the list date shown in the listing and detail page are different in all properties page when the property has older listings 282, Crawley Green Road, Luton LU2 0SJ 36, Rathbone Road, Wavertree, Liverpool, Merseyside L15 4HQ - in the listing page it's given as 13-01-2023 and in the detail page it's 13-09-2023 Keepers Cottage, Upper Barnhill, Hunton, Maidstone, Kent ME15 0QL 60, Curtis Road, Hounslow, London, TW4 5PT Flat 36, Marlborough Mansions, Cannon Hill, London, NW6 1JS |  | UNASSIGNED | CLOSED | MEDIUM | [5 empty] | related to task 478
472 | 2023-09-18 | ISSUE | Withdrawn | the property is Under offer but on the platform it is marked as withdrawn Flat 404, Chalmers House, York Road, London, SW11 3QT - https://prospectingtool.letsbidproperty.co.uk/properties/w-388720 |  | ABHIJITH | COMPLETED | MEDIUM | [5 empty] | outcode not running for zoopla as there are more than 1000 properties
473 | 2023-09-18 | ISSUE | Back to Market | shows a warning pop up when we click on back to market in the menu |  | ABHIJITH | COMPLETED | URGENT |  |  | 2023-09-18 | 2023-09-18
474 | 2023-09-18 | ISSUE | Price Drop | shows a warning pop up when we click on price drop in the menu |  | ABHIJITH | COMPLETED | URGENT |  |  | 2023-09-18 | 2023-09-18
475 | 2023-09-18 | ISSUE | Price Drop | property is withdrawn but listed under price drop, z activity not updated Flat 13, Ramar House, Hanbury Street, London, E1 5JH |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-11 |  |  | E1 outcode not running for zoopla as there are more than 1000 properties
476 | 2023-09-18 | ISSUE | Quick Send | If a user initially selects a few addresses, previews them, and then proceeds to deselect or add more addresses, the letters will be sent only to the addresses that were initially selected. to get the issue: 1. select few addresses from the bulk mail list 2. preview the letter 3. select more addresses or deselect addresses 4. send bulk mails |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-16 |  | 2023-10-27 |  | no-476-quick-send
477 | 2023-09-19 | ISSUE | Wallet/Credit | multiple refund on 20-20 |  | RIJO | COMPLETED | HIGH |  |  | 2023-09-19 |  |  | multiple refund stopped, need to add a check | no477_multiple_refund_issue_Rijo_20Sep2023
478 | 2023-09-19 | ISSUE | Dashboard | 16 weeks or more count not correct | Web | RIJO | NOT STARTED | MEDIUM | [5 empty] | updated Oct 2: only properties listed upto 142 days need to be shown ----------------------- updated Oct 4: count is still not correct
479 | 2023-09-19 | ISSUE | 20-20 Campaign | all letters are not going through to stannp addresses with 3 lines are not reaching stannp |  | RIJO | COMPLETED | HIGH |  |  | 2023-09-20 | 2023-09-20 | 2023-09-21 |  | no479_20_20_letters_not_going_to_stannp_Rijo_20sep2023
480 | 2023-09-19 | ISSUE | Live campaign | probate local print preview - there is a delay in showing Preparing preview pdf loader after clicking on preview button |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-09 |  | 2023-10-27 | updated sep 20: even if there are many addresses in the other campaign tabs, the preview loader is shown when we click on preview button. there is a delay only for probate campaign | no480-print-preview-delay-sandeep-09oct2023
481 | 2023-09-19 | ISSUE | Live campaign | second instruction local print preview - when many addresses are selected for local print, when viewing the preview it loads multiple times and then only can the user see the letter preview preview loop not ending |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-22 |  | 2023-10-02 |  | no481-preview-loop-not-ending-sandeep-22sep2023
482 | 2023-09-19 | ISSUE | Probate properties | some addresses are missing Water Hall Care Centre, 44 Winsford, MILTON KEYNES, Buckinghamshire MK4 1BN - Sidney Beard 6 Firbrock Avenue Chester CH5 4PE - Barbara Foley 89 Helmsley Road, Leicester, LE2 6QH - Kenneth Garner 296 Melbourne Road, Ibstock, Leicestershire, LE67 6NR - George Ball Kew House Nursing Home, 58 Spencer Hill Road, Wimbledon, SW19 4EL - Ann Salvadori 13 Morningside Close Derby Derbyshire DE24 9JQ - John Gordon |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | 22 sep: Not clean address provided for suggestions from gassete API
483 | 2023-09-19 | SUGGESTION | Live campaign | second instruction bulk mail list - show Company Owned and Company Address tag in the bulk mail list as well (similar to quick send list) remove the loading circle in bulk mail after table load |  | SHARAN | COMPLETED | LOW |  |  | 2024-02-26 | 2024-02-26 | 2024-03-06 |  | No483_Bulk_send_company_tag_26_02_2024_Sharan_N_P
484 | 2023-09-19 | ISSUE | Targeted Properties | if the property is already added to targeted campaign, please make sure Added to Targeted Campaign button is disabled |  | ABHIJITH | COMPLETED | LOW |  |  |  |  | 2023-10-16 | updated oct 16: button not disabled after adding to targeted campaign | no-484-targeted-campaign-2
485 | 2023-09-20 | SUGGESTION | Wallet/Credit | for credits that have been refunded, please make sure appropriate titles are given for probate, targeted and 20-20 refunds for all 4 campaign refunds it's given as Bulk Mail Refund |  | RIJO | COMPLETED | LOW
486 | 2023-09-21 | ISSUE | Live campaign | probate campaign - remove pop up does not close |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-21 |  | 2023-10-02 | updated sep 27: - there is a delay in showing the success pop up (please check the other campaigns) | no486-probate-campaign-remove-sandeep-21sep2023
487 | 2023-09-21 | ISSUE | Report | planning - one application is missing 77 Turkey Street Enfield EN1 4PJ https://planningandbuildingcontrol.enfield.gov.uk/online-applications/applicationDetails.do?keyVal=R8YFPUJNL8200&activeTab=summary |  | VISHNU | CLOSED | LOW
488 | 2023-09-21 | DISCUSS | Report | property has epc but it's not shown in the report 1, Waver Court, Tadcaster, North Yorkshire, LS24 9UN |  |  | COMPLETED | MEDIUM | [5 empty] | need to confirm if it's because it was recently assessed
489 | 2023-09-21 | ISSUE | Live campaign | 20-20 campaign - some addresses are shown in single line when it reaches stannp |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-09-21 | 2023-09-21 | 2023-09-21
490 | 2023-09-21 | ISSUE | Live campaign | wrong addresses are reaching stannp |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-09-21 | 2023-09-21 | 2023-09-21
491 | 2023-09-25 | ISSUE | Probate properties | posting error |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-09-25 | 2023-09-25 |  |  | no491-probate-posting-error-sandeep-25sep2023
492 | 2023-09-25 | ISSUE | Targeted Properties | sold history of the property is not correct 35a, Holdenhurst Avenue, London, Barnet, N12 0JA - https://www.zoopla.co.uk/property/uprn/200065038/ 66, Glenhurst Road, London, Barnet, N12 9UB - https://www.zoopla.co.uk/property/uprn/200047822/ 27, Broadway Street, Burton-on-trent, East Staffordshire, Staffordshire, DE14 3NB - https://www.rightmove.co.uk/house-prices/details/england-38651097?s=5fa12119666022f3d3c7a88db1156a57843653a67e2644b00686588342e672b7#/ |  | UNASSIGNED | COMPLETED | MEDIUM | [5 empty] | https://www.housepricesintheuk.co.uk/h/35A-HOLDENHURST+AVENUE-LONDON-N12+0JA https://www.homipi.co.uk/property/london/n12-9ub/66-glenhurst-road/ https://www.homipi.co.uk/property/burtonontrent/de14-3nb/27-broadway-street/
493 | 2023-09-26 | ISSUE | Detail Page | showing lorem ipsum text when we add the address to 20-20 campaign https://tinyurl.com/2cr2rkoa |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-09-27 |  | 2023-10-02 | change text to Adding to 20-20 campaign | no493-lorem-ipsum-text-sandeep-27sep2023
494 | 2023-09-26 | ISSUE | Summary | when local printing company owned property, the no. of letter sent count is not correct |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-09 | 2023-11-10 | 2023-11-27 |  | no494-letter-sent-count-summary-sandeep-08nov2023
495 | 2023-09-28 | ISSUE | Detail Page | property sold history missing EH11 143, Uplands Avenue, Connahs Quay, Deeside, Flintshire CH5 4LQ |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-10-09 |  |  | updated oct 12: only the latest sold data is shown, the rest arent displayed 94/1, Stenhouse Crescent, Edinburgh, Midlothian EH11 3HU 5, Westfield Street, Edinburgh, Midlothian EH11 2RA 6, Daisy Terrace, Edinburgh, Midlothian EH11 1PL --------------------------- updated oct 13: need to get update from Vishnu
496 | 2023-09-28 | ISSUE | Probate properties | some addresses are not in the correct format 5290 Maple Street, Vancouver, British Columbia V6m 3t5 Canada And 48 Dennington Park Road, London, NW6 1BD 37 Avenue Normandie, Fresnaye, Cape Town, South Africa And 56b Dennington Park Road, West Hampstead, London, NW6 1BD |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | #Sandeep - 29Sep2023 Updated in table
497 | 2023-09-28 | ISSUE | Probate properties | address when compared to gazette is different https://prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6IllvM3BCZnpwV1hqUDNBSVFzVDNKNVE9PSIsInZhbHVlIjoiVHhibjVJUzFTTnY0RjdDODhNRk1CQT09IiwibWFjIjoiYTVmNjNhZTFiN2JhYmI3YTEyZTdjODI3YjViMzNkMzk1NGRhZWE0MjBhYmUxMTkxMDllMTRhMmM1NmI1ZjNhMyIsInRhZyI6IiJ9 - 88 Camden Street, London, NW1 0JA - this is the address given in gazette but on our platform St Michaels Primary School is shown with the address https://www.thegazette.co.uk/notice/4348848 https://prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6InBBZTVyeTRTL3pVMVNqZDMzV1ZhUVE9PSIsInZhbHVlIjoidFFOQTVqQTlCb0ZVSHY0Y1lHL0dMQT09IiwibWFjIjoiMGMxODNiNDQ0ZDNhZTJmODc5ZjBhNmZmY2U2YmM3YjE1OWRhODQ1YTBhZjFkYTA0OTdmNWFkMGE5MjU2MjE0ZCIsInRhZyI6IiJ9 - https://www.thegazette.co.uk/notice/4160350 https://prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6InpuQ2dTYllTcHlTL2hhTGtNcTdBOUE9PSIsInZhbHVlIjoicE5vdTFVaTJ2ZE4yWEhCZVEyVzU4dz09IiwibWFjIjoiNDgyNWExNjM5ZjI1ZDJkMGIwZDhmODU0MTQxOWE1N2M3NzZkOGRmODQzZjBkMDVjNGI5OTQzNGFiYWEzNTFjOSIsInRhZyI6IiJ9 - https://www.thegazette.co.uk/notice/4286287 |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | #Sandeep - 29Sep2023 Updated in table
498 | 2023-10-02 | ISSUE | Report | report history is missing and also nothing happens when we click on confirm address |  | ABHIJITH | COMPLETED | HIGH |  |  | 2023-10-02 | 2023-10-02
499 | 2023-10-02 | ISSUE | Probate properties | there is a delay in showing the success message after adding to probate campaign |  |  | COMPLETED | MEDIUM
500 | 2023-10-02 | ISSUE | Probate properties | in the detail page after adding to campaign, success message pop up closes before clicking on Confirm button the page reloads before that |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-04 |  | 2023-10-09 |  | no500-success-message-popup-sandeep-04oct2023
501 | 2023-10-02 | ISSUE | Report | title number is not shown in the report |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-10-04 | 2023-10-05 | 2023-10-16 | updated oct 16: 23, Tennyson Road, London, NW6 7RT 38, Ordish Street, Burton-on-Trent, Staffordshire, DE14 3SA 3, Garth Close, Morden, Surrey, SM4 4NN 14, Hillcrest View, Carlton, Nottingham, Nottinghamshire NG4 1LQ 16, Judge Street, Watford, Hertfordshire, WD24 5AW 39, Stanley Road, Bootle, Merseyside L20 7BY | no-501-title-number
502 | 2023-10-02 | TASK |  | change price new Price ------------------------ 55p + 10p = 65p 65p + 13p (20% VAT) = 78p per letter (= 1 credit) |  | RIJO | COMPLETED | HIGH |  |  | 2023-10-02 | 2023-10-02 | 2023-10-02
503 | 2023-10-02 | TASK |  | add a Lettings button in the prospecting tool - on clicking they will be redirected to their lettings platform |  | ASHIK | COMPLETED | MEDIUM
504 | 2023-10-02 | ISSUE | Sold- Under offer | stc/under offer activity is repeating for some addresses First Floor Flat, 8, Sevington Street, London, W9 2QN 36, Bedford Street, Watford, Hertfordshire WD24 5DT 59, Altenburg Gardens, London, SW11 1JH 2, Hill Crescent, Halifax, West Yorkshire HX3 9PG 4, White Hart Court, Waltham Cross, Hertfordshire EN8 7EH 15, Whitby Road, Ruislip, London, HA4 9DS 4, Park Mead, Harlow, Essex, CM20 1RJ 1, Briton Street, Royton, Oldham, Greater Manchester, OL2 6AW 10, Eleanor Road, Royton, Oldham, Greater Manchester, OL2 6BS |  | SANDEEP | CLOSED | MEDIUM
505 | 2023-10-04 | ISSUE | Listing Page | there are more addresses which are company owned but not tagged in the listing 8, Birinus Close, High Wycombe, HP12 3LZ 21, Laurel Bank Mews, Bromsgrove, Worcestershire, B60 1PD |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | Related to task 741 rijo
506 | 2023-10-05 | ISSUE | Detail Page | campaign history section - 2 campaigns are shown in the campaign history section in the detail page when we do local print/bulk mail for company owned address using quick send https://tinyurl.com/yrrzczps |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-16 |  | 2023-11-06 | group campaigns if same campaign id ----------------------------- updated oct 27: still shows the campaign twice in the detail page after doing quick send bulk mail | no506-campaign-history-detail-sandeep-16oct2023
507 | 2023-10-05 | TASK | Summary | add a section for report in the summary page to show the view count and other details |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-10-11
508 | 2023-10-09 | SUGGESTION |  | delete confirmation pop up in targeted detail page and letter management is in the old format |  | SANDEEP | COMPLETED | LOW |  |  |  |  | 2023-11-06 |  | no508-confirmation-popup-in-targeted-sandeep-30oct2023
509 | 2023-10-09 | ISSUE | Report | showing a warning pop up when we go to the report page |  | RIJO | COMPLETED | URGENT
510 | 2023-10-09 | ISSUE | Wallet/Credit | Credit Cost per letter Sent and the top up credits has changed back to £0.66 |  | RIJO | COMPLETED | URGENT
511 | 2023-10-10 | ISSUE | Detail Page | property has floorplan but it shows a broken image in the detail page 18, Hill View Gardens, Halifax, West Yorkshire HX3 7BT 18, Middleton Road, Morden, London, SM4 6SD Polperro, Goole Road, Hook, Goole, East Riding Of Yorkshire DN14 5NG 21, Belgrave Gardens, London, N14 4TS |  | SHARAN | COMPLETED | LOW |  |  | 2024-02-23 | 2024-02-23 | 2024-03-12 |  | No511_property_detail_page_pdf_floorplan_23_02_2024_Sharan_N_P
512 | 2023-10-11 | ISSUE | Listing Page | the contacted properties pop up shown when we add properties to 20-20 campaign - the user is redirected to the first page if we click remove/add contacted properties |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-19 |  | 2023-10-27 |  | no512-redirected-to-first-page-sandeep-19oct2023
513 | 2023-10-11 | ISSUE | Listing Page | "No neighbours found" pop up is shown even if that property isn't selected, this happens when already contacted pop up is shown the address was first select and the pop up was shown, if we choose another outcode and then try adding it still shows the pop up for the previous address |  | SANDEEP | COMPLETED | MEDIUM
514 | 2023-10-16 | ISSUE | Campaign History | 2nd instruction - shows a warning pop up when we view bulk mail campaign |  | ANISHA | COMPLETED | URGENT
515 | 2023-10-16 | ISSUE | Letter management | letter management - the file name after uploading letterhead https://tinyurl.com/yorb6des |  | ANISHA | COMPLETED | MEDIUM
516 | 2023-10-16 | ISSUE | Report | reports history section takes some time to load |  | RIJO | COMPLETED | MEDIUM
517 | 2023-10-17 | ISSUE | Summary | shows 1 row selected text when we click on the row |  | SANDEEP | COMPLETED | LOW |  |  | 2024-10-31 | 2024-04-16 |  | updated Nov 29: still shows 1 row selected for 20-20 targeted section, please check Direct Mail Anywhere as well | no517-row-selected-text-summary-page-sandeep-31oct2023
518 | 2023-10-17 | ISSUE |  | email recieved when the dynamic link is opened https://tinyurl.com/yqzaztf7 |  | ANISHA | COMPLETED | LOW | [6 empty] | no-518_mail_received_text_update_anishaoct17
519 | 2023-10-17 | SUGGESTION |  | email recieved when the dynamic link is opened, change Opened Time to Opened On |  | ANISHA | COMPLETED | LOW | [6 empty] | no-519_mail_received_openedtime_update__anishaoct17
520 | 2023-10-17 | ISSUE |  | mail received when agent clicks on the mail icon, there is a section in the mail that is not required https://tinyurl.com/ytqb45c4 |  | ANISHA | COMPLETED | LOW | [6 empty] | no-520_property_report_mail_removesection_anishaoct17
521 | 2023-10-17 | TASK | Anniversary Letter | add anniversary letters for info@burnsandreid.co.uk |  | RISHIKA | COMPLETED | MEDIUM
522 | 2023-10-17 | ISSUE | Live campaign | letters are not reaching stannp, credits are debited |  | RIJO | COMPLETED | URGENT
523 | 2023-10-17 | ISSUE | Live campaign | local print not working |  | RIJO | COMPLETED | URGENT
524 | 2023-10-18 | TASK | Detail Page | add Length of Lease Left in detail page |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-10-23 | 2023-10-26 | 2023-10-31 | updated oct 31: check after next run | no524-length-lease-in-detail-sandeep-24oct2023
525 | 2023-10-18 | TASK | Settings | add a toggle to hide market info in a new tab Side Panel Hide Market Information in side panel - text |  | ANISHA | COMPLETED | HIGH |  |  | 2023-10-20 | 2023-10-20 | 2023-10-27 | updated oct 23: even if the toggle is enabled it still shows side panel data ------------------------- updated oct 24: market info is hidden when the toggle is disabled and displayed when it's enabled, it should be the opposite | no525_addtoggle_hidemarketinfo_sidepanel_anisha20oct
526 | 2023-10-20 | TASK | Report | in the dynamic url pop up add a toggle for email address When the toggle is enabled, the user must input their email to access the report when clicking the link. |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-10-20 | 2023-10-26 | 2023-10-27 | updated oct 26: * if we enable the email for a report and then try to copy the link for another report even though the toggle is enabled, when we open the report we can view the report without entering the email to reproduce the issue: 1. click on the dynamic link button for a report 2. enable email 3. click on the dynamic link button for a different report 4. the email toggle is already enabled for the report * can the email form be centered | no526_dynamic_url_popup_addemailaddress_anisha_20oct
527 | 2023-10-20 | TASK | Summary | in summary page add a column for Email Address, if email is available display it otherwise leave it blank |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-10-20 | 2023-10-26 | 2023-10-27 |  | no527_add_emailcolumn_summarypage_anisha25oct
528 | 2023-10-23 | ISSUE | Quick Send | bulk mail list - company address tag spelling error |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-27 |  | 2023-11-06 |  | no528-company-address-spelling-error-sandeep-27oct2023
529 | 2023-10-25 | ISSUE | Detail Page | while doing quick send the button remains as Added to campaign when we preview the letter and local print or close the pop up after previewing the letter to reproduce the issue: 1. go to the detail page of the property 2. click on quick send 3. click on preview button 4. local print or close the pop up after previewing |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-27 |  | 2023-11-06 |  | no529-quick-send-issue-sandeep-27oct2023
530 | 2023-10-25 | ISSUE | Email | emails received after opening the link and report received is from lino@letsbidproperty.co.uk please replace the from email address to info@letsbidproperty.co.uk |  | ANISHA | COMPLETED | MEDIUM
531 | 2023-10-25 | SUGGESTION | Email | content when report is sent - property report attachment mail Dear *Name*, Please find the attached report with this mail. Thank you. LetsBid Team |  | RIJO | COMPLETED | LOW |  |  | 2024-02-13 | 2024-02-13 | 2024-02-13 |  | no531_report_mail_edits_12Feb24
532 | 2023-10-25 | SUGGESTION | Email | property report attachment mail does the Sub: Property Report Attachment Mail need to be shown in the mail content ? |  | RIJO | COMPLETED | LOW |  |  | 2024-02-13 | 2024-02-13 | 2024-02-13 |  | no531_report_mail_edits_12Feb24
533 | 2023-10-27 | TASK | Report | in the email form 1. Remove the logo 2. Add the text to: Please provide your email address to view the property report. |  | ANISHA | COMPLETED | MEDIUM |  |  | 2023-10-27 | 2023-10-27 |  |  | no533_emailform_changes_anishaoct27
534 | 2023-10-31 | TASK | Probate properties | add Rest Home, Retirement filter when excluding Care Homes |  | SANDEEP | COMPLETED | MEDIUM |  |  |  |  | 2023-11-06 | update 1 Nov: residential home is not getting excluded | no534-probate-rest-home-filter-sandeep-31oct2023
535 | 2023-10-31 | ISSUE | Probate properties | while doing quick send the button remains as Added to campaign when we preview the letter and local print or close the pop up after previewing the letter to reproduce the issue: 1. go to the detail page of the property 2. click on quick send 3. click on preview button 4. local print or close the pop up after previewing |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-01 | 2023-11-01 |  |  | no535-probate-quicksend-local-print-sandeep-01nov2023
536 | 2023-10-31 | ISSUE | Probate properties | campaign history section - 2 campaigns are shown in the campaign history section in the detail page when we do local print/bulk mail for company owned address using quick send https://tinyurl.com/2xb9ced5 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-01 | 2023-11-01 | 2023-11-08 |  | no535-probate-quicksend-local-print-sandeep-01nov2023
537 | 2023-10-31 | ISSUE | Probate properties | campaign history section in detail page - please show the latest campaigns first https://tinyurl.com/ynf39bs8 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-01 | 2023-11-01 | 2024-11-08 |  | no535-probate-quicksend-local-print-sandeep-01nov2023
538 | 2023-10-31 | ISSUE | Probate properties | when we do probate quick send local print the address gets added to the probate campaign after previewing, even after it has been sent it remains in the campaign |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-02 |  | 2024-11-08 |  | no538-quicksend-preview-campaign-sandeep-02nov2023
539 | 2023-11-01 | ISSUE | Summary | if any of the letters fail and the user is refunded the count does not need to increase | Web | RIJO | NOT STARTED | LOW
540 | 2023-11-01 | ISSUE | Detail Page | if the Length Of Lease is Not Available please remove years left https://tinyurl.com/yr8nnuzx Flat 8, Oak House, 101, Ducks Hill Road, Northwood, London, HA6 2WQ Flat 1, Frith Grange, 23, Frithwood Avenue, Northwood, London, HA6 3SF |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-10-24 | 2023-11-10 | 2023-11-17 |  | no524-length-lease-in-detail-sandeep-24oct2023
541 | 2023-11-02 | TASK | Detail Page | in the detail page of company owned property, the title number of property to be separated from company details section |  | SHARAN | COMPLETED | LOW |  |  | 2024-01-26 | 2024-01-26 |  |  | No541_listing_page_detail_page_errors_25_01_2024_Sharan_N_P
542 | 2023-11-03 | ISSUE | Live campaign | probate campaign - when multiple triggers are selected while doing local print, when we preview the second trigger it shows the campaign listing in the pop up https://tinyurl.com/ylzpn8oa to get this issue: 1. go to probate campaign 2. select atleast 2 address 3. choose multiple triggers 4. select local print 5. preview the second trigger |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-06 | 2023-11-16 | 2024-02-12 |  | no542-probate-trigger-preview-issue-sandeep-06nov2023
543 | 2023-11-06 | TASK | Probate properties | export - when agents export data for probate, please add a column for claims date |  | SANDEEP | COMPLETED | HIGH |  |  | 2023-11-16 | 2023-11-22 | 2023-11-27 |  | no543-probate-export-claim-date-sandeep-16nov2023
544 | 2023-10-07 | SUGGESTION | Settings | delete confirmation pop up for Company Icon, Report Logo, Team Image is in the old format |  | SANDEEP | COMPLETED | LOW |  |  | 2023-11-21 | 2024-11-21 | 2024-02-12 |  | no544-delete-confirmation-popup-sandeep-20nov2023
545 | 2023-11-08 | DISCUSS | Detail Page | properties have lease length but it's not shown in the detail page Flat 17, Dagobert House, Smithy Street, London, E1 3HW (withdrawn) Flat 17, Athlone House, Sidney Street, London, E1 3EJ (withdrawn) Flat 10, Galway House, White Horse Lane, London, E1 4LY (withdrawn) |  | RIJO | COMPLETED | MEDIUM | [5 empty] | not getting updates from json file
546 | 2023-11-08 | ISSUE - DEMO | Live campaign | 20-20 targeted - even if no triggers were added for 20-20 targeted it still shows triggers triggers shown are that of Targeted |  | ABHIJITH | COMPLETED | MEDIUM
547 | 2023-11-08 | ISSUE - DEMO | Campaign History | 20-20 - the title is given as 20 20 Targeted Campaign History https://tinyurl.com/ynk6wfdk |  | ABHIJITH | COMPLETED | MEDIUM
548 | 2023-11-08 | ISSUE - DEMO | Campaign History | 20-20 - the campaigns shown are not correct, the campaigns shown are that of 20-20 Targeted https://tinyurl.com/ylhuktft |  | ABHIJITH | COMPLETED | MEDIUM
549 | 2023-11-08 | ISSUE - DEMO | Campaign History | when the user is in the Targeted tab, 20-20 Targeted tab is missing https://tinyurl.com/ykp554zk |  | ABHIJITH | COMPLETED | MEDIUM
550 | 2023-11-08 | ISSUE - DEMO | Campaign History | from the 20-20 tab when we click on 2nd instruction, probate, targeted tabs it shows both the title when the page is loading |  | ABHIJITH | COMPLETED | MEDIUM
551 | 2023-11-08 | ISSUE - DEMO | Live campaign | 20-20 targeted - please change Listed Date to Added On and show the date the address was added to 20-20 Targeted campaign (similar to Targeted) |  | ABHIJITH | COMPLETED | MEDIUM
552 | 2023-11-08 | ISSUE - DEMO | Live campaign | 20-20 targeted - please remove Agency column |  | ABHIJITH | COMPLETED | MEDIUM
553 | 2023-11-08 | ISSUE - DEMO | Live campaign | 20-20 targeted - local print and bulk mail is not working |  | ABHIJITH | COMPLETED | MEDIUM
554 | 2023-11-09 | ISSUE | Probate properties | property has sold history but it's not shown 69 Boleyn Way, Barnet, EN5 5LH 6 Elm Croft, Deeside, CH5 2BZ 11 Rufford Road, Bootle, L20 5EP 47, St Laurence Drive, Broxbourne, Hertfordshire EN10 6LH |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2023-11-13 |  |  | if there are no results in sold history please check with County text in the address (use getaddress)
555 | 2023-11-10 | ISSUE - DEMO | Summary | 20-20 targeted is not added in the summary page |  | ABHIJITH | COMPLETED | MEDIUM |  |  | 2023-11-15 | 2023-11-16
556 | 2023-11-10 | ISSUE - DEMO | Campaign History | 20-20 targeted - please change the title to 20-20 Targeted Campaign History add - in between |  | ABHIJITH | COMPLETED | MEDIUM
557 | 2023-11-10 | ISSUE - DEMO | Wallet/Credit | change the title for 20-20 targeted bulk mail to Twenty Targeted Bulk Mail Payment |  | ABHIJITH | COMPLETED | MEDIUM
558 | 2023-11-10 | ISSUE - DEMO | Dashboard | 20-20 targeted is not added anywhere |  | ABHIJITH | COMPLETED | MEDIUM
559 | 2023-11-11 | SUGGESTION | Listing Page | list of estate agent pop up - make the first letter capital for Platform |  | SHARAN | COMPLETED | LOW |  |  | 2024-01-26 | 2024-01-26 |  |  | No541_listing_page_detail_page_errors_25_01_2024_Sharan_N_P
560 | 2023-11-11 | SUGGESTION | Detail Page | list of estate agent pop up - make the first letter capital for Platform |  | SHARAN | COMPLETED | LOW |  |  | 2024-01-26 | 2024-01-26 |  |  | No541_listing_page_detail_page_errors_25_01_2024_Sharan_N_P
561 | 2023-11-13 | ISSUE | Withdrawn | properties that are still on sale or stc are listed under Withdrawn |  | SANDEEP | COMPLETED | HIGH | [5 empty] | updated mar 12: The Old Orchard, Aston Hill, Ewloe, Deeside, Flintshire, CH5 3AH 64, Towpath Close, Longford, Coventry, Warwickshire CV6 6RG
562 | 2023-11-16 | ISSUE - DEMO | Dashboard | 20-20 targeted bulk mail letter sent count not correct |  | ABHIJITH | COMPLETED | MEDIUM
563 | 2023-11-16 | ISSUE - DEMO | Dashboard | qr code scanned and form submitted count does not increase |  | ABHIJITH | COMPLETED | MEDIUM
564 | 2023-11-16 | ISSUE - DEMO | Dashboard | 20-20 targeted is not shown in the graph shown in Campaigns ¦ Last 30 Days in the dashboard https://tinyurl.com/ytjuo54z |  | ABHIJITH | COMPLETED | MEDIUM
565 | 2023-11-16 | ISSUE - DEMO | Dashboard | 20-20 targeted not shown in Campaign - Activity Summary https://tinyurl.com/yle5oa8f |  | ABHIJITH | COMPLETED | MEDIUM
566 | 2023-11-16 | ISSUE - DEMO | Live campaign | 20-20 campaign - direct mail anywhere title is also shown in the 20-20 tab https://tinyurl.com/ymjt6cqf |  | ANISHA | COMPLETED | MEDIUM
567 | 2023-11-16 | ISSUE - DEMO | Live campaign | direct mail anywhere - shows server error when we click on it |  | ANISHA | COMPLETED | MEDIUM
568 | 2023-11-16 | ISSUE | Live campaign | when the user is in 20-20 targeted campaign tab, Direct mail anywhere is missing https://tinyurl.com/ys7d6dhd |  | RIJO | CLOSED | MEDIUM
569 | 2023-11-16 | ISSUE - DEMO | Campaign History | when the user is in 2nd instruction tab, Direct Mail Anywhere is not shown as a separate tab like the rest it looks as though it has also been selected https://tinyurl.com/ypk96fe8 |  | ANISHA | COMPLETED | MEDIUM
570 | 2023-11-16 | ISSUE | Live campaign | when the user is in 20-20 targeted campaign history tab, Direct mail anywhere is missing https://tinyurl.com/yqad87kd |  | RIJO | COMPLETED | MEDIUM
571 | 2023-11-16 | ISSUE - DEMO | Direct Mail Anywhere | when searching with postcode, in the results shown please make sure the postcode is shown in capital https://tinyurl.com/ykarzdlk |  | ANISHA | COMPLETED | MEDIUM
572 | 2023-11-16 | ISSUE - DEMO | Direct Mail Anywhere | when searching with postcode, in the results shown the last letter of the address before the postcode is missing https://tinyurl.com/ym29nx63 |  | ANISHA | COMPLETED | MEDIUM
573 | 2023-11-16 | ISSUE - DEMO | Direct Mail Anywhere | nothing happens when we select properties and add it to direct mail anywhere campaign |  | ANISHA | COMPLETED | MEDIUM
574 | 2023-11-17 | TASK | Active Buyer | active buyer page |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-11-20 | 2023-11-28 | 2024-01-10 |  | No574_active_user_feature_20_11_2023_Sharan_N_P
575 | 2023-11-27 | ISSUE | Detail Page | withdrawn activity is missing in the listing activity |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-02-13 |  |  | will monitor for few days
576 | 2023-11-27 | ISSUE | Withdrawn | listing activity not correct, the last activity is given as For Sale but the property is withdrawn Ground Floor Flat, 23, Ivy Road, London, NW2 6SY 139a, Deacon Road, London, NW2 5NJ |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | to check after posting is completed
577 | 2023-11-27 | ISSUE | Campaign History | when user is in the Direct Mail Anywhere tab, 20-20 Targeted tab is not shown and vice versa |  | RIJO | COMPLETED | MEDIUM
578 | 2023-11-27 | ISSUE | Direct Mail Anywhere | after adding few properties to campaign the searched postcode gets cleared. |  | SHARAN | COMPLETED | LOW |  |  | 2024-12-13 | 2024-12-13 | 2024-12-17 |  | No578_DMA_postcode_search_Sharan_N_P_13_12_2024
579 | 2023-11-27 | ISSUE - DEMO | Live campaign | direct mail anywhere - the addresses are shown in one line in edit address |  | RIJO | COMPLETED | MEDIUM
580 | 2023-11-27 | ISSUE - DEMO | Direct Mail Anywhere | shows please search with valid postcode message even if the postcodes are correct |  | RIJO | COMPLETED | MEDIUM
581 | 2023-11-27 | ISSUE - DEMO | Live campaign | direct mail anywhere - in bulk mail confirmation pop up - the selected triggers are not shown against the addresses - please change the text to Auto Mail Summary - there is space beside the text please display the text across the entire width of the popup. https://tinyurl.com/ym8qxgj6 |  | RIJO | COMPLETED | MEDIUM
582 | 2023-11-27 | ISSUE - DEMO | Live campaign | print preview not working, it keeps loading when we click on the preview button |  | RIJO | COMPLETED | HIGH
583 | 2023-11-27 | ISSUE - DEMO | Live campaign | shows server error when we do bulk mail for any of the campaigns |  | RIJO | COMPLETED | HIGH
584 | 2023-11-27 | SUGGESTION | Live campaign | direct mail anywhere - remove all property popup - Display the text across the entire width of the popup - please change the text of the pop up to: Are you sure you want to remove all properties? Please confirm on removing all the properties from campaign https://tinyurl.com/yryrgjta |  | SHARAN | COMPLETED | LOW |  |  | 2024-02-23 | 2024-02-23 | 2024-02-29 |  | No584_Delete_popup_added_msg_23_02_2024_Sharan_N_P
585 | 2023-11-27 | ISSUE - DEMO | Live campaign | local print does not work |  | RIJO | COMPLETED | HIGH
586 | 2023-11-27 | ISSUE - DEMO | Live campaign | direct mail anywhere - please change the column name to Added On |  | RIJO | COMPLETED | MEDIUM
587 | 2023-11-27 | ISSUE - DEMO | Wallet/Credit | please change the title for payment deducted for Direct Mail Anywhere |  | RIJO | COMPLETED | MEDIUM
588 | 2023-11-28 | ISSUE - DEMO | Live campaign | direct mail anywhere - local print preview does not work, the page keeps loading |  | RIJO | COMPLETED | MEDIUM
589 | 2023-11-28 | ISSUE | Live campaign | when user is in 20-20 Targeted campaign, Direct mail anywhere tab is not shown |  |  | COMPLETED | MEDIUM
590 | 2023-11-28 | SUGGESTION | Direct Mail Anywhere | When users choose multiple addresses to add into the campaign, they need to scroll to the top of the page to access the button. Unlike other pages where the button remains fixed at the top while scrolling |  | RIJO | COMPLETED | LOW
591 | 2023-11-28 | ISSUE - DEMO | QR Form | direct mail anywhere - when we scan the qr in the letter, difficult to read the texts |  | RIJO | COMPLETED | MEDIUM | [5 empty] | will check when it goes live, seems to be an issue only in demo
592 | 2023-11-28 | ISSUE - DEMO | Summary | direct mail anywhere - qr form scanned and submitted count remains 0 even if the customer has submitted it |  | RIJO | COMPLETED | MEDIUM
593 | 2023-11-28 | ISSUE - DEMO | Dashboard | qr scanned and submitted count is the same for targeted and 20-20 targeted in Campaign Insight ¦ Last 90 Days |  |  | COMPLETED | MEDIUM
594 | 2023-11-28 | ISSUE - DEMO | Dashboard | graph shown in Campaigns ¦ Last 30 Days in the dashboard: - 2nd instruction marketing count is not shown in the graph - in the graph legend blue is given for 2nd instructiion but in the graph the count shown is of 20-20 targeted |  |  | COMPLETED | MEDIUM
595 | 2023-11-28 | ISSUE | Probate properties | manually add probate properties that are not already in our system |  | RIJO | COMPLETED | MEDIUM
596 | 2023-11-29 | ISSUE | Detail Page | property has Length of Lease but it's not shown in the detail page 20, Ormonde Terrace, London, NW8 7LP Apartment 1, 16a, Abbey Road, London, NW8 9GS Penthouse Flat 23, Athena Court, 2, Finchley Road, London, NW8 6DP The Penthouse, 95, Avenue Road, London, NW8 6HY Flat 306, Pavilion Apartments, 34, St Johns Wood Road, London, NW8 7HB Flat 4, Bridge House, 69, Station Road, Cuffley, Potters Bar, Hertfordshire EN6 4HG |  | RAHUL | COMPLETED | HIGH |  |  | 2024-01-22 |  |  | zoopla not showing - 22 jan 2023 updated Feb 1: length of lease given in Zoopla website, please check scrapping data ---------------------- lease length will be available for latest addresses
597 | 2023-11-29 | ISSUE | Live campaign | direct mail anywhere - remove in edit address for local print does not work, even if we remove addresses letters are still printed for these addresses |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-01 | 2024-02-01 |  |  | No597_remove-the-checkboxes_dma_edit_address_01_02_2024_Sharan_N_P
598 | 2023-11-30 | TASK |  | Mongo DB Driver setup |  | SHARAN | COMPLETED | HIGH |  |  | 2023-11-30 |  |  |  | No598_Mongo_DB_driver_setup_30_11_2023_Sharan_N_P
599 | 2023-11-30 | ISSUE | Dashboard | Campaigns ¦ Last 30 Days graph is not correct, data shown is not according to the graph legend given - 2nd instruction marketing count is not shown in the graph - in the graph legend blue is given for 2nd instruction but in the graph the count shown is of 20-20 targeted |  | SHARAN | COMPLETED | MEDIUM
600 | 2023-11-30 | ISSUE | Dashboard | Campaigns ¦ Last 30 Days graph - 20-20 targeted campaign count is not shown in the graph |  | SHARAN | COMPLETED | MEDIUM
601 | 2023-11-30 | ISSUE | 20-20 Targeted Campaign | 20-20 targeted campaign - when letters are being sent to multiple addresses, the addresses are not greyed out like the rest when processing |  | SANDEEP | DUPLICATE TASK | LOW |  |  | 2024-02-01 | 2024-02-02 |  | updated Jun 13: when we send bulk mails the addresses are not greyed out, the page keeps loading ---------------------------- updated Oct 9: when doing local print for multiple addresses, the addresses are not greyed out | no601-t20-targeted-campaign-sandeep-01feb2024
602 | 2023-11-30 | ISSUE | Dashboard | qr scanned and submitted count is the same for targeted and 20-20 targeted in Campaign Insight ¦ Last 90 Days |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-30 | 2024-01-30
603 | 2023-11-30 | ISSUE | Summary | targeted local print letter sent count is not correct when agents remove addresses before printing letters to get this issue: 1. go to Targeted campaign 2. select multiple addresses 3. remove some addresses 4. local print 5. check count |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-31 | 2024-01-31 |  |  | No603_targeted_letter_count_issue_31_01_2024_Sharan_N_P
604 | 2023-11-30 | ISSUE - DEMO | Active Buyer | postcodes dropdown - please show in alphabet order |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-12-07 | 2023-12-07
605 | 2023-11-30 | ISSUE - DEMO | Active Buyer | shows server error when we click on any of the address |  | SHARAN | COMPLETED | MEDIUM
606 | 2023-11-30 | ISSUE - DEMO | Live campaign | when user is in the active buyer tab, the 20-20 targeted and direct mail anywhere tabs are not shown and vice versa |  | SHARAN | CLOSED | MEDIUM | [5 empty] | task 700
607 | 2023-11-30 | ISSUE - DEMO | Campaign History | when the agent is in Active Buyer tab, 20-20 targeted and direct mail anywhere tabs are not shown and vice versa |  | SHARAN | CLOSED | MEDIUM
608 | 2023-11-30 | ISSUE - DEMO | Active Buyer | for some addresses the company address in the listing and detail page are different 57, Sherbrooke Road, Nottingham, City Of Nottingham, NG5 2BE |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 |  | Logic Changed
609 | 2023-11-30 | ISSUE - DEMO | Live campaign | active buyer - local print does not work when side panel is enabled, the status remains pending |  | SHARAN | COMPLETED | MEDIUM
610 | 2023-11-30 | ISSUE - DEMO | Live campaign | active buyer - bulk mail does not work when side panel is enables, shows server error |  | SHARAN | COMPLETED | MEDIUM
611 | 2023-11-30 | ISSUE - DEMO | Active Buyer | shows server error when we click on any address to which letters have been sent |  | SHARAN | COMPLETED | MEDIUM
612 | 2023-11-30 | ISSUE - DEMO | Live campaign | active buyer local print preview - only the preview for property address is shown |  | SHARAN | COMPLETED | MEDIUM
613 | 2023-11-30 | ISSUE - DEMO | Live campaign | active buyer bulk mail preview - ref address is missing in the preview |  | SHARAN | COMPLETED | MEDIUM
614 | 2023-11-30 | ISSUE - DEMO | Live campaign | active buyer - please change the success message shown after removing addresses from campaign list to Success Active Buyer Campaign Removal Successful! https://tinyurl.com/ykgzrkl7 |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-12-07 | 2023-12-07
615 | 2023-11-30 | ISSUE - DEMO | Active Buyer | in campaign tag is shown only when the page is refreshed |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-07 | 2023-07-07
616 | 2023-11-30 | ISSUE - DEMO | Active Buyer | detail page - the button changes to Added to Active Buyer Campaign only when the page is refreshed |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-07 | 2023-07-07
617 | 2023-11-30 | ISSUE - DEMO | Wallet/Credit | when credits are deducted for Active Buyer Bulk Mail please change the title in wallet accordingly |  | SHARAN | COMPLETED | MEDIUM |  |  | 2023-07-07 | 2023-07-07
618 | 2023-11-30 | ISSUE - DEMO | Campaign History | active buyer - status for some letters are failed |  | SHARAN | COMPLETED | MEDIUM
619 | 2023-11-30 | ISSUE - DEMO | Active Buyer | letters should be sent only to company address |  | SHARAN | COMPLETED | MEDIUM
620 | 2023-11-30 | ISSUE - DEMO | QR Form | direct mail anywhere - when we scan the qr, in the form property address is not given |  | RIJO | COMPLETED | MEDIUM |  |  |  | 2023-12-05 | 2023-12-05
621 | 2023-12-01 | ISSUE | Summary | 2nd instruction local print letter sent count not correct when letters are sent from live campaign |  |  | CLOSED | MEDIUM
622 | 2023-12-05 | ISSUE | Listing Page | property type in the listing page has _ in between the texts https://tinyurl.com/ynonq4m7 |  | RIJO | COMPLETED | LOW |  |  | 2024-02-20 | 2024-02-20
623 | 2023-12-05 | ISSUE | Quick Send | preview issue - please show the confirmation message oonly after user has previewed the letter |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-12-06 | 2023-12-06 | 2023-12-06
624 | 2023-12-06 | SUGGESTION | Live campaign | users can just confirm and send letters without previewing |  | RIJO | CLOSED | MEDIUM
625 | 2023-12-06 | ISSUE | Quick Send | quick send preview takes time save and show only the preview of the first address in the quick send mail list as there is a delay in showing the preview |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-12-07 | 2023-12-07 | 2023-12-07
626 | 2023-12-06 | ISSUE - DEMO | Active Buyer | only few properties are listed |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 |  | Logic Changed
627 | 2023-12-06 | ISSUE - DEMO | Active Buyer | company details are shown in the listing page but it shows Company Details not found in the detail page 45, Station Road, Queensferry, Deeside, Flintshire, CH5 1SU |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 |  | Logic Changed
628 | 2023-12-06 | ISSUE - DEMO | QR Form | active buyer - when we sent letters to multiple addresses the property address shown after scanning is not correct, it shows the last address added |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-12 | 2024-01-12
629 | 2023-12-06 | ISSUE - DEMO | Active Buyer | company details are not shown in the listing and detail page 7, Fairfax Gardens, London, Greenwich, SE3 8PY |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 |  | Logic Changed
630 | 2023-12-06 | ISSUE | Probate properties | Vonage clean flag update |  | SHARAN | COMPLETED | HIGH |  |  | 2023-12-06 | 2023-12-06 | 2023-12-06 |  | No630_text_message_clean_flag_update_06_12_2023_Sharan_N_P
631 | 2023-12-08 | TASK | Settings | custom Sidepanel data |  | RIJO | COMPLETED | HIGH |  |  | 2023-12-08 | 2023-12-14 | 2023-12-18
632 | 2023-12-13 | ISSUE | Probate properties | executor address when compared to Gazette is different |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-01-26 | 2024-01-31 |  | will monitor for few days
633 | 2023-12-16 | ISSUE - DEMO | Side Panel | if we give an input and submit even if we havent enabled that data after submitting it automatically is enabled |  | RIJO | COMPLETED | MEDIUM
634 | 2023-12-16 | ISSUE - DEMO | Side Panel | when we submit data the user is directed to Settings > Overview tab same in rest of the tabs, when we make changes and submit user gets redirected to Overview tab |  | RIJO | COMPLETED | MEDIUM
635 | 2023-12-16 | SUGGESTION | Side Panel | if any of the three side panel data options are enabled, user shouldnt be able to disable "Hide market info" toggle. |  | RIJO | CLOSED | MEDIUM
636 | 2023-12-16 | ISSUE - DEMO | Letter | the border between the side panel and content does not look aligned https://tinyurl.com/yw29sb96 |  | RIJO | COMPLETED | MEDIUM
637 | 2023-12-16 | ISSUE - DEMO | Side Panel | getting an error page when we click on settings if we clear the input and then submit https://tinyurl.com/ysx9srar |  | RIJO | COMPLETED | MEDIUM
638 | 2023-12-16 | ISSUE - DEMO | Side Panel | Even when we disable any of the side panel options, it becomes enabled again after submitting |  | RIJO | COMPLETED | MEDIUM
639 | 2023-12-16 | ISSUE | Report | when we generate report by clicking on Generate Report button in the property detail page and then generate another report for a different address in property report page, the property image, floor plan and market price is the same as that of the address which was first generated to get the issue: 1. go to a property detail page 2. click on Generate button 3. Generate report for the address 4. In the Property report page, search for a new address 5. Generate a new report 6. Check property images |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-29 | 2024-01-29 |  |  | No639_report_page_reload_29_01_2024_Sharan_N_P No639_report_page_reload_11_03_2024_Sharan_N_P
640 | 2023-12-19 | TASK | Side Panel | add "% of Asking Price Achieved" in custom side panel in the letter % should automatically be displayed with the value given by the user |  | RIJO | COMPLETED | MEDIUM |  |  | 2023-12-19 | 2023-12-19 | 2023-12-19
641 | 2023-12-19 | TASK | Planning Application | - display data of last 2 years - remove search by postcode and years - letter will be sent to property address and address of agent |  | SANDEEP | COMPLETED | MEDIUM
642 | 2023-12-19 | TASK | Active Buyer | - list the company if there is atleast one property in the any of the subscribed outcodes (all properties owned by company will be listed) - last 12 months - company owned - properties sold in the chosen outcode should be highlighted in the pop up and shown first - letter will be sent only to the company address - no need for property address as reference |  | SHARAN | COMPLETED | MEDIUM |  |  |  | 2024-01-12
643 | 2023-12-20 | ISSUE | Detail Page | property images and floorplan are missing 4, Shaw Close, Ewloe, Deeside, Flintshire CH5 3UH |  | RIJO | COMPLETED | MEDIUM
644 | 2023-12-20 | ISSUE | Report | flood risk data - please check 27, Saffron Lodge, Radwinter Road, Saffron Walden, Essex, CB11 3UZ https://check-long-term-flood-risk.service.gov.uk/risk# |  | RIJO | CLOSED | MEDIUM
645 | 2023-12-27 | ISSUE | Detail Page | after adding properties to 20-20 and 2nd instruction campaign, the buttons do not change to Added to 20-20 campaign and Added to campaign |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-29 | 2024-01-30 |  |  | No645_button_text_change_to_added_to_campaign_29_01_2024_Sharan_N_P
646 | 2023-12-29 | ISSUE | Report | not able to generate report 47 St. Laurence Drive, Broxbourne, EN10 6LH |  | SHARAN | COMPLETED | HIGH |  |  | 2023-12-29 | 2023-12-29 |  |  | No646_Report_error_Sharan_29_12_2023
647 | 2023-12-30 | ISSUE - DEMO | Planning Application | keywords - please change to House In Multiple Occupation Development Loft Conversion http://tinyurl.com/yo4nnynf |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
648 | 2023-12-30 | ISSUE - DEMO | Planning Application | when multiple planning keywords are selected, the tags shown are not aligned properly and the tags overlap http://tinyurl.com/ywxvnewd |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
649 | 2023-12-30 | ISSUE - DEMO | Planning Application | description looks cropped http://tinyurl.com/yl9jm7nc |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
650 | 2024-01-05 | ISSUE | Quick Send | when sending bulk mail only 1 letter is being sent even if we select multiple addresses |  | SHARAN | COMPLETED | HIGH |  |  |  |  | 2024-01-16
651 | 2024-01-05 | ISSUE | Probate properties | both addresses are shown Atholl House Nursing Home, 98-100 Richmond Road, Compton, Wolverhampton Wv3 9jj And 55 Brookhouse Lane, Featherstone, Wolverhampton, WV10 7AW |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-01-30 | 2024-01-30
652 | 2024-01-05 | ISSUE - DEMO | Planning Application | change Planning to New Homes in the menu |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
653 | 2024-01-05 | ISSUE - DEMO |  | Direct mail anywhere is missing in the menu and all the other pages - dashboard: Campaigns ¦ Last 30 Days, Campaign Insight ¦ Last 90 Days, Campaign - Activity Summary - summary - live campaign - campaign history - letter management |  | RIJO | COMPLETED | MEDIUM
654 | 2024-01-05 | ISSUE - DEMO | Planning Application | sort by date - show the latest applications first |  | SANDEEP | COMPLETED | MEDIUM
655 | 2024-01-05 | ISSUE - DEMO | Planning Application | show more button is displayed only for some description, the rest remain cropped http://tinyurl.com/yr3q4axb |  | SANDEEP | COMPLETED | MEDIUM
656 | 2024-01-05 | ISSUE - DEMO | Planning Application | when we click on Show More for one description, all the descriptions are expanded |  | SANDEEP | COMPLETED | MEDIUM
657 | 2024-01-05 | SUGGESTION | Planning Application | if no data is available for some councils, can we not show the message shown in Propmarker http://tinyurl.com/yvvf5lvb |  | SANDEEP | COMPLETED | MEDIUM
658 | 2024-01-05 | ISSUE - DEMO | Planning Application | when we click on show More once, it remains as Show Less even when the description is collapsed |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
659 | 2024-01-05 | SUGGESTION | Planning Application | When users choose multiple addresses to add into the campaign, they need to scroll to the top of the page to access the button. Unlike other pages where the button remains fixed at the top while scrolling |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-02-01 | 2024-02-01
660 | 2024-01-05 | ISSUE - DEMO | Campaign History | planning - when bulk mail is sent only to property address, the campaign history is blank |  | SANDEEP | COMPLETED | MEDIUM
661 | 2024-01-05 | ISSUE - DEMO | Campaign History | planning campaign history - when we click on the back button it redirects to the second instruction campaign history listing |  | SANDEEP | COMPLETED | MEDIUM | [6 empty] | planning-application-data-from-propmarker-sandeep-30nov2023
662 | 2024-01-05 | ISSUE - DEMO | Campaign History | planning - when we local print letter or send bulk mail to both addresses in the campaign history it is not shown separately like when we send letters to company owned or probate addresses |  | SANDEEP | COMPLETED | MEDIUM
663 | 2024-01-05 | SUGGESTION | Campaign History | planning - please show a tag for the Agent address |  | SANDEEP | COMPLETED | MEDIUM
664 | 2024-01-05 | ISSUE - DEMO | Campaign History | planning - when bulk mail is sent only to the property address, the status is failed |  | SANDEEP | COMPLETED | MEDIUM
665 | 2024-01-05 | ISSUE - DEMO | Live campaign | planning - if agent address is not available and we try to send letters to only the property address, the local print and bulk mail does not work |  | SANDEEP | COMPLETED | MEDIUM
666 | 2024-01-05 | ISSUE - DEMO | Planning Application | if multiple keywords are selected, in the tag shown below the description please make sure that the keyword with multiple words are shown as a single tag and not in multiple lines http://tinyurl.com/yvmklspu |  | SANDEEP | COMPLETED | MEDIUM
667 | 2024-01-05 | ISSUE - DEMO | Active Buyer | the listing page does not look aligned http://tinyurl.com/yv9nj62n |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-09 | 2024-01-09
668 | 2024-01-05 | ISSUE - DEMO | Wallet/Credit | when credits are deducted for Planning Bulk Mail please change the title in the wallet accordingly |  | SANDEEP | COMPLETED | MEDIUM
669 | 2024-01-05 | SUGGESTION | Active Buyer | when we add the company address to campaign from property list pop up, the pop up closes and user will have to again open it |  | SHARAN | CLOSED | MEDIUM
670 | 2024-01-05 | ISSUE - DEMO | Active Buyer | the button in the property list pop up does not change to Added to Active Buyer Campaign after adding the address to campaign |  | SHARAN | CLOSED | MEDIUM
671 | 2024-01-05 | ISSUE - DEMO | Active Buyer | the same company address gets added to campaign multiple times when we add to campaign from the property detail page of properties listed under the same company - click on view property list - click on view details for few properties - click add to campaign in the detail page - check live campaign |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-08 | 2024-01-08
672 | 2024-01-05 | ISSUE - DEMO | Active Buyer | when we add properties to campaign from any page other than the first page, after adding the property to campaign the user gets redirected to the first page |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-08 | 2024-01-08
673 | 2024-01-05 | ISSUE - DEMO | Active Buyer | when we click on any box, at the bottom it shows 1 row selected http://tinyurl.com/yoctgdvk |  | SHARAN | COMPLETED | LOW |  |  | 2024-01-08 | 2024-01-08
674 | 2024-01-08 | ISSUE | Detail Page | check if lease left is shown in detail page for all proeperties |  |  | CLOSED | MEDIUM | [5 empty] | task 596
675 | 2024-01-08 | UK TEAM |  | multiple users login for a single estate agent company | Web | RIJO | DISCUSS | MEDIUM |  | 2 weeks |  |  |  | Need to integrate the module to website cms, wil take atleast 1-2 week work
676 | 2024-01-08 | TASK |  | LH for Paul IAD |  | RIJO | COMPLETED
677 | 2024-01-08 | TASK |  | Can you please change the following email inglebybarwick@robinsonsteesvalley.co.uk to markhodgson@smith-and-friends.co.uk they have had a brand change and mark will be using this himself so wants it to his email |  | RIJO | COMPLETED | MEDIUM
678 | 2024-01-08 | TASK |  | add the RM/Z IDs for Smith&Friends they have zoopla too https://www.rightmove.co.uk/properties/142603718#/?channel=RES_BUY |  | RIJO | COMPLETED | MEDIUM
679 | 2024-01-08 | UK TEAM |  | Change the letter editor The picture showing you the text of a letter is regarding the font sizes. I have asked if we can change this and allow agents to have more font sizes available. As you can see this is selected with the smallest font. | Web | RIJO | DISCUSS | MEDIUM |  | 2 weeks |  |  |  | editor needs to be revamped so that we can include images, will require 2 weeks
680 | 2024-01-08 | TASK |  | Can you please change the sidepanel data third one along for sales to Total Sales Value in last 6 months |  | RIJO | COMPLETED | MEDIUM
681 | 2024-01-08 | UK TEAM |  | Recent Valuations Tab | Web | RIJO | DISCUSS | MEDIUM
682 | 2024-01-09 | ISSUE - DEMO | Live campaign | active buyer - when addresses are added to campaign it is greyed out, not able to select addresses http://tinyurl.com/yw7umuox |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-08 | 2024-01-08
683 | 2024-01-09 | ISSUE - DEMO | Active Buyer | in campaign tag overlaps the Company name sometimes http://tinyurl.com/ynaldxrj |  | SHARAN | CLOSED | MEDIUM
684 | 2024-01-09 | ISSUE | Live campaign | active buyer - the address after adding to campaign is different than the one in the listing the address after adding to the campaign is the one in Find Company page HP12 GIRIK PROPERTY LTD SACHAN GB LTD |  | DATA TEAM | CLOSED | MEDIUM | [5 empty] | data issue the address shown in campaign is correct, we are showing the correct address from getaddress
685 | 2024-01-09 | ISSUE - DEMO | Side Panel | side panel custom data textboxes are missing http://tinyurl.com/yojdjjg3 |  |  | COMPLETED | MEDIUM
686 | 2024-01-09 | ISSUE | Active Buyer | the company address in the active buyer listing and property detail page is different HP12 GIRIK PROPERTY LTD SACHAN GB LTD |  | DATA TEAM | CLOSED | MEDIUM | [5 empty] | data issue the address shown in the detail page is correct, we are showing the correct address from getaddress
687 | 2024-01-09 | TASK | Targeted Properties | shorten url |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 | 2024-01-17 |  | No574_active_user_feature_20_11_2023_Sharan_N_P
688 | 2024-01-10 | ISSUE - DEMO | Planning Application | full description is not shown for some addresses, also See More button is not shown http://tinyurl.com/yndhjlxk |  | SANDEEP | COMPLETED | MEDIUM
689 | 2024-01-10 | SUGGESTION | Active Buyer | if there is no data for the selected outcode, please show the message Unfortunately, there is currently no active buyers for the chosen outcode. Please consider choosing a different outcode to view active buyers. |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-10 | 2024-01-10
690 | 2024-01-10 | ISSUE - DEMO | Planning Application | when we move to the next page or the previous page, the user remains at the bottom of the page and they will have to scroll to the top |  | SANDEEP | COMPLETED | MEDIUM
691 | 2024-01-10 | TASK | Report | NHS response time issue |  | RIJO | COMPLETED | MEDIUM
692 | 2024-01-10 | ISSUE | Active Buyer | when we move to the next page or the previous page, the user remains at the bottom of the page and they will have to scroll to the top |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-10 | 2024-01-10
693 | 2024-01-10 | SUGGESTION | Active Buyer | when no outcodes are selected, center the text and please change the message to: To view active buyers, please select an outcode. http://tinyurl.com/yu4zxqel |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-10 | 2024-01-10
694 | 2024-01-10 | DISCUSS | Active Buyer | property detail page - in Other properties owned by the company section, the sold data is shown as not available is it because we are not getting the data NW6 - BENTRY CAPITAL LIMITED (102 Priory Road, London, NW6 3NS) |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-12 | 2024-01-12 |  |  | No574_active_user_feature_20_11_2023_Sharan_N_P
695 | 2024-01-10 | ISSUE | Live campaign | active buyer - not able to local print or send bulk mail to some addresses, after trying to send letters to this address a blank listing is shown in the campaign http://tinyurl.com/ymtxhyeu NW6 - YUSUF ISLAM FOUNDATION |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-10 | 2024-01-10
696 | 2024-01-10 | ISSUE | Active Buyer | in campaign tag overlaps the company name sometimes http://tinyurl.com/ynaldxrj |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-10 | 2024-01-10
697 | 2024-01-10 | ISSUE | Active Buyer | property list - same property is listed in the active buyer property list N17 - OLDHILL ESTATES LIMITED http://tinyurl.com/yma3u7er |  | DATA TEAM | COMPLETED | MEDIUM | [5 empty] | Need to discuss with Rahul and team
698 | 2024-01-10 | DISCUSS | Active Buyer | property detail page - in Other properties owned by the company section, there are other properties but it shows no other properties NW6 - BENTRY CAPITAL LIMITED (102 Priory Road, London, NW6 3NS) 102, Priory Road, London, NW6 3NS NW6 - CLARKE AND COMPANY 3 LIMITED 37 Creighton Road, London, NW6 6EE |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-16 | 2024-01-16 |  | With in Subscribed outcodes only | No574_active_user_feature_20_11_2023_Sharan_N_P
699 | 2024-01-10 | ISSUE | Live campaign | tabs missing - when in DMA tab: the active buyer and planning tabs are missing - when we are in 20-20 targeted tab: the DMA and Active Buyer tabs are missing - when in Active Buyer tab: DMA, the 20-20 targeted and planning tabs are missing - when in Planning tab: the DMA and active buyer tabs are missing |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-01-29 | 2024-01-31
700 | 2024-01-10 | ISSUE | Campaign History | tabs missing - when in DMA tab: 20-20 Targeted, Active Buyer and Planning tabs are missing - when we are in 20-20 targeted tab: DMA, Active Buyer and Planning tabs are missing - when in Active Buyer tab: DMA, 20-20 targeted and Planning tabs are missing - when in Planning tab: DMA and Active Buyer tabs are missing |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-01-29 | 2024-01-31
701 | 2024-01-10 | ISSUE |  | print letter pop up - even if we have opened it once is still shown in the other tabs open and it shows a blank page on clicking |  | RIJO | CLOSED | MEDIUM
702 | 2024-01-10 | ISSUE - DEMO | Planning Application | shows a warning pop up when we select some council Erewash West Devon Slough Bournemouth Christchurch And Poole Cannock Chase there are a few others |  | SANDEEP | COMPLETED | MEDIUM
703 | 2024-01-10 | ISSUE - DEMO | Planning Application | can we show a loader when we select a council from the dropdown |  | SANDEEP | COMPLETED | MEDIUM
704 | 2024-01-11 | ISSUE - DEMO | Live campaign | planning application - in edit address, some address are shown in one line and it shows "Address not valid" http://tinyurl.com/ymdzod9e |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | addresses which we do not get from getaddress is shown in single line corrected the text as "Address cannot be single line".
705 | 2024-01-11 | ISSUE - DEMO | Planning Application | shows the text " row selected" at the bottom when we select addresses |  | SANDEEP | COMPLETED | MEDIUM
706 | 2024-01-11 | ISSUE | Active Buyer | active buyer detail page - only the first letter of the property type shown in the detail page of properties listed under Other properties owned by the company https://www.prospectingtool.letsbidproperty.co.uk/active-buyers/eyJpdiI6IlNWWWRSTTVCV3IxZkd6S1NnR3QvVFE9PSIsInZhbHVlIjoiK202YTBPVy9RUkcrT0VzK2NBZTBUYnhXZXRRdHd6SFZyc2lCaEwwQndjY2t3bGJZc2F0aDI2MDdDbWt2azhDUDhXcmtGZ2p1aE9MQkpyeTRkVi9lT0xFUEo1YVZsdk5vSFZZdFpPTHVHRThjVmlnNFZsOWswMWNLRXM5N1ZIWW1tYkxJQjZHbGtITWhiSFA4cDVaWmlRVHg2RDVYU1dpaEpBblZ2aDliRDMyZ3BJMTdEa1MxNHV4Smx0dTd5NmFRMGdnVVBOcXQ2a2lHRngxUXYwbytFUFBSWXRkc01GL0dKK0NVZitNQW14UHQ0RjF3N1Z4aVp2dFFEV3NZNVJielZJb205dFFTdURud2hDZkdiR2tuSmxKdjlnWm5oWlQ0SGYvKyt2bHVvcXovY3VsV1NFM1lDdTQxdUJKOXFWZU1mWlhOUkRKeEtQOStEN0RCYVF1U2FFTDRta2lyeHVnUFJnUWc1SU4yVHo5V2FyWFRnaWc4OTRSVUVaM1ltcmxFbjVIRDFUNW5ydjRnemk0MFFwUkxTZVg4c2JIYWJKd3YvS0N1b0gvdWZCTGQzUER4cDhwVjczMHJ2ejJNK2JqbGQ3amJMSC9EWW82anRscWFsbE5ncXE4UUhEdnVoYTBJRHVOMU9WQW81MHIzOUNPRThTWFc2UDBOWVVSV3BnQURJVC9qMkR1K3BjdzNqdng3QUEveXM2T0h4U2x6RXlUTVpCYVROTmw2cFc3ckNUcmhvNWd4N0Q5Q3pLOGdRRkZLVmplOTFYTmZMU1c1blozaUxRMUZET0ZUSk9VNU5NMS9tMllkeFBDZUNrSnN5TWtEeEZWcytaN1pEanJiSHB0WC9YenlPSjUwS2JqYkdOK3JYSDN4bWJLUExCUyt0YXJnZncyR292a0Jmek15TmFyVGJUMERzWXZhQ3hwaGxNa0FOeDhFdmRzSDNMaUkxdzVsaFZ0TXBGTmJsVnZXbEZPZ01lOXY1L0hTUnE0QjcvVzZLeE1JeElwQjNnTUVnTzY4dEdJUHhlaU96T3ZIUTdsOVRFc1diL0pKQmc2UENBYkkrY0ZvZVhzZExQWDFXVFlMc2hLbitNUjNlcEo5cEZsUUFZTXlrOE9ZODd1NzJqVU0yaU1XN3BHSTNjamlpRnBtbkhIUmZZWGhBRXc9IiwibWFjIjoiOTU0ZmUwOWNiNzM3ZTI0YzMzMWIxNjc4OTQ0YWZlNzg0NjAwMTI5MjZlNTZhYTNiYjA5YzMyZDM3ODIwMzZhZiIsInRhZyI6IiJ9 http://tinyurl.com/ysewsod6 |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-16 | 2024-01-16 |  |  | No574_active_user_feature_20_11_2023_Sharan_N_P
707 | 2024-01-11 | TASK | Report | custom value - add Miles |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-06 |  |  |  | No707_custom_miles_on_report_06_02_2024_Sharan_N_P
708 | 2024-01-11 | ISSUE - DEMO | Campaign History | planning application - not able to edit campaign name, nothing happens on submitting |  | SANDEEP | COMPLETED | MEDIUM
709 | 2024-01-11 | ISSUE - DEMO | Campaign History | planning application - delete campaign does not work |  | SANDEEP | COMPLETED | MEDIUM
710 | 2024-01-15 | ISSUE | Report | flood risk data please check when checked with Nimbus it is given as Not in a flooding zone but in our report it shows Flood Risk Area 21, Orchard Square, Broxbourne, Hertfordshire, EN10 6JA 8, Fairfield Drive, Broxbourne, Hertfordshire, EN10 6DX |  | VIPIN | CLOSED | MEDIUM
711 | 2024-01-15 | ISSUE | Probate properties | quick send - shows server error when doing bulk mail |  | SHARAN | COMPLETED | HIGH |  |  | 2024-01-15 | 2024-01-16 |  |  | quick_send_fixes_Rijo_12Jan24
712 | 2024-01-15 | DISCUSS | Active Buyer | url is lengthy |  | SHARAN | COMPLETED | MEDIUM
713 | 2024-01-15 | ISSUE | Detail Page | quick send pop up - the column names are not shown above the correct data http://tinyurl.com/yneuf27m |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-16 | 2024-01-16 | 2024-01-16 |  | quick_send_fixes_Rijo_12Jan24
714 | 2024-01-15 | ISSUE | Probate properties | detail page - in the quick send pop up the column names are not shown above the correct data http://tinyurl.com/yk8jnm3z |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-16 | 2024-01-16 | 2024-01-16 |  | quick_send_fixes_Rijo_12Jan24
715 | 2024-01-15 | ISSUE | Campaign History | 2nd instruction campaign history - when we click on the property address, in the property url the campaign id is also shown |  | RIJO | COMPLETED | MEDIUM | [5 empty] | that is to ensure we go back to campaign history detail page when we click back there is no error here
716 | 2024-01-16 | ISSUE | Detail Page | quick send - for company owned properties when we do quick send bulk mail from detail page, the letters are sent only to the property address |  | SHARAN | COMPLETED | HIGH |  |  | 2024-01-16 | 2024-01-16 | 2024-01-16 |  | quick_send_fixes_Rijo_12Jan24
717 | 2024-01-16 | ISSUE - DEMO | Planning Application | when we click on clear filter the keywords selected are still shown with each planning description but the keywords are not highlighted 1. select few keywords or enable Select all 2. click on clear filter 3. check the listing |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-01-23 | 2024-01-24
718 | 2024-01-16 | ISSUE - DEMO | Summary | planning application - when we scan and submit the qr form, the count does not increase |  | SANDEEP | COMPLETED | MEDIUM
719 | 2024-01-16 | ISSUE - DEMO | Dashboard | Campaigns ¦ Last 30 Days - planning is not added |  | SANDEEP | COMPLETED | MEDIUM
720 | 2024-01-16 | ISSUE - DEMO | Summary | Campaign Insight ¦ Last 90 Days - the QR Codes scanned and QRs Forms Completed count is the same as 20-20 targeted |  | SANDEEP | COMPLETED | MEDIUM
721 | 2024-01-16 | ISSUE - DEMO | QR Form | planning application - when we scan the qr code, the address is not mentioned in the qr form |  | SANDEEP | COMPLETED | MEDIUM
722 | 2024-01-16 | ISSUE - DEMO | Dashboard | Campaign - Activity Summary - planning is not added |  | SANDEEP | COMPLETED | MEDIUM
723 | 2024-01-17 | ISSUE | Planning Application | show the latest planning data first |  | SANDEEP | COMPLETED | LOW |  |  | 2024-02-09 | 2024-02-22 | 2024-02-23 | Jinto is checking the same issue in Propmarker | no723-planning-sort-issue-sandeep-09feb2024
724 | 2024-01-17 | ISSUE | Report | not able to generate report |  | RIJO | COMPLETED | HIGH
725 | 2024-01-18 | ISSUE | Dashboard | Targeted QR Codes scanned and QRs Forms Completed count does not increase when scanned |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-30 | 2024-01-30 |  |  | No725_qr_code_error_targeted_30_01_2024_Sharan_N_P
726 | 2024-01-18 | ISSUE | Sold- Under offer | the listing activity is given as Withdrawn and STC multiple times 59, Altenburg Gardens, London, SW11 1JH 11, Wolftencroft Close, London, SW11 2LB |  | SANDEEP | CLOSED | HIGH |  |  | 2024-04-02 |  |  | Need example | no726-
727 | 2024-01-19 | ISSUE | Report | download report button does not work in Report History section |  | RIJO | COMPLETED | MEDIUM
728 | 2024-01-22 | ISSUE | Live campaign | active buyer - company address is not shown in edit address CH5 - FIRST CHOICE HOUSING ASSOCIATION LTD |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-25 | 2024-01-25 |  |  | No728_edit_company_address_error_25_01_2024_Sharan_N_P
729 | 2024-01-23 | ISSUE | Report | property is company owned but it is not tagged in the report 51, Market Place, Hornsea, East Riding Of Yorkshire HU18 1AP 5, Shuttleworth Court, Hornsea, Yorkshire, HU18 1PP |  | SHARAN | COMPLETED | LOW |  |  | 2024-01-25 | 2024-02-04 | 2024-02-15 |  | No729_report_company_owned_issue_25_01_2024_Sharan_N_P
730 | 2024-01-23 | ISSUE | Report | On Market Comparable Properties list keeps loading 5, Shuttleworth Court, Hornsea, Yorkshire, HU18 1PP |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-25 | 2024-01-25 |  |  | No730_on_market_comparable_loading_25_01_2024_Sharan_N_P
731 | 2024-01-24 | TASK |  | Letsbid redesign |  | SATHEESH | COMPLETED | MEDIUM |  |  | 2024-01-24
732 | 2024-01-26 | TASK | Report | if habitable room is 0 don't display it in the report 7, Gloucester Drive, Southampton, Hampshire, SO31 7PE |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-30 | 2024-01-30 |  |  | No732_report_habitable_rooms_30_01_2024_Sharan_N_P
733 | 2024-01-26 | TASK |  | display floorplan only if the floorplan url is 'media.rightmove.co.uk' detail page and report |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-30 | 2024-01-30 | 2024-02-12 | 30, Ashwood Road, Potters Bar, Hertfordshire EN6 2PH Gable End, 40, Manor Road, Potters Bar, Hertfordshire EN6 1DQ | No733_floorplan_checks_30_01_2024_Sharan_N_P
734 | 2024-01-26 | TASK | Active Buyer | company address and display address same (transaction table update/handle) | Data | DATA TEAM | PENDING UPDATE | MEDIUM
735 | 2024-01-26 | TASK | Targeted Properties | remove all properties from targeted that do not have company data |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-01-31 | 2024-02-01
736 |  | ISSUE | Dashboard | Dasboard charts |  | SHARAN | COMPLETED | HIGH |  |  | 2024-01-28 | 2024-01-28 |  |  | No736_dasboard_charts_28_01_2024_Sharan_N_P
737 | 2024-01-31 | ISSUE - DEMO | Dashboard | Campaigns ¦ Last 30 Days graph - active buyer is shown in the graph instead of Direct Mail Anywhere - for Targeted in the graph DMA is shown - instead of Active Buyer campaign, in the graph Planning is shown - for planning campaign, the same color as 2nd instruction is shown in the graph |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-01-31 | 2024-02-01 |  |  | No736_dasboard_charts_28_01_2024_Sharan_N_P
738 | 2024-01-31 | ISSUE |  | CompanyOwnedService company_registration_no_1 undefined error in log |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-01 | 2024-02-01 |  |  | No738_company_registration_no_1_error_01_02_2024_Sharan_N_P
739 | 2024-02-01 | ISSUE | Dashboard | planning - local print Letter Sent count is not correct |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-02 | 2024-02-02 |  |  | No739_dashboard_planning_count_02_02_2024_Sharan_N_P
740 | 2024-02-01 | SUGGESTION | Detail Page | property detail page - please shown Company details section and Title number only if the property is company owned http://tinyurl.com/ytwoacqc |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-01 | 2024-02-01 |  |  | No740_company_detail_section_01_02_2024_Sharan_N_P
741 | 2024-02-01 | TASK | Company Owned | create a manual function to update if the property is Company Owned or not |  | SHARAN | DUPLICATE TASK | MEDIUM |  | 6 days
742 | 2024-02-01 | TASK |  | Log Error - Property detail page undefined variable companyownd company_registration_no_1 |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-01 | 2024-02-01 |  |  | No742_property_detail_company_reg_no_1_undefined_01_02_2024_Sharan_N_P
743 | 2024-02-02 | TASK | Report | EPC page - if habitable room is 0 in the EPC page please shown Not Available 7, Gloucester Drive, Southampton, Hampshire, SO31 7PE |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-05 | 2024-02-05 |  |  | No743_epc_habitable-_rooms_count_05_02_2024_Sharan_N_P
744 | 2024-02-02 | ISSUE | Report | title numbers are not shown in the report for some addresses getting title number for all the addresses in Lettings please check this task: https://docs.google.com/spreadsheets/d/1WjnUjBmxpyUdjSZ_jo_ebfFABn2g78Pkl4hRvaLRBlg/edit#gid=51567162&range=501:501 23, Tennyson Road, London, NW6 7RT 38, Ordish Street, Burton-on-Trent, Staffordshire, DE14 3SA 3, Garth Close, Morden, Surrey, SM4 4NN 14, Hillcrest View, Carlton, Nottingham, Nottinghamshire NG4 1LQ 16, Judge Street, Watford, Hertfordshire, WD24 5AW 39, Stanley Road, Bootle, Merseyside L20 7BY |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-06 | 2024-02-06 |  |  | No744_Title_number_missing_on_report_06_02_2024_Sharan_N_P
745 | 2024-02-05 | TASK |  | postcard design |  | SATHEESH | COMPLETED | HIGH |  |  |  | 2024-02-08
746 | 2024-02-05 | ISSUE | Price Drop | 63, Plymouth Drive, Fareham, Hampshire PO14 3SS - https://www.prospectingtool.letsbidproperty.co.uk/properties/d-2060486 checked in zoopla and rm but price has not been reduced, but we are showing as price reduced |  | RISHIKA | COMPLETED | MEDIUM
747 | 2024-02-05 | TASK |  | Add small information buttons next to the title, so if a user hovers over the button it shows the content New Homes - Find and target all new developments and planning applications in your local area Targeted - Target specific properties off the market in your area by house type, price and sold dates. Direct mail anywhere - Canvas any street in your local area by postcode Active Buyers - Find and target all of the active buyers in your area that are purchasing multiple properties under company names. Sold/under offer - Use this tool to find your sold stock and target neighbouring properties in the form of a 20-20 letter Anniversary letters - Add all of your completions into this feature and our system will send them a letter of your choice on their 1 year anniversary. |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-02-08 | 2024-02-08 | 2024-02-08 |  | No747_info_text_for_letters_Rijo8Feb24
748 | 2024-02-05 | ISSUE | Report | when we search for "Summerhill House, Fingest Lane, Bolter End, High Wycombe, Buckinghamshire HP14 3LS" in generate report page, it is shown as Off Market |  | SHARAN | COMPLETED | LOW |  |  | 2024-02-06 | 2024-02-06
749 | 2024-02-05 | ISSUE | Probate properties | when previewing letters while doing quick send shows "In Campaign" tag in the probate listing |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-02-08 | 2024-02-08 | 2024-02-23 | @Rishika : Pls check this issue in normal properties also. | no749-quicksend-incampign-issue-08feb2024
750 | 2024-02-06 | SUGGESTION | Direct Mail Anywhere | same addresses are repeating in the listing SW16 2NY |  | RIJO | CLOSED | MEDIUM
751 | 2024-02-06 | ISSUE | DMA Campaign | remove the comma after the building number when pushing to Stannp |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-06 | 2024-02-06 | 2024-02-12 |  | No751_dma_remove_coma_in_address_06_02_2024_Sharan_N_P
752 | 2024-02-06 | ISSUE | Report | comparables property list is blank Flat 7, 16, The Avenue, Taunton, Somerset, TA1 1EA |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-06 | 2024-02-06 | 2024-02-07 |  | No752_no_comparable_page_06_02_2024_Sharan_N_P
753 | 2024-02-06 | ISSUE |  | log error - Undefined array key "custom_agent" pdf.blade.php |  | SHARAN | COMPLETED | HIGH |  |  |  |  | 2024-02-29 |  | No753_log_undefined_error_06_02_2024_Sharan_N_P
754 | 2024-02-07 | ISSUE | Detail Page | property is tagged as Company Owned but the company details are not shown in the detail page 63, Chartley Avenue, London, NW2 7QY |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-14 | 2024-02-14 | 2024-02-29 |  | No754_company_owned_company_details_missing_14_02_2024_Sharan_N_P
755 | 2024-02-07 | ISSUE | Properties | if unconfirmed in portal properties hide them (unconfirmed=1) |  | RIJO | COMPLETED | HIGH |  |  | 2024-02-07 | 2024-02-07 | 2024-02-09 | 7feb2024 ========== unconfirmed condition != 1 9feb2024 ========== unconfirmed condition checking removed | no755_unconfirmed_properties_removed_Rijo1Feb24
756 | 2024-02-07 | ISSUE | Properties | Flat B, 98, Fordwych Road, London, NW2 3TJ - when checked in RM there is a difference in the building number https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2353747 https://www.rightmove.co.uk/house-prices/nw2-3tj.html?country=england&searchLocation=NW2+3TJ |  | RIJO | COMPLETED | HIGH
757 | 2024-02-07 | ISSUE | Report | when we give custom value for bedroom as 5+ beds, in the comparables list it includes 4 bedroom properties the nursery house, tylers road, harlow, essex, CM19 5LG |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-15 | 2024-02-15 |  | Custom Bed : This value will only affect rental comparable.
758 | 2024-02-07 | TASK | Report | in comparable pop-up show miles instead of price/sqft |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-15 | 2024-03-07 | 2024-03-12 | updated feb 27 please hide price/sqft and show miles updated Mar 1: price/sqft is shown in the generated report | No758_report_comparables_popup_miles_15_02_2024_Sharan_N_P
759 | 2024-02-07 | DISCUSS | Report | increase top limit of comparable data to 5 miles in comparable table |  | RAHUL | COMPLETED
760 | 2024-02-08 | ISSUE | Report | in Rental Comparables, the selected property address is shown in the comparables list 23, Tennyson Road, London, NW6 7RT |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-27 | 2024-02-27 | 2024-02-29 | nothing happens when we click on Confirm Address No786_Report_epc_property_type_21_02_2024_Sharan_N_P | No760_report_address_in_rental_comparables_list_15_02_2024_Sharan_N_P
761 | 2024-02-08 | DISCUSS | Active Buyer | same property is listed under 2 companies BN44 STEYNDENT LIMITED ADI HOLDINGS LIMITED 4 High Street, Steyning BN44 3GG is listed under both companies (when checked in Find Company page the company address is same for both) |  | DATA TEAM | CLOSED | MEDIUM | [5 empty] | Rahul & Vishnu [COP Transaction table mistakes]
762 | 2024-02-08 | ISSUE | Planning Campaign | agent address is not shown in the campaign when we add addresses in Havering council |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-02-19 |  | 2024-03-25
763 | 2024-02-08 | ISSUE | Planning Application | Hartlepool - the addresses are not spaced out properly http://tinyurl.com/2yyj8yku | Data | DATA TEAM | PENDING UPDATE | MEDIUM | [5 empty] | spoke to vishnu regarding this
764 | 2024-02-08 | SUGGESTION | Planning Application | do we need to show the keyword filter section at the top when we scroll? just the Add to campaign button needs too be shown at the top |  | SATHEESH | CLOSED | LOW
765 | 2024-02-12 | ISSUE | Listing Page | Agent name not correct for Zoopla listing, it's given as $agent_name http://tinyurl.com/28os9udx |  | RAHUL | COMPLETED | HIGH
766 | 2024-02-12 | ISSUE | Detail Page | Agent name not correct for Zoopla listing, it's given as $agent_name http://tinyurl.com/2c8nvumz |  | RAHUL | COMPLETED | HIGH
767 | 2024-02-12 | ISSUE | Detail Page | when doing quick send if we preview the letter and close the pop up or send letters, the button changes to Added to Campaign |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-02-14 | 2024-02-14 | 2024-03-06 |  | no767-added-to-campaign-quicksend-issue-sandeep-14feb2024
768 | 2024-02-12 | TASK | Planning Application | sort planning in alphabetic order and grey out councils without data |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-02-21 | 2024-03-04 | 2024-03-04 | @satheesh doing style | no768-planning-data-greyout-sandeep-21feb2024
769 | 2024-02-13 | ISSUE | Report | customize report page takes time to load the loader remains for sometime in the 3rd page reduce API calls |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-03-01 | 2024-03-07 | 2024-03-12 |  | No769_report_api_calls_usage_03_03_2024_Sharan_N_P
770 | 2024-02-13 | ISSUE | DMA Campaign | bulk mail not working |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-13 | 2024-02-13 | 2024-02-14 |  | No751_dma_remove_coma_in_address_06_02_2024_Sharan_N_P
771 | 2024-02-13 | ISSUE | Campaign History | Planning - delivery status is shown as Not Available for agent address in campaign history |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-02-15 | 2024-02-15 | 2024-03-06 | updated Feb 27: cannot check in demo | no771-planning-delivery-status-sandeep-15feb2024
772 | 2024-02-14 | ISSUE | Active Buyer | shows server error page when we view some addresses BN44 STEYNDENT LIMITED ADI HOLDINGS LIMITED 4 High Street, Steyning BN44 3GG is listed under both companies |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-15 | 2024-02-15 |  |  | No761_active_buyer_view_details_15_02_2024_Sharan_N_P
773 | 2024-02-14 | ISSUE | Detail Page | address is tagged as Company owned but the company details are not shown in the detail page 63, Chartley Avenue, London, NW2 7QY |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-15 | 2024-02-15 | 2024-03-06 |  | No754_company_owned_company_details_missing_14_02_2024_Sharan_N_P
774 | 2024-02-14 | ISSUE | Live campaign | gap between the tabs in twenty-targeted-instruction, directmail, targeted, active-buyer, planning-instruction |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-02-14 | 2024-02-14 | 2024-02-14
775 | 2024-02-15 | ISSUE | Report | from the Select sections page if we click on the back button 3-4 times, on returning to Select sections page the Submit button is missing user will have to go back again and then return to submit |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-16 | 2024-02-16 | 2024-02-29 |  | No775_report_generate_button_missing_16_02_2024_Sharan_N_P
776 | 2024-02-15 | ISSUE | Report | Report - Specific API company owned error |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-15 | 2024-02-15 | 2024-02-16 |  | No776_report_specific_api_error_15_02_2024_Sharan_N_P
777 | 2024-02-19 | TASK | Probate properties | Probate Quicksend - Remove property address automatically if executor trigger chosen and vice versa |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-02-26 | 2024-03-04 | 2024-03-25 | updated mar 8: * when we do quick send local print, each letters are printed twice. this happens when we print after previewing. * when we first select Family Executor or Follow Up trigger when doing quick send, non of the letters are selected - https://tinyurl.com/2bks69dh * when choosing the Family Executor and Follow-Up triggers, there seems to be an issue with the selected properties. The addresses being selected depends on the previously chosen trigger. | no777-trigger-chosen-probate-properties-sandeep-26feb2024
778 | 2024-02-19 | TASK | Probate Campaign | Remove property address automatically if executor trigger chosen and vice versa |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-02-27 | 2024-03-05 | 2024-03-25 | updated mar 6: total credits and no. of letters shown is not correct - https://tinyurl.com/23cbxeze updated mar 8: * Address limit exceeded message is shown only when we click in the edit box | no777-trigger-chosen-probate-properties-sandeep-26feb2024
779 | 2024-02-19 | TASK | Live campaign | Local Print - When agents choose this option sometimes the PDF comes up when it says letters to print sometimes it doesnt so we need to add in some text on that last box to say something like 'All pdf letters to print can be found via campaign history' clarify wording with Milton. |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-23 | 2024-02-23 | 2024-02-29 |  | No779_add_msg_local_print_text_23_02_2024_Sharan_N_P
780 | 2024-02-19 | TASK | Planning Application | Councils - Please can we make Derby a priority as this agent asks me weekly where it is as he wants to get going on it. List of many other councils I have sent over to be scrapped and prioritized so if we can please look at these and update me on ones we are struggling with just so I can manage our clients expectations. |  | VISHNU | COMPLETED
781 | 2024-02-19 | ISSUE | Targeted Properties | Targeted section - Max/Min price filter does not work. working but after entering the price we should change any other field[type/year] something like that |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-19 | 2024-02-28 | 2024-03-06 | updated feb 27: can we not use the same logic used in Lettings Targeted? Updated feb 28 : Make it same as lettings | No781_targeted_price_filter_19_02_2024_Sharan_N_P
782 | 2024-02-19 | UK TEAM | Report | Reports S&L - We need a page before the last page which includes statistics that agents can input. Makes the vendor want to call this agent as they have the most market share or get a tenant in within 5 days etc. (Potentially can use same toggles we have on side of letters with a few others) Again please clarify with Milton what stats he wants. | Web | RIJO | DISCUSS | LOW
783 | 2024-02-19 | ISSUE | Report | Planning dates error 18, Steel Close, Bromsgrove, Worcestershire, B60 3GQ |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-21 | 2024-02-22 | 2024-02-26 |  | No783_planning_date_error_22_02_2024_Sharan_N_P
784 | 2024-02-19 | TASK | Probate Detail | when doing quick send in the detail page, show the edit box first |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-02-29 |  | 2024-05-30 | updated mar 11: please add edit box in normal property quick send also | no784-quick-send-editbox-detailpage-sandeep-28feb2024
785 | 2024-02-20 | ISSUE | Report | Hospitals / GP / Dentists / NHS page - Response spelling error http://tinyurl.com/22kuc3ol |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-21 | 2024-02-21 | 2024-02-26 |  | No785_Report_NHS_page_spelling_mistake_21_02_2024_Sharan_N_P
786 | 2024-02-21 | ISSUE | Report | 4, 654, Lime Park Mews, Dorchester Road, Weymouth, Dorset, DT3 5LG property is marked as Terraced in db but in the report it's shown as Flat 'town house' moved to 'terraced' main type from 'unknown' main type |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-21 | 2024-02-21 | 2024-02-29 |  | No786_Report_epc_property_type_21_02_2024_Sharan_N_P
787 | 2024-02-22 | ISSUE | Properties | Flat 1, Rosewood, Park Road, Haslemere, Surrey GU27 2NJ not changed to Flat 2 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2085211 |  | RAHUL | COMPLETED | MEDIUM | [5 empty] | year only specified in rightmove so matching with the first price and year in sold data
788 | 2024-02-22 | ISSUE | Detail Page | getting an error page https://demo.devidiamober.com/properties/p-2477548 https://demo.devidiamober.com/properties/p-2473015 |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-23 | 2024-02-23 | 2024-02-29 |  | No786_Report_epc_property_type_21_02_2024_Sharan_N_P
789 | 2024-02-22 | ISSUE | Properties | zoopla gives full sold date but on our platform we are showing different dates in the detail page in the property info section and sold history sections Flat 59, Coleby House, 2, Woodley Crescent, London, NW2 2DL - the address shown on the platform is not correct, the sold date given in zoopla and that of the property displayed is different https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2505504 https://www.zoopla.co.uk/for-sale/details/66538276/ ----------------------------------------------------------------------------------------------------------------------------- 2, Bowhill Way, Harlow, Essex CM20 1FH - the address shown on the platform is not correct, the sold date given in zoopla and that of the property displayed is different sold date in Z is 30 Aug 2013 but that of the address shown is 20 Dec 2013 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2104865 https://www.zoopla.co.uk/for-sale/details/65804110/ |  | RAHUL | CLOSED | HIGH | [5 empty] | properties withdrawn
790 | 2024-02-22 | ISSUE | Report | Distance Calculator logic issue |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-02-22 | 2024-02-22 |  |  | No790_report_distance_calculator_issue_22_02_2024_Sharan_N_P
791 | 2024-02-27 | TASK | Listing Page | property filter logic change If the property is withdrawn and then becomes on market after 150 days, the property shouldn't be listed under 16 weeks or more; it needs to be considered as a new listing. This happens only if the property is listed by another agent. |  | RIJO | COMPLETED | MEDIUM |  | 4 day | 2024-03-13 | 2024-03-19 |  | updated mar 14: need an example to check in staging | no831_new_listing_logic_Rijo13Mar24
792 | 2024-02-27 | ISSUE | Report | Specific API Error - titleNumberData 4, 654, Lime Park Mews, Dorchester Road, Weymouth, Dorset, DT3 5LG |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-27 | 2024-02-27 | 2024-02-27 |  | No792_Report_specific_error_27_02_2024_Sharan_N_P
793 | 2024-02-27 | TASK | Report | Static Datas are shifted to mongodb |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-27 | 2024-02-28 | 2024-03-25 |  | No793_Static_datas_shifted_to_mongo_db_27_02_2024_Sharan_N_P
794 | 2024-02-27 | SUGGESTION | Live campaign | show the campaign count next to the title in the tabs itself (similar to lettings) |  | SHARAN | COMPLETED | LOW |  | 5 hrs | 2024-12-16 | 2024-12-16 | 2024-12-19 |  | No794_Campaing_count_display_tabs_Sharan_N_P_16_12_2024
795 | 2024-02-27 | ISSUE | Detail Page | property type in the detail page has _ in between the texts http://tinyurl.com/23unjjqo |  | RIJO | COMPLETED | LOW
796 | 2024-02-28 | ISSUE | Report | planning dates not correct for the property 1, Steel Close, Bromsgrove, Worcestershire, B60 3GQ 15, Railway Walk, Bromsgrove, Worcestershire, B60 3GJ 17, Railway Walk, Bromsgrove, Worcestershire, B60 3GJ please check if there is any issues with the dates for Bromsgrove |  | SHARAN | COMPLETED | HIGH |  |  | 2024-02-29 | 2024-02-29 | 2024-03-12 | https://prospectingtool.letsbidproperty.co.uk/view-report/report_8969_290220240527574309.pdf https://prospectingtool.letsbidproperty.co.uk/view-report/report_8970_290220240538825639.pdf | No796_797_Planning_dates_error_29_02_2024_Sharan_N_P
797 | 2024-02-28 | ISSUE | Report | planning dates missing in report 31, Illshaw Close, Redditch, B98 0QY 6, Alton Close, Redditch, Worcestershire, B97 5XH 210, Barnet Road, Potters Bar, Hertsmere, Hertfordshire, EN6 2SE |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-29 | 2024-02-29 | 2024-03-12 |  | No796_797_Planning_dates_error_29_02_2024_Sharan_N_P
798 | 2024-02-28 | ISSUE | Report | sold in street - addresses are going into market analysis https://prospectingtool.letsbidproperty.co.uk/view-report/report_8971_280220241420945814.pdf |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-02-29 | 2024-02-29 | 2024-03-12 |  | No798_Report_sold_street_page_overlaping_29_02_2024_Sharan_N_P
799 | 2024-02-29 | ISSUE | Probate properties | executor address when compared to Gazette is different Ruby Beckford Avon Lodge Uk Ltd, 33 Bridgend Road, Enfield, EN1 4PD https://www.thegazette.co.uk/notice/4449800 |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-02-06
800 | 2024-02-29 | ISSUE | Detail Page | floor plan is available in Rightmove/Zoopla listing but it's not shown in Letsbid detail page 51, Market Place, Hornsea, East Riding Of Yorkshire, HU18 1AP - https://www.rightmove.co.uk/properties/143097212#/?channel=RES_BUY |  | UNASSIGNED | CLOSED | MEDIUM
801 | 2024-03-04 | ISSUE | Detail Page | property images are available in RM/Z listing but in the detail page it shows broken image 13, Ballantine Road, Coventry, West Midlands CV6 3AP |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-03-08 | 2024-03-08 |  |  | No801_property_image_broken_link_08_03_2024_Sharan_N_P
802 | 2024-03-04 | ISSUE | Report | not able to generate reports |  | RIJO | COMPLETED | URGENT |  |  | 2024-03-04 | 2024-03-04 | 2024-03-04
803 | 2024-03-04 | ISSUE | Live campaign | when Market info is enabled, not able to send letters both bulk mail and local print is not working |  | RIJO | COMPLETED | URGENT |  |  | 2024-03-04 | 2024-03-04 | 2024-03-04
804 | 2024-03-05 | ISSUE | Detail Page | shows ,, in the detail page https://tinyurl.com/yqoo8khz 54, Turner Street, Stoke-On-Trent, ST1 2NF 46, Fifth Street, Horden, Peterlee, County Durham, SR8 4LA |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-03-22 | 2024-03-22
805 | 2024-03-06 | SUGGESTION | Planning Application | councils dropdown and the field - make it same width |  | SATHEESH | COMPLETED | LOW
806 | 2024-03-06 | Issue | Targeted Properties | Company Owned properties missing (check in detail page) 326, Lincoln Road, Enfield, EN3 4AA 328, Lincoln Road, Enfield, EN3 4AA |  | SHARAN | CLOSED | HIGH |  |  | 2024-03-06 | 2024-03-06 |  | updated mar 8: getting an error page when we click on an address https://tinyurl.com/2dawrtqv | No806_company_owned_properties_06_03_2024_Sharan_N_P
807 | 2024-03-06 | ISSUE | Campaign History | Planning - property address letter is shown instead of the agent address letter |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-03-07 | 2024-03-07 | 2024-03-08
808 | 2024-03-06 | ISSUE | Campaign History | Planning - shows Letter not available when we click on agent address |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-03-07 | 2024-03-07 | 2024-03-08
809 | 2024-03-07 | ISSUE | Detail Page | quick send bulk mail - after sending bulk mail, only when the page is refreshed the button changes to Add to Campaign and campaign history section is shown in the detail page |  | SANDEEP | COMPLETED | LOW |  | 4 hrs | 2024-03-27 | 2024-03-27 | 2024-04-23 | updated mar 28: * when doing quick send for an already contacted address, the address gets added to the campaign | no809-reload-issue-bulk-mail-sandeep-26mar2024
810 | 2024-03-07 | ISSUE | Probate Detail | quick send bulk mail - after sending bulk mail, only when the page is refreshed the button changes to Add to Campaign and campaign history section is shown in the detail page |  | SANDEEP | COMPLETED | LOW |  | 4 hrs | 2024-03-27 | 2024-03-27 | 2024-04-16 | Cache issue --------------- updated mar 20: have to refresh after quick send bulk mail, it works fine for local print | no809-reload-issue-bulk-mail-sandeep-26mar2024
811 | 2024-03-07 | ISSUE | Detail Page | listing activity not correct when compared to Zoopla listing history 45, Campbell Road, Hartlepool, TS25 3AZ |  | UNASSIGNED | COMPLETED | MEDIUM
812 | 2024-03-07 | SUGGESTION | Live campaign | do we need to show the addresses in blue like it's clickable? it is just displayed there, the addresses are not clickable |  | SATHEESH | CLOSED | LOW
813 | 2024-03-07 | ISSUE | Summary | spelling error - please change to TOTAL INSTRUCTIONS RECEIVED https://tinyurl.com/2a6wzmqm |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-03-08 | 2024-03-08 | 2024-03-14 |  | No813_Summary_spelling_mistake_08_03_2024_Sharan_N_P
814 | 2024-03-07 | SUGGESTION | Summary | can the boxes be aligned https://tinyurl.com/29rsfzof |  | SATHEESH | COMPLETED | LOW
815 | 2024-03-07 | ISSUE |  | menu - when the user is in outcode page and then click on Properties, the highlights overlap https://tinyurl.com/25hvaz6h |  | SHARAN | COMPLETED | LOW
816 | 2024-03-07 | SUGGESTION | Outcodes | the boxes shown when we choose outcodes, please make sure it's aligned https://tinyurl.com/26at3ccw |  | SATHEESH | COMPLETED | LOW
817 | 2024-03-07 | SUGGESTION | Letter management | create letter - please make sure the toggle button and the texts are aligned https://tinyurl.com/27cd482q |  | SATHEESH | COMPLETED | LOW
818 | 2024-03-07 | SUGGESTION | Anniversary Letter | addresses are not clickable, do we need to show it in blue and underlined ? |  | RIJO | COMPLETED | LOW |  | 15 mins | 2024-03-18 | 2024-03-19 | 2024-03-25 |  | no834_anniverasary_home_owner_greeting_18mar24
819 | 2024-03-07 | SUGGESTION | Probate Detail | can we show Last Sold Details below the map? |  | SATHEESH | CLOSED | LOW
820 | 2024-03-07 | SUGGESTION | Active Buyer | please show Find Company button in the same line as Properties Transacted in the Last Twelve Months https://tinyurl.com/ykqp2lnk |  | SHARAN | COMPLETED | LOW |  |  | 2024-12-13 | 2024-12-13 | 2024-12-17 |  | No820_Active_Buyer_find_company_text_alignment_Sharan_N_P_13_12_2024
821 | 2024-03-08 | ISSUE - DEMO | Probate Campaign | total credits and no. of letters shown is not correct https://tinyurl.com/22enxfrn |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-03-08 | 2024-03-11 | 2024-03-12 |  | no821-probate-campaign-credit-issue-sandeep-08mar2024
822 | 2024-03-08 | TASK | Report | Complete Static Datas are shifted to mongodb - airport, population |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-03-08 |  | 2024-03-25 |  | No793_Static_datas_shifted_to_mongo_db_27_02_2024_Sharan_N_P
823 | 2024-03-11 | ISSUE | Detail Page | when doing quick send, please show Sending Bulk Mail loader (similar to campaign) |  | SANDEEP | COMPLETED | LOW |  | 4 hrs | 2024-03-26 | 2024-03-27
824 | 2024-03-11 | ISSUE | Report | message shown when no suggestions are available - difficult to see against the background https://tinyurl.com/28jh8ms2 |  | RIJO | COMPLETED | MEDIUM | [6 empty] | no1311_report_fix_Rijo_04_10_24
825 | 2024-03-11 | ISSUE | Live campaign | if the address exceeds the limit, the message is shown only when we click in the edit box |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs |  |  |  | @Rishika : Please provide an example for testing #Sandeep - 26Mar2024
826 | 2024-03-11 | ISSUE | Report | when we generate report by clicking on Generate Report button in the property detail page and then generate another report for a different address in property report page, the property image, floor plan and market price is the same as that of the address which was first generated to get the issue: 1. go to a property detail page 2. click on Generate button 3. Generate report for the address 4. In the Property report page, search for a new address 5. Generate a new report 6. Check property images |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-03-11 | 2024-03-11 | 2024-03-11 |  | No639_report_page_reload_11_03_2024_Sharan_N_P
827 | 2024-03-11 | TASK | Detail Page | quick send - when doing quick send in the detail page, show the edit box first |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-03-26 | 2024-03-27 | 2024-05-27 | updated mar 28: * even if we edit the address, it does not reflect in the letter * if we edit the address and continue, the address gets added to the campaign --------------------- updated apr 3: * even if we edit the address, it does not reflect in the letter * remove in the edit box does not work, either hide it as there is an option to select address in the quick send pop up | no827-editbox-normal-properties-quicksend-sandeep-12mar2024
828 | 2024-03-12 | SUGGESTION | Detail Page | if the floorplan is in pdf, on clicking do we need to open the image like we do for floorplans? https://tinyurl.com/29fl6yqq 18, Hill View Gardens, Halifax, West Yorkshire HX3 7BT |  | SHARAN | CLOSED | LOW
829 | 2024-03-12 | ISSUE | Detail Page | property has floorplan but it's not shown in the detail page 18, Middleton Road, Morden, London, SM4 6SD Polperro, Goole Road, Hook, Goole, East Riding Of Yorkshire DN14 5NG 21, Belgrave Gardens, London, N14 4TS |  | SHARAN | CLOSED | MEDIUM
830 | 2024-03-12 | ISSUE | Detail Page | property images are available in RM or Z listing but the images are not shown on our platform 64, Towpath Close, Longford, Coventry, Warwickshire CV6 6RG 13, Ballantine Road, Coventry, West Midlands CV6 3AP |  | SHARAN | COMPLETED | MEDIUM |  |  |  |  | 2024-05-29 |  | No830_property_image_break_issue_14_03_2024_Sharan_N_P
831 | 2024-03-13 | TASK | Listing Page | 16 weeks - new listing |  | RIJO | DUPLICATE TASK | MEDIUM
832 | 2024-03-13 | TASK | Report | report ui improvement (refer sprift report) show agent address in the front page (similar to sprift report) property plot boundary info missing to add - outside space (imp), uprn, council tax band (imp), additional epc data, planning history, house price stats - improve ui introduction - 2nd page ---------------------------------------------------- https://sprift.com/dashboard/property-report/107-bourne-vale-bromley-br2-7nw/2115712 Sellers reports: https://sprift.com/dashboard/property-report/11-diamond-jubilee-way-carshalton-sm5-4as/3262826 |  | SATHEESH | COMPLETED | HIGH |  |  | 2024-03-25
833 | 2024-03-13 | ISSUE | Targeted Properties | targeted url shorten |  | SHARAN | COMPLETED | HIGH |  | 1 day | 2024-03-14 | 2024-03-15 | 2024-03-20 |  | No833_targeted_url_shorten_13_03_2024_Sharan_N_P
834 | 2024-03-13 | TASK | Anniversary Letter | Option to edit each template to include homeowners name instead of "Dear Homeowners" |  | RIJO | COMPLETED | MEDIUM |  | 2 day | 2024-03-18 | 2024-03-20 | 2024-03-25 | updated Mar 20: the greeting entered is not shown in the letter when we print | no834_anniverasary_home_owner_greeting_18mar24
835 | 2024-03-14 | UK TEAM | Title Plan/Register | option to purchase title plan and title register (refer Propmarker) | Web | SHARAN | DISCUSS | HIGH | [5 empty] | already done in lettings, need to confirm if it's needed in Sales platform
836 | 2024-03-14 | ISSUE - DEMO | Probate Detail | when we preview addresses, it gets added to campaign |  | SANDEEP | CLOSED | MEDIUM
837 | 2024-03-14 | DISCUSS |  | static data platform | Web | SHARAN | HOLD | MEDIUM |  | 2 weeks |  |  |  | - new data will be pushed to mongodb - option to edit current static data is pending
838 | 2024-03-14 | ISSUE | Active Buyer | url shorten |  | SHARAN | COMPLETED | HIGH |  | 1 day | 2024-03-14 | 2024-03-15 | 2024-03-20 |  | No833_targeted_url_shorten_13_03_2024_Sharan_N_P
839 | 2024-03-14 | DISCUSS | Report Revamp | sprift report data sources Sprift Report Data Source |  | RIJO | CLOSED | MEDIUM
840 | 2024-03-15 | ISSUE | Detail Page | quick send - even if the credits are 0, using the quick send in the detail page user can still send bulk mail |  | SANDEEP | COMPLETED | HIGH |  | 1 day | 2024-03-20 | 2024-03-21 | 2024-03-25 |  | no840-send-bulk-mail-with-no-credits-sandeep-20mar2024 no840-1-credit-issue-bulk-mail-sandeep-25mar2024
841 | 2024-03-15 | ISSUE | Probate Detail | quick send - the property gets added to campaign if we go to the pop up and then close it |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-03-21 | 2024-03-21 | 2024-03-25 |  | no841-added-to-campaign-issue-sandeep-21mar2024
842 | 2024-03-15 | ISSUE | Probate Detail | executor address is not fully shown 37 Greenway, London, N14 6NR - |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-03 | 2024-04-03 | 2024-05-27 |  | no842-executor-address-error-sandeep-03Apr2024
843 | 2024-03-15 | ISSUE | Probate Campaign | when sending letters to some addresses, the postcode is not shown with the executor address even when it's available https://tinyurl.com/2azkvrwu 37 Greenway, London, N14 6NR - https://www.thegazette.co.uk/notice/4572367 Hampden House, 120 Duchy Road, Harrogate, North Yorkshire, HG1 2HE |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-03 | 2024-04-03 | 2024-05-27 |  | no842-executor-address-error-sandeep-03Apr2024
844 | 2024-03-15 | ISSUE | Back to Market | some properties that are marked as Back to market, when checked with RM/Z the added on date is different (looks like the property was not withdrawn but we have marked it as withdrawn) 107, Wytham Street, Oxford, Oxfordshire OX1 4TN 81, Medcalf Road, Enfield, London, EN3 6HJ 20, Werrell Drive, Wootton, Oxford, Oxfordshire OX1 5LF 253, Shaw Road, Royton, Oldham, Greater Manchester, OL2 6EF 12, Orchard Way, Snodland, Tonbridge And Malling, Kent, ME6 5EW 110, Holborough Road, Snodland, Kent ME6 5PB |  | SANDEEP | COMPLETED | HIGH
845 | 2024-03-15 | ISSUE | Back to Market | listing activity for Rightmove is not correct, it is withdrawn but we are showing as For sale 6, Arncott Close, Royton, Oldham, Greater Manchester, OL2 6SN |  | UNASSIGNED | COMPLETED | MEDIUM
846 | 2024-03-18 | SUGGESTION | Detail Page | quick send in detail page - after clicking on local print buttons the pop up doesn't close and also the buttons are not disabled agent can click on local print multiple times |  | SHARAN | COMPLETED | LOW |  | 1hrs | 2024-03-21 | 2024-03-21 |  | updated Mar 25: the pop up closes but 2 campaigns are generated | No846_847_quick_send_modal_hide_21_03_2024_Sharan_N_P
847 | 2024-03-18 | SUGGESTION | Probate Detail | quick send in detail page - after clicking on local print buttons the pop up doesn't close and also the buttons are not disabled agent can click on local print multiple times |  | SHARAN | COMPLETED | LOW |  | 1hrs | 2024-03-21 | 2024-03-21 |  | updated Mar 25 the pop up doesnt close when we click on local print | No846_847_quick_send_modal_hide_21_03_2024_Sharan_N_P
848 | 2024-03-18 | SUGGESTION | Report | when reports are downloaded (click on download button), the file name shoud be the property address |  | SHARAN | CLOSED | LOW
849 | 2024-03-18 | ISSUE | Withdrawn | if property is under offer/stc/STC REMOVED and then becomes withdrawn, please remove it from withdrawn 51, Fernwood Avenue, Hartlepool TS25 5LU 27, Clarkson Court, Hartlepool TS25 5HP 7, Felixstowe Close, Hartlepool TS25 2RE 9, Bennett Road, Hartlepool TS25 4NR 21, Countisbury Avenue, Enfield, London, EN1 2NL 7, Philip Avenue, Bowburn, Durham, County Durham, DH6 5EQ 6, Foster Terrace, Croxdale, Durham, County Durham, DH6 5HP 1, Hawthorn View, Thornley, Durham, Easington, DH6 3HZ 33, Carlisle Street, Hartlepool, TS25 1BL |  | SANDEEP | COMPLETED | HIGH |  |  |  |  | 2024-10-02
850 | 2024-03-19 | SUGGESTION | Planning Application | option to search Councils (please refere Planning Application in PropMarker) |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-15 | 2024-04-16 | 2024-04-23 | #delayed due to style changes | no850-option-to-search-council-sandeep-11apr2024
851 | 2024-03-19 | ISSUE | Planning Campaign | edit address keeps loading when we select addresses under Hartlepool |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-02 | 2024-04-02
852 | 2024-03-19 | ISSUE | Active Buyer | detail page - spelling error in company details section, please change to PROPRIETOR ADDED |  | SANDEEP | COMPLETED | MEDIUM |  | 30 mins | 2024-03-22 | 2024-03-22 |  |  | no852-active-buyer-spelling-mistake-sandeep-22mar2024
853 | 2024-03-20 | TASK | Listing Page | implement new logic for 16 weeks or more in listing If the property is withdrawn and then becomes on market after 150 days, the property shouldn't be listed under 16 weeks or more; it needs to be considered as a new listing. This happens only if the property is listed by another agent. |  | SANDEEP | COMPLETED | HIGH
854 | 2024-03-20 | ISSUE | Active Buyer | address in the listing and detail page is different CV2 - THE PROPERTY BUYING COMPANY SPV1 LIMITED address not correct when compared to company registration page CV2 - THE PROPERTY BUYING COMPANY SPV1 LIMITED company address is the same as property address CV2 - BDW TRADING LIMITED |  | DATA TEAM | CLOSED | MEDIUM
855 | 2024-03-20 | ISSUE | Detail Page | quick send - when we click on bulk mail quick send without selecting a trigger 1. credits are deducted from the wallet even though no letters are sent 2. a blank campaign is created in cmapaign history 3. shows server error page when we go to the detail page of the property |  | SANDEEP | COMPLETED | HIGH |  | 1 day | 2024-03-20 | 2024-03-21 | 2024-03-25 |  | no840-send-bulk-mail-with-no-credits-sandeep-20mar2024
856 | 2024-03-20 | ISSUE | Report | Flat 1, 5, John Street, Stroud, Gloucestershire, GL5 2HA (probate address) comparables are shown in the detail page but when generating reports, only when we give custom value comparables are shown. also the comparables shown in report and detail page are different |  | SHARAN | COMPLETED | LOW |  | 4hrs | 2024-03-21 | 2024-03-21
857 | 2024-03-20 | ISSUE | Targeted Properties | when company registration number not provided - the other properties owned by company has wrong data eg: Flat 2, 17, Bower Road, Harrogate, North Yorkshire, HG1 1BE 81 not owned by that company |  | SHARAN | COMPLETED | HIGH |  | 2hrs | 2024-03-20 | 2024-03-20 |  |  | No857_company_own_properties_company_registration_20_03_2024_Sharan_N_P
858 | 2024-03-21 | TASK | Title Plan/Register | Design for purchase title plan and title register |  | SATHEESH | COMPLETED | HIGH | [5 empty] | already done in lettings, need to confirm if it's needed in Sales platform
859 | 2024-03-21 | TASK | Anniversary Letter | if the next send date is within one week of the sold date, we will show a prompt to the agent |  | RIJO | COMPLETED | HIGH |  | 3 day | 2024-03-21 | 2024-04-04 | 2024-04-04 |  | no859_anniversary_properties_notify_agents_Rijo21Mar24
860 | 2024-03-21 | ISSUE - DEMO | Dashboard | there are properties in quick send but it shows no properties |  |  | COMPLETED | MEDIUM
861 | 2024-03-21 | TASK | Comparable Tool | Comparison tool |  | SHARAN | COMPLETED | MEDIUM |  | 4 days | 2024-05-10 | 2024-05-15 |  | updated may 17: "in the exported file: * Â is shown in front of the pound symbol in few columns * if date is not available, in the exported file it's given as 01-01-1970" when we click on the Reset button, the property type dropdown does not get cleared when we click on Reset button the comparables are not cleared | No861_Comparison_tool_13_05_2024_Sharan_N_P
862 | 2024-03-25 | ISSUE | Dashboard | Property Insights ¦ Last 30 Days - there are properties in the quick send list but when we click on the quick send button it shows No properties |  | SANDEEP | COMPLETED | URGENT |  | 3 hrs | 2024-03-25 | 2024-03-25 |  |  | no862-1-button-click-issue-dashboard-sandeep-25mar2024
863 | 2024-03-28 | ISSUE | Planning Application | Council has data but it's not active, it's still greyed out Derby Reading Kensington And Chelsea Brent Bournemouth Christchurch And Poole |  |  | COMPLETED | MEDIUM
864 | 2024-04-02 | ISSUE | Report | not able to generate reports for some addresses TA1, TA6, HG1 |  | SHARAN | COMPLETED | MEDIUM
865 | 2024-04-03 | ISSUE | Planning Campaign | if the address is in a single line or postcode is not available, only if we click in the edit box the warning message is shown |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-05 | 2024-04-05 | 2024-05-27 | updated Apr 9: * not able to print or send bulk mail if there is an address in single line, even if we remove or edit it | no865-editbox-warning-message-sandeep-05Apr2024
866 | 2024-04-04 | ISSUE | Active Buyer Campaign | when user adds the address to campaign from the detail page it shows undefined in Active buyer campaign listing but the address is shown in edit box https://tinyurl.com/28t7l68p to get the issue: 1. go to Active Buyer listing 2. click on view list for any company 3. click on View details for a property 4. in the detail page, click on Add to campaign 5. check in active campaign listing |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-08 | 2024-04-08 | 2024-04-23 | updated Apr 9: * shows "undefined" when we add to campaign from the active buyer property detail page | no866-active-buyer-campaign-issue-sandeep-08apr2024
867 | 2024-04-04 | ISSUE | Probate properties | shows number of rows selected near entries, when we select any addresses or when we click beside the radio button https://tinyurl.com/2chmsmq9 |  | SANDEEP | COMPLETED | LOW |  | 4 hrs | 2024-04-09 | 2024-04-09 | 2024-04-23 |  | no867-number-of-rows-selected-sandeep-09apr2024
868 | 2024-04-04 | ISSUE | Targeted Properties | shows 1 row selected near the number of entries when we click beside the radio button https://tinyurl.com/27dzpdo4 |  | SANDEEP | COMPLETED | LOW |  | 4 hrs | 2024-04-09 | 2024-04-09 |  |  | no867-number-of-rows-selected-sandeep-09apr2024
869 | 2024-04-05 | TASK | Planning Application | if agent_name and agent_company_name is not available put applicant_name and property address | Data | DATA TEAM | NOT STARTED | MEDIUM
870 | 2024-04-05 | ISSUE | Report | not able to generate report ML16 |  | SHARAN | CLOSED | MEDIUM
871 | 2024-04-05 | ISSUE | Summary | bulk mail letter sent count is not correct 2nd instruction 20-20 |  |  | CLOSED
872 | 2024-04-05 | ISSUE | Detail Page | when doing quick send local print from the detail page, 2 campaigns are created please check in campaign history page |  | SANDEEP | COMPLETED | MEDIUM | [5 empty] | test if issue exist again ------------ updated Apr 30: 2 campaigns are created when we do quick send local print @Rishika : Issue only in live, will clear after some branches may get merge
873 | 2024-04-05 | ISSUE | Probate Detail | when doing quick send local print in probate detail page, when we print the letters after previewing in the generated pdf the number of letters are doubled eg: if we are sending letters to 2 addresses, after previewing and local printing in the pdf there will be a total of 4 letters in that campaign https://tinyurl.com/2aej342k |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-26 |  |  | test if issue exist again ------------------------------------ please check in live @Rishika : Issue only in live, will clear after some branches may get merge
874 | 2024-04-09 | ISSUE | Listing Page | shows number of rows selected near entries, when we select any addresses or when we click beside the radio button |  | SANDEEP | COMPLETED | LOW |  | 2 hrs | 2024-04-09 | 2024-04-09 |  |  | no867-number-of-rows-selected-sandeep-09apr2024
875 | 2024-04-09 | TASK | Report | Option to edit address |  | SHARAN | COMPLETED | HIGH |  | 16 hrs | 2024-05-23 | 2024-05-24 | 2024-06-05 |  | No875_Report_option_to_edit_address_23_05_2024_Sharan_N_P
876 | 2024-04-09 | ISSUE | Live campaign | bulk mail campaigns are not working |  |  | COMPLETED | URGENT | [5 empty] | stannp balance issue
877 | 2024-04-09 | ISSUE | Quick Send | bulk mail is not working |  |  | COMPLETED | URGENT | [5 empty] | stannp balance issue
878 | 2024-04-09 | ISSUE | Settings | when we change the email address to an already used email it shows server error |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-04-10 | 2024-04-10 | 2024-04-23 |  | no878-email-already-used-sandeep-10apr2024
879 | 2024-03-10 | TASK | Report Revamp | add parking facilities, accessibility features, utility supplies, rights and restrictions, service charge |  | RIJO | COMPLETED | MEDIUM
880 | 2024-03-10 | ISSUE | Report | ambulance response time issue for address Swansea Bay University Health Board Ash Tree Cottage, Swansea, SA3 1EH |  | RIJO | CLOSED | MEDIUM
881 | 2024-04-11 | ISSUE | Listing Page | the count shown for RM and Z icons are not aligned properly https://tinyurl.com/2crh2nda |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-02 | 2024-12-02 | 2024-12-05 |  | No881_Properties_rm_z_count_align_Sharan_N_P_02_12_2024
882 | 2024-04-11 | ISSUE | Detail Page | the count shown for RM and Z icons are not aligned properly |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-02 | 2024-12-02 | 2024-12-05 |  | No881_Properties_rm_z_count_align_Sharan_N_P_02_12_2024
883 | 2024-04-11 | ISSUE | Live campaign | preview - when there are lots of addresses in the campaign (more than 250), not able to preview the letters nothing happens when we click on the preview button | Web | SANDEEP | IN PROGRESS | MEDIUM |  | 4 hrs | 2024-05-24 |  | 2024-11-29 | Updated Jun 6: if there are 200 addresses, the preview doesnt work for local print targeted campaign, 2nd instruction ----------------- updated jul 12: * probate campaign - local print does not work when there are 100 letters * when there are 100 addresses, on clicking on bulk mail or local print no loader is shown * planning campaign - bulk mail and local print does not work when there are 100 letters ---------------------- updated Oct 17: - probate - loader is not shown for local print (it's there for bulk mail) - probate bulk mail - after clicking on confirm and send button, the loader is not shown (check 2nd instruction) ----------------------- updated Nov 19: - probate - loader is not shown for local print (it's there for bulk mail) | no883-more-than-200-address-in-campaign-sandeep-24may2024 correct branch - no883-sub-more-than-200-letters-issue-sandeep-18nov2024 ------------- put in a new branch
884 | 2024-04-12 | ISSUE | Active Buyer | Getting an error page when we click on View Details of the property B60 - COUNTRYWIDE TAX & TRUST CORPORATION LIMITED (Wharf Cottage, Shaw Lane, Stoke Prior, Bromsgrove, B60 4EQ) |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-19
885 | 2024-04-12 | ISSUE | Active Buyer | property is listed under a company but it shows "Company details not found." in the detail page of the property B60 - COUNTRYWIDE TAX & TRUST CORPORATION LIMITED (Wharf Cottage, Shaw Lane, Stoke Prior, Bromsgrove, B60 4EQ) https://tinyurl.com/24eexfpx check company register number - rijo https://tinyurl.com/2cnsbl63 |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-22 |  | 2024-05-27 |  | no885-company-details-not-found-sandeep-22apr2024
886 | 2024-04-12 | SUGGESTION | Probate Campaign | when sending letters to lots of addresses, please show loaders - after clicking on bulk mail or local print button it takes some time to show the edit box - there is a delay in showing the Bulk Mail Confirmation pop up after clicking on Confirm and send bulk mail button | Web | SANDEEP | IN PROGRESS | MEDIUM | [5 empty] | related to 883
887 | 2024-04-12 | SUGGESTION | Probate Campaign | when sending bulk mail to lots of addresses, there is a delay in showing the Bulk Mail Confirmation pop up after clicking on Confirm and send bulk mail button please show a loader in such case |  | SANDEEP | DUPLICATE TASK | LOW
888 | 2024-04-12 | ISSUE | Probate Campaign | when the trigger selected is executor/property, even if the addresses are removed the user cannot proceed if a warning message is shown for the removed address https://tinyurl.com/27bkuy7s |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-15 | 2024-04-15 | 2024-05-30 | updated May 8: does not work, not able to proceed if a warning message is shown for removed address Northend Cottage, Main Street, Rye, TN31 6LE | no888-trigger-issue-warning-message-sandeep-15apr2024
889 | 2024-04-12 | ISSUE | Report | for some addresses the suggestions shown are not correct correct suggestions are shown when we search with just the flat number and postcode Flat 4, 141 West Wycome Road, High Wycombe, HP12 3AB Flat 2, Worcester Court, Anderton Road, Aldermans Green, Coventry, West Midlands, CV6 6JQ Flat 125, Langford Court, 22, Abbey Road, London, City Of Westminster, London, NW8 9DP https://tinyurl.com/2d9qkp38 |  | SHARAN | CLOSED | LOW | [5 empty] | getaddress limitation
890 | 2024-04-15 | DISCUSS | Report | sold comparables and on market comparables - shouldnt we show similar properties in terms of property type, bedroom count? |  | RIJO | CLOSED | MEDIUM
891 | 2024-04-15 | ISSUE | Live campaign | if the address is in 2 lines, when we send bulk mail to that address the letters are failing please check in all the campaigns |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-30 |  | 2024-05-27 |  | no891-address-line-issue-bulksend-30Apr2024
892 | 2024-04-15 | ISSUE | Planning Campaign | even if some addresses are not proper, no warning messages are shown https://tinyurl.com/2add52p4 |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-18 |  | 2024-05-27 |  | no892-warning-for-planning-campaign-sandeep-18apr2024
893 | 2024-04-16 | ISSUE | Detail Page | quick send preview - in front of the preview displayed another pop up is shown https://tinyurl.com/2yydv2ss |  | SANDEEP | COMPLETED | MEDIUM |  | - | 2024-04-18 |  |  | cant reproduce the issue
894 | 2024-04-16 | ISSUE | Report | on market comparable keeps loading 68, Knocklea, Biggar, Lanarkshire ML12 6EG |  | SANDEEP | CLOSED | MEDIUM
895 | 2024-04-16 | ISSUE | Detail Page | quick send bulk mail - after editing the address, even if we edit the address the changes does not reflect in the letter |  | SANDEEP | COMPLETED | MEDIUM |  | 6 hrs | 2024-05-01 |  | 2024-05-27 | updated may 8: getting an error page when we do quick send bulk mail in the detail page | no891-address-line-issue-bulksend-30Apr2024
896 | 2024-04-16 | ISSUE | Active Buyer | active buyer property detail page - Campaign History section when we click on the campaign, user is redirected to targeted campaign history detail B60 - COUNTRYWIDE TAX & TRUST CORPORATION LIMITED 13 Wyndham Road, Woking, GU21 3DS https://tinyurl.com/23tdpwp9 |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-22 | 2024-04-22 |  | updated May 7: not updated in live | no885-company-details-not-found-sandeep-22apr2024
897 | 2024-04-16 | ISSUE | Quick Send | quick send local print is not working, it shows a blank pop up and also the campaign is empty |  | SANDEEP | COMPLETED | URGENT |  | 6 hrs | 2024-04-17 |  |  |  | quicksend-test-17apr2024
898 | 2024-04-16 | TASK | Report | comparables - change it to the same logic as Propmarker |  | SHARAN | COMPLETED | HIGH |  | 4 hrs | 2024-04-19 | 2024-04-19 |  | updated Apr 23: when generating report, the sold and rental comparable keeps loading and also it's not shown in the report in the property detail page, the comparable section keeps loading ------------------------------- updated Apr 30: for on market comparables are not shown according to the bedroom given | No903_report_comparabels_not_found_19_04_2024_Sharan_N_P
899 | 2024-04-16 | ISSUE | Report | even if property has sqft, the sqft is not being displayed the first time |  | RIJO | COMPLETED | HIGH
900 | 2024-04-17 | ISSUE | Probate properties | property has sold history but it's not shown 1, Snow Hill, Leicester LE4 0GX 29 Vantage Copse, Southampton, SO31 1ES 16 Lynmouth Road, Coventry, CV2 1AN 79 The Grove, Southampton, SO19 9LW 9 Vineyard Drive, Telford, TF1 1SE |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-25
901 | 2024-04-17 | ISSUE | Targeted Properties | Properties owned by the company code change |  | SHARAN | TEST STAGING | HIGH |  | 3hrs | 2024-04-17 | 2024-04-17 |  |  | No901_company_owned_code_change_17_04_2024_Sharan_N_P
902 | 2024-04-18 | TASK | Report | show a page showing recently sold properties for other property types Other Property Type on Street * if the property is semi detached, in this page we will be showing Terraced and Detached proeprties * if property is detached, in this page we will be showing Semi-detached and terraced * if property is terraced, in this page we will show detached and semi-detached * For Flat, we will be shown Maisonette and terraced |  | SHARAN | COMPLETED | HIGH |  |  | 2024-04-23 | 2024-04-26 | 2024-05-06 | updated May 2: * Other Property Type Comparables pop up - please change the text shown below the title - https://tinyurl.com/ylh9wdjq * | No902_Report_comparables_other_property_types_23_04_2024_Sharan_N_P
903 | 2024-04-18 | ISSUE | Report | comparable Not Found Govan, Weymouth, Dorset, DT3 4BH |  | SHARAN | COMPLETED | HIGH |  | 4 hrs | 2024-04-19 | 2024-04-19 |  | updated Apr 23: when generating report, the sold and rental comparable keeps loading and also it's not shown in the report in the property detail page, the comparable section keeps loading | No903_report_comparabels_not_found_19_04_2024_Sharan_N_P
904 | 2024-04-22 | ISSUE | Targeted Properties | Export csv - The count of properties in the exported file does not match the count in the listing. The exported file contains more properties than what is listed. |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-04-23 | 2024-04-23 | 2024-05-30 | updated Apr 30: on clicking Export CSV it shows "File wasn't available on the site" | no904-export-csv-for-targeted-sandeep-23apr2024
905 | 2024-04-22 | ISSUE | Active Buyer | in the detail page of a property under "Other properties owned by the company", even if the property type is known it's shown as not available |  | SANDEEP | CLOSED | MEDIUM |  | 4 hrs |  |  |  | @Rishika : need example #Sandeep
906 | 2024-04-22 | SUGGESTION |  | if we sign in and return to the page after a long time, instead of showing 419 ¦ PAGE EXPIRED can we not show someother page https://tinyurl.com/24gbh7e3 |  | RIJO | DUPLICATE TASK | LOW
907 | 2024-04-22 | ISSUE | Planning Campaign | address not proper https://tinyurl.com/2yxxo942 | Data | DATA TEAM | HOLD | MEDIUM | [5 empty] | @Rishika : the agent address getting from mongodb can edit by edit address box #Sandeep | -
908 | 2024-04-23 | ISSUE | Wallet/Credit | please change the title when agent tops up, it's shown as Land Registry Title File - £ and also the credits are not getting added to the wallet when they top up |  | SHARAN | COMPLETED | URGENT |  |  | 2024-05-27 | 2024-05-28 |  |  | No420_Land_registrty_webhook_18_04_2024_Sharan_N_P
909 | 2024-04-25 | ISSUE | Active Buyer | when we click on the back button from the active buyer campaign history it shows an error page - https://tinyurl.com/25suy69p when we click on the campaign history in the active buyer detail page |  | SANDEEP | COMPLETED | MEDIUM |  | 6 hrs | 2024-04-25 |  | 2024-06-13 | Updated Jun 6: works but when click on the back button from the campaign history onyl the first letter of the property type is shown | no909-active-buyer-campaign-history-sandeep-25Apr2024
910 | 2024-04-29 | ISSUE | Price Drop | not able to add properties to campaign from price drop listing |  |  | CLOSED | MEDIUM
911 | 2024-04-20 | ISSUE | Anniversary Letter | Pending Anniversary Letters alert - even if the letters are inactive, the pending alert is shown |  | RIJO | COMPLETED | LOW |  | 1 hrs | 2024-05-03 | 2024-05-03 | 2024-05-08
912 | 2024-04-30 | ISSUE | Planning Campaign | agent address edit box - if the address is in a single line or postcode is not available, only if we click in the edit box the warning message is shown |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | no need of validation for agent address
913 | 2024-05-01 | ISSUE | Detail Page | property images are available in RM or Z listing but the images are not shown on our platform 21B, Danbury Street, London, Islington, London, N1 8LE 100, Palace Meadow, Chudleigh, Newton Abbot, Teignbridge, Devon, TQ13 0PJ |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-05-29 | 2024-05-29 | 2024-05-29 |  | No830_property_image_break_issue_14_03_2024_Sharan_N_P
914 | 2024-05-01 | ISSUE | Withdrawn | property is on sale but it's listed as withdrawn 15, Gray Drive, Swanton Morley, Dereham, Breckland, Norfolk, NR20 4PG 8, The Larches, Hawarden, Deeside, Flintshire, CH5 3LH |  |  | COMPLETED | MEDIUM
915 | 2024-05-01 | ISSUE | Report | if the floorplan is pdf, when we generate report it shows a blank page for floorplan 18, Hill View Gardens, Halifax, West Yorkshire HX3 7BT 23, Travellers Gate, Hartlepool, TS25 5TD 6, Symington Street, Leadhills, Biggar, Lanarkshire ML12 6YE |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-07 | 2024-08-07 |  | please speak to Jinto
916 | 2024-05-01 | ISSUE | Sold- Under offer | zoopla activity not updated 30, Perham Way, London Colney, St Albans, Hertfordshire, AL2 1LB |  | RISHIKA | COMPLETED | MEDIUM
917 | 2024-05-06 | ISSUE | Report | 18, Coppice Rise, Harrogate, North Yorkshire HG1 2DP - has sold comparables in the detail page but not shown in the report |  | RISHIKA | COMPLETED | MEDIUM
918 | 2024-05-02 | TASK |  | static page - data import |  | SHARAN | CLOSED | MEDIUM | [6 empty] | No918_report_static_data_import_feature_02_05_2024_Sharan_N_P
919 | 2024-05-02 | ISSUE | Detail Page | not able to add properties to campaign after previewing it please check quick send in detail page and dashboard |  | SANDEEP | COMPLETED | HIGH |  | 4 hrs | 2024-05-06 | 2024-05-06 | 2024-05-30 | updated may 8: getting an error page when we do quick send bulk mail in the detail page updated may 17: when we preview letters in dashboard quick send and close without sending and add any of the properties in the quick send list, in live campaign it is shown as greyed out https://tinyurl.com/22k5ladh | added-to-campaign-after-preview-issue-sandeep-02may2024
920 | 2024-05-03 | TASK | Report Revamp | add bunglow type to custom value drop down |  | SHARAN | COMPLETED | MEDIUM |  | 8 | 2024-06-05 | 2024-06-05 |  |  | No920_Report_custom_property_type_bunglow_Sharan_N_P_05_06_2024
921 | 2024-05-03 | TASK | Report | Comparables - He said that sometimes with our reports it doesnt grab the closest comparables for example I have attached the hollyhocks report below. If you look at the rightmove link there are 3 comparables that are right by the property (one being his own!) that dont show up. This needs to be sorted asap how can our reports not show the closest comps? if you look at the picture below the comps are from 375k to 1.7m? He said how are they comparables? Maybe we could include a price range which just pulls up comps for the price range they put in? |  | SHARAN | COMPLETED | MEDIUM
922 | 2024-05-03 | TASK | Campaign History | option to redo campaign on clicking the redo button all the addresses in that campaign gets added to the respective campaign |  | SANDEEP | COMPLETED | HIGH |  | 16 hrs | 2024-05-17 |  | 2024-05-27
923 | 2024-05-06 | ISSUE | Report | address suggestions are not shown when search an address or postcode in reposrt generation page |  | RIJO | COMPLETED | URGENT |  |  |  |  | 2024-05-06
924 | 2024-05-06 | ISSUE | Detail Page | comparable section keeps loading in the detail page |  | RIJO | COMPLETED | MEDIUM |  |  |  |  | 2024-05-06
925 | 2024-05-06 | ISSUE | Live campaign | Letters are not reaching stannp when we do bulk mail, credits are deducted from wallet and also a blank campaign is created in campaign history |  | RIJO | COMPLETED | URGENT |  |  |  |  | 2024-05-06
926 | 2024-05-06 | ISSUE | Report | sold comparables shown are more than 1 mile https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_10221_060520241804313275.pdf |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-05-07 | 2024-05-07 | 2024-05-15 |  | No926_927_comparables_issues_07_05_2024_Sharan_N_P
927 | 2024-05-07 | ISSUE | Report | for on market comparables are not shown according to the bedroom given 34, Bunyan Road, Hitchin, Hertfordshire, SG5 1NW |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-05-07 | 2024-05-07 | 2024-05-15 |  | No926_927_comparables_issues_07_05_2024_Sharan_N_P
928 | 2024-05-07 | ISSUE | Detail Page | quick send - when doing quick send in the detail page, the edit box is not shown |  | SANDEEP | COMPLETED | MEDIUM
929 | 2024-05-07 | TASK | Report | add the following data to the report Accommodation type Adults and children in household Number of adults in employment in household Tenure of household Country of birth Distance travelled to work Industry (current) Marital and civil partnership status Second address indicator |  | RIJO | COMPLETED | MEDIUM |  | 172 hrs | 2024-05-07
930 | 2024-05-07 | ISSUE | Report | some of the on market comparable shown are more than 1 mile https://tinyurl.com/27t6c7bg https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_10224_070520240356368316.pdf 34, Clarendon Road, Croydon, London, CR0 3SG |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-05-07 | 2024-05-07 |  |  | No926_927_comparables_issues_07_05_2024_Sharan_N_P
931 | 2024-05-13 | TASK | Live campaign | add loader for probate property edit address pop up and confirm and send click on edit address pop up please check and update in all campaigns and detail pages | Web | SANDEEP | IN PROGRESS | MEDIUM |  | 4 hrs |  |  |  | updated Sep 10: * when sending 100+ letters, the loader is not shown when we click on the bulk mail or local print buttons --------------------- updated Oct 30: - probate - loader is not shown for local print (it's there for bulk mail) - probate bulk mail - after clicking on confirm and send button, the loader is not shown (check 2nd instruction) -------------- related to 883
932 | 2024-05-13 | ISSUE | Report | in the pop up please change to Additional Property Comparables |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-06-11 | 2024-06-11 | 2024-06-13 | Other Property Type Comparables => Additional Property Comparables | no932-change-text-in-report-sandeep-11jun2024
933 | 2024-05-15 | TASK | Report | comparables price cutoff logic - same as propmarker |  | RIJO | COMPLETED | MEDIUM
934 | 2024-05-15 | ISSUE | Properties | the listed date is not correct 10, Wick Point Mews, Christchurch, Dorset, BH23 1NZ - property was listed on 10 May 2024, 12, Smugglers Wood Road, Christchurch, Dorset, BH23 4PL - Added on 15/03/2024 759, Fulham Road, London, , SW6 5UU - 14 October 2020 First listed but we are showing 28 Jun 2021 |  |  | CLOSED
935 | 2024-05-15 | ISSUE | Properties | property is stc but the rightmove listing is not updated 26 Pipers Drive, Christchurch, BH23 4TR 67, Smugglers Lane North, Christchurch, Dorset, BH23 4NH |  | VIPIN | COMPLETED | MEDIUM
936 | 2024-05-16 | ISSUE | Properties | we are showing withdrawn but it's still on market 9, Wych Elm Road, Oadby, Leicester, Leicestershire LE2 4EF - https://prospectingtool.letsbidproperty.co.uk/properties/p-83303 22, Wheatsheaf Court, Leicester LE2 6ET - https://prospectingtool.letsbidproperty.co.uk/properties/p-56283 |  |  | COMPLETED | MEDIUM
937 | 2024-05-16 | ISSUE | Properties | property images and floorplan are missing 16, Blackthorn Close, Newton, Preston, Lancashire PR4 3TU |  | RIJO | CLOSED | MEDIUM
938 | 2024-05-20 | TASK | Report Revamp | on market comparables - add a section for on market, stc and under offer properties in report |  | SHARAN | COMPLETED | MEDIUM
939 | 2024-05-20 | DISCUSS | Properties | for some properties, the floorplan is given as a link to the estate agent website so on our platform we are showing it as a broken image 11, Claremont Road, London, Waltham Forest, London, E17 5RJ - https://www.rightmove.co.uk/properties/144056297#/floorplan?activePlan=2&channel=RES_BUY |  | UNASSIGNED | CLOSED | LOW
940 | 2024-05-20 | ISSUE | Properties | zoopla activity not updated 164, Kenrick Road, Nottingham, Gedling, Nottinghamshire, NG3 6EX |  |  | COMPLETED
941 | 2024-05-20 | ISSUE | Properties | the listing activity is not correct, the price has been reduced but in the activity the price shown is not correct. The price shown for the latest activity is given as £0 and the first listed price is the same as current price https://tinyurl.com/27dztwh4 mainly for Zoopla properties 22 Wigton Road, London, E17 5HU 119 Orchard Croft, Harlow, CM20 3BD 234 Porchester Road, Nottingham, NG3 6HE 34 Churchill Road, Kidlington, OX5 1BN Shenley House, 2A Churchill Road, Kidlington, OX5 1BN 6 Lynden Close, Holyport, Maidenhead, SL6 2LB Apartment 20, Fusion 5, 10 Middlewood Street, Salford, M5 4LN 15A Rawlins Street, Liverpool, L7 0JE 68 Royston Street, Liverpool, L7 1PZ 68 Crown Station Place, Crown Street, Liverpool, L7 3LB 11, Westfield Drive, Warton, Preston, Fylde, Lancashire, PR4 1ED - https://www.prospectingtool.letsbidproperty.co.uk/properties/b-2834206 27 Sydney Road, London, N10 2LR - https://www.prospectingtool.letsbidproperty.co.uk/properties/d-2890904 10 Maria Terrace, London, E1 4NE ----- Nov 29 16 Sycamore Avenue, Hatfield, AL10 8LZ - https://www.prospectingtool.letsbidproperty.co.uk/properties/d-3258787 ( | Web | SANDEEP | NOT STARTED | HIGH | [5 empty] | not getting this issue for newly added properties but it's there for older listings
942 | 2024-05-20 | ISSUE | Properties | same properties are listed in both sections of week CM17 |  | RIJO | COMPLETED | HIGH
943 | 2024-05-21 | UK TEAM |  | on market probate (refer propmarker) highlight a probate property that is on the market | Web | ANISHA | TESTING | MEDIUM |  | 1 week | 2024-12-20 | 2024-12-23 | 2024-12-24 | Updated Dec 23: - change the title to On Market Probate listing - remove (without filters) from the title - bed, property type, price filters applied is removed when we go into the detail page and return to the listing page - hide the info icon beside the title for now - only on market properties need to be shown in the listing, if the property is sold stc/under offer/withdrawn no need to include it in On market probate listing | no943onmarket_probate_Anisha_17dec2024
944 | 2024-05-21 | TASK |  | sold comparables - images for sold properties (speak to Rahul) |  | SHARAN | COMPLETED | MEDIUM
945 | 2024-05-21 | TASK | Comparable Tool | for on market and rental comparables please show the Rightmove and Zoopla links |  | SHARAN | COMPLETED | MEDIUM
946 | 2024-05-21 | ISSUE | Comparable Tool | miles for on market comparables are not correct |  | SHARAN | COMPLETED | MEDIUM
947 | 2024-05-21 | ISSUE | Comparable Tool | tenure for on market comparable is Not available for all address (it's given in Propmarker) EN1 1HT ¦ Terraced ¦ 3 |  | SHARAN | COMPLETED | MEDIUM
948 | 2024-05-21 | ISSUE | DMA Campaign | letters are getting missed when we do local print - side panel api issue |  | RIJO | COMPLETED | HIGH |  | 2 days | 2024-05-22 | 2024-05-23 | 2024-05-24
949 | 2024-05-21 | ISSUE | Comparable Tool | Please also change the wording to comparable Tool remove the S |  | SHARAN | COMPLETED | MEDIUM
950 | 2024-05-21 | ISSUE | Comparable Tool | the back button doesn’t work rijo when you click an on market property and go back |  | SHARAN | COMPLETED | MEDIUM
951 | 2024-05-21 | ISSUE | Comparable Tool | the heading should say comparable generation tool not comparison |  | SHARAN | COMPLETED | MEDIUM
952 | 2024-05-22 | TASK | Properties | new listing cron - if the property is withdrawn for 3 months or more and then gets relisted, it should be shown as a new listing even if the same agent lists |  | SANDEEP | CLOSED | HIGH |  | 4 days | 2024-05-24
953 | 2024-05-24 | TASK |  | Re-arrange Letsbid menu to : Dashboard Property Report Comparable Tool Outcodes Properties Withdrawn Back to Market Price Drop Sold/Under-Offer Targeted Direct Mail Anywhere Probate New Homes Active Buyers Anniversary Letters Live Campaign Campaign History Letter Management Summary Settings |  | RIJO | COMPLETED | MEDIUM |  | 2 days | 2024-05-24 | 2024-05-27 | 2024-05-27
954 | 2024-05-24 | ISSUE | Back to Market | back to market cron - if property becomes withdrawn and for sale within 1 week, remove the property from back to market |  | SANDEEP | COMPLETED | MEDIUM
955 | 2024-05-27 | ISSUE | Detail Page | quick send preview in detail page - in front of the preview displayed another pop up is shown |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-05-27
956 | 2024-05-27 | ISSUE | Planning Campaign | if the agent address is in a single line or postcode is not available, only if we click in the edit box the warning message is shown (works for property address) |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | No need of validation for agent address
957 | 2024-05-27 | ISSUE | Active Buyer Campaign | bulk mail and local print in active buyer campaign does not work |  | SANDEEP | COMPLETED | HIGH |  | 4 hrs | 2024-05-28 | 2024-05-28 | 2024-05-30 |  | no957-active-buyer-campaign-issue-sandeep-28may2024
958 | 2024-05-27 | ISSUE | Active Buyer | in the detail page of an address, under 'Other properties owned by the company' when we click on some address it shows server error issue is mostly with flat/apartment addresses TA1 - MCCARTHY & STONE RENTAL PROPERTIES NO. 3 LIMITED > 12, Kingfisher Court, South Street, Taunton, TA1 3GH > Flat 7, The Boathouse, 100 Riverdene Place, Southampton, SO18 1ER LE17 - PLATFORM HOUSING LIMITED > 1 Fernie Court, Husbands Bosworth, Lutterworth, LE17 6LW > |  | SANDEEP | COMPLETED | MEDIUM
959 | 2024-05-27 | ISSUE | Active Buyer | shows server error when we click on View Detail button for some addresses issue is mostly with flat/apartment addresses SL6 - OAK PROPERTY REDEVELOPMENTS LIMITED > Flat 1, 26a King Street, Maidenhead, SL6 1EF SW11 - A2DOMINION HOMES LIMITED > Flat 6, 21 Plough Road, London, SW11 2DE Apartment 1, The Saddler Building, 24 Wharf Road, London, N1 7GQ AL RAYAN BANK PLC > Apartment 22, Fitzroy House, 6 Palmer Road, London, SW11 4GG DORRINGTON LONDON FLATS LIMITED > Flat 325, The Circle, Queen Elizabeth Street, London, SE1 2JU N21 - ETON HOUSE INVESTMENTS LIMITED > Flat 1, Eton House, 53a Station Road, London, N21 3NB |  | SANDEEP | COMPLETED | MEDIUM
960 | 2024-05-27 | SUGGESTION | Campaign History | campaign history detail page - can the Redo button be changed from the small circle to Redo Campaign so user knows what it's for show a tool tip/title attribute on hover for all action buttons |  | SANDEEP | COMPLETED | LOW |  |  | 2024-07-18 | 2024-07-18 | 2024-07-18 | updated Jul 12: * shows an error page when we click on view campaign history in active buyer | no960-tooltip-for-redo-campaign-button-sandeep-18jun2024
961 | 2024-05-29 | ISSUE | Report | comparables are not loading before generating report |  | SHARAN | COMPLETED | HIGH |  |  | 2024-05-29 | 2024-05-29 | 2024-06-13 |  | No961_comparable_loading_29_05_2024_Sharan_N_P
962 | 2024-05-30 | ISSUE | Targeted Properties | in the comparables section in the detail page, the selected property is shown as a comparable 15, Church Drive, Lincoln, Lincolnshire, LN6 7AX |  | SHARAN | COMPLETED | MEDIUM
963 | 2024-05-30 | ISSUE | Targeted Properties | when we go into a campaign history of an address and then click on the back button it shows an error page please redirect to targeted listing page https://tinyurl.com/272bqexs please check 20-20 targeted campaign as well |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-05-06 |  | 2024-06-13 |  | no963-targeted-campaign-issue-sandeep-03jun2024
964 | 2024-05-20 | ISSUE | Probate properties | quick send is not working in probate detail page |  | SANDEEP | COMPLETED | URGENT |  | 6 hrs | 2024-05-30 | 2024-05-31 | 2024-06-03 |  | tmp-quicksend-probate-issue-sandeep-30may2024
965 | 2024-05-30 | ISSUE | Report | Error parsing "30/07/2018" as 64-bit integer for MongoDB\BSON\UTCDateTime Address : White Lodge, Poulton-le-Fylde, Lancashire, FY6 8DJ |  | SHARAN | COMPLETED | URGENT |  |  | 2024-05-30 | 2024-05-30 |  |  | No965_Report_planning_date_error_30_05_2024_Sharan_N_P
966 | 2024-05-31 | DISCUSS | Report | the rental comparable is different when we compare with the comparable tool SW11 4EZ ¦ Flat ¦ 3 Flat 22, Prince of Wales Drive, London, SW11 4E |  | SHARAN | COMPLETED | MEDIUM
967 | 2024-06-03 | ISSUE | Dashboard | when we preview the letters it shows a blank page |  | SANDEEP | COMPLETED | URGENT |  |  | 2024-06-03 | 2024-06-04 | 2024-06-05
968 | 2024-06-03 | ISSUE | Dashboard | quick send bulk mail does not work credits are debited but letters are not reaching stannp and also the campaign history is empty |  | SANDEEP | COMPLETED | URGENT |  |  | 2024-06-03 | 2024-06-04 | 2024-06-05
969 | 2024-06-03 | ISSUE | Detail Page | quick send bulk mail does not work if the address is not edited It works only if we edit the address |  | SANDEEP | COMPLETED | URGENT |  |  | 2024-06-03 | 2024-06-04 | 2024-06-05
970 | 2024-06-04 | ISSUE | Active Buyer | active buyer page keeps loading |  |  | CLOSED | HIGH
971 | 2024-06-05 | ISSUE | Report | when generating reports for on market addresses, the status is show as Off Market Property $data['property_portal_data']['portal_property_title'] |  | SHARAN | COMPLETED | HIGH |  | 3 hrs | 2024-06-05 | 2024-06-05 | 2024-06-06 |  | No875_Report_option_to_edit_address_23_05_2024_Sharan_N_P
972 | 2024-06-05 | ISSUE | Comparable Tool | on market comparables - please show the comparables nearest to searched postcode |  | SHARAN | COMPLETED | MEDIUM
973 | 2024-06-05 | ISSUE | Comparable Tool | sold comparable - properties without sqft are excluded |  | SHARAN | COMPLETED | HIGH
974 | 2024-06-06 | ISSUE | Properties | the latest activity is given as Withdrawn but the property is still on sale 9, Wych Elm Road, Oadby, Leicester, Leicestershire LE2 4EF - https://prospectingtool.letsbidproperty.co.uk/properties/p-83303 |  | UNASSIGNED | COMPLETED | MEDIUM
975 | 2024-06-06 | ISSUE | Report | when we try to generate report from the detail page, if we edit the address even if it's off market it's shown as On market and also shows the image, floor plans of the address which is on market please reduce the button size for confirm address and regenerate report 74, Glenwood Close, Coychurch, Bridgend, CF35 5EU edited address - 89, Glenwood Close, Coychurch, Bridgend, CF35 5EU |  | SHARAN | COMPLETED | HIGH |  | 3 hrs | 2024-06-06 | 2024-06-06 | 2024-06-13 |  | No975_Report_modifed_address_status_error_Sharan_N_P_06_06_2024
976 | 2024-06-06 | ISSUE | Report | in the comparables if the sqft is 0 make it - 94, Wellington Road North, Hounslow, Greater London, TW4 7AA 44, Sandringham Road, Watford, Hertfordshire, WD24 7BB |  | SANDEEP | CLOSED | MEDIUM
977 | 2024-06-06 | ISSUE | Properties | property is on market but we are showing as withdrawn 103, Kelsterton Road, Connahs Quay, Deeside, Flintshire, CH5 4BL |  | DATA TEAM | DUPLICATE TASK | MEDIUM
978 | 2024-06-07 | ISSUE | Report | Report other type comparables fetching issue eg: 124, Arnold Street, Bolton, Lancashire, BL1 3EY https://www.prospectingtool.letsbidproperty.co.uk/log-viewer?file=a4937178-laravel-2024-06-06.log&query=log-index%3A10065 |  | SHARAN | COMPLETED | HIGH |  | 1hr | 2024-06-07 | 2024-06-07 | 2024-06-13 |  | No978_Report_other_type_comparables_index_error_Sharan_N_P_07_06_2024
979 | 2024-06-07 | ISSUE | Report | property has planning application but it's not shown in the report 11, Rickard Close, London, NW4 4XH 44 Holders Hill Avenue, London, NW4 1ET |  | SHARAN | CLOSED | MEDIUM
980 | 2024-06-07 | ISSUE | Report | on market comparables - the miles are not correct when we compare it to the comparable tool |  | SHARAN | COMPLETED | MEDIUM
981 | 2024-06-10 | ISSUE | Report | on market comparables - the miles are not correct when we compare it to the comparable tool |  | SHARAN | COMPLETED | MEDIUM
982 | 2024-06-10 | ISSUE | Comparable Tool | the bedroom count is not available for sold comparable but we are showing ST4 7LU ¦ semi detached ¦ 5 |  | SHARAN | COMPLETED | MEDIUM
983 | 2024-06-10 | ISSUE | Comparable Tool | on market comparables are missing TN31 6NP ¦ semi detached ¦ 3 |  | SHARAN | COMPLETED | MEDIUM
984 | 2024-06-11 | ISSUE | Probate properties | property has sale history but it's not shown 83 Moyser Road, London, SW16 6SG |  | SANDEEP | COMPLETED | MEDIUM
985 | 2024-06-11 | ISSUE | Comparable Tool | on market comparable fetching switch to mongo db |  | SHARAN | COMPLETED | URGENT |  | 7hrs | 2024-06-11 | 2024-06-11
986 | 2024-06-12 | ISSUE | Comparable Tool | on market comparable - shows server error page when we click on addresses |  | SHARAN | COMPLETED | HIGH
987 | 2024-06-13 | ISSUE | Active Buyer | property is listed under a company but when we go into the property detail page it's shows "Company details not found." issue seen mostly with flat/apartment addresses SW16 DORIEN ROAD 2 LTD Flat D, 219 Streatham High Road, London, SW16 6EN Flat B, 219 Streatham High Road, London, SW16 6EN NW4 TBG OPEN DOOR LIMITED Flat 7, Rockfield House, Belle Vue Estate, London And Store, NW4 2BH MANI ESTATES LTD Flat 4, Fernside Court, Holders Hill Road, London, NW4 1JT DN14 SETH PROPERTY SERVICES LTD Flat 3, 20 Oxford Grove, Ilfracombe, EX34 9HQ SUBWAY REALTY LIMITED Unit 6, Ladybarn House, 2 Moseley Road, Fallowfield, Manchester, M14 6ND |  | SANDEEP | COMPLETED | MEDIUM |  |  |  |  | 2024-09-12 |  | no987-active-buyer-company-details-issue-sandeep-17jun2024
988 | 2024-06-14 | ISSUE | Comparable Tool | for on market comparables please make sure that the listing date is in the last 1 year ST4 7LU ¦ semi deteached ¦ 5 SS11 7FG ¦ detached ¦ 4 |  | SHARAN | COMPLETED | HIGH
989 | 2024-06-14 | ISSUE | Properties | property images are missing 102 Spencer Street, Norwich, NR3 4PE |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | propery is withdrawn
990 | 2024-06-14 | ISSUE |  | property images and floor plan missing |  | UNASSIGNED | CLOSED | MEDIUM
991 | 2024-06-14 | TASK | Report | filter and sorting for comparable https://docs.google.com/document/d/1ZhIHqOwnd8RywF_Fqie70ReKscZfwiWajDuhYjG0mxA/edit?usp=sharing |  | SHARAN | COMPLETED | HIGH |  |  |  |  | 2024-07-16
992 | 2024-06-14 | TASK | Comparable Tool | filter and sorting for comparable https://docs.google.com/document/d/1ZhIHqOwnd8RywF_Fqie70ReKscZfwiWajDuhYjG0mxA/edit?usp=sharing |  | SHARAN | COMPLETED | HIGH |  |  | 2024-06-17 |  | 2024-07-16
993 | 2024-06-17 | ISSUE | Report | additional property comparables - if comparables are not avaialbale for any of the property types, please make sure it's not shown https://tinyurl.com/2c6ar22t |  | SHARAN | COMPLETED | MEDIUM
994 | 2024-06-19 | ISSUE | Comparable Tool | on market comparable - the comparable changes each time we go into a detail page and return to the comparable tool page or when we generate comparable for the same postcode, property type and bed count |  | SHARAN | COMPLETED | MEDIUM
995 | 2024-06-27 | ISSUE | Summary | design issue - the line overlaps the count under QR Codes scanned, QR Forms Completed, Instructions Received https://tinyurl.com/2g4q5a4n |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-13 | 2024-12-13 | 2024-12-17 |  | No995_Summary_desing_issue_Sharan_N_P_13_12_2024
996 | 2024-07-02 | ISSUE | Report | in market analysis page the sales volume data is not correct |  | RIJO | COMPLETED | MEDIUM
997 | 2024-07-02 | DISCUSS | Report | iamproperty.com report generation ui - preview of comparable page and generation section https://iamproperty.com/why-iamproperty/marketing-toolkit/property-reports/?_gl=1*hdgd4d*_up*MQ..*_ga*MjAwNTkyNjE3MS4xNzMyODg1ODE2*_ga_RMPZN23ZSH*MTczMjg4NTgxNS4xLjEuMTczMjg4NTg3Ni4wLjAuMA.. | UI | RIJO | DISCUSS | MEDIUM
998 | 2024-07-12 | TASK | Detail Page | wrong event cleaning for withdrawn |  | DATA TEAM | CLOSED | MEDIUM
999 | 2024-07-12 | TASK | Detail Page | logic change for fallen through in detail page |  | SANDEEP | COMPLETED | MEDIUM
1000 | 2024-07-15 | ISSUE | Title Plan/Register | Title purchase payment errors |  | SHARAN | COMPLETED | HIGH |  |  | 2024-07-15 | 2024-07-15 |  |  | No1000_title_purchase_payment_error_Sharan_N_P_15_07_2024
1001 | 2024-07-15 | ISSUE | Withdrawn | to check the withdrawn issue 3, Carter Street, Howden, Goole, East Riding Of Yorkshire, DN14 7GP 35, Westfield Avenue, Goole, East Riding Of Yorkshire, DN14 6JY Ivy House, Asselby, Goole, East Riding Of Yorkshire, DN14 7HB |  | RISHIKA | COMPLETED | HIGH
1002 | 2024-07-15 | ISSUE | Report | the address we are generating report for is shown as the sold comparable 26, Almond Tree Avenue, Goole, Yorkshire, DN14 9QQ |  |  | CLOSED
1003 | 2024-07-16 | ISSUE | Report | property type is available but it's not shown in the sold comparable pop up 52b, Edge Grove, Liverpool, Merseyside, L7 0HW |  |  | COMPLETED | MEDIUM
1004 | 2024-07-16 | ISSUE | Live campaign | showing server error when we do bulk mail |  | RIJO | COMPLETED | URGENT |  |  | 2024-07-16 | 2024-07-16 | 2024-07-16
1005 | 2024-07-16 | ISSUE | Report | if property type is not selected, it shows blank in additional comparable pop up 13, The Greenway, Potters Bar, Hertfordshire, EN6 2NB https://tinyurl.com/23v537wj |  | SHARAN | COMPLETED | LOW |  | 3 hrs | 2024-12-16 | 2024-12-16 | 2024-12-24 | updated Dec 18: - no warning message is shown like the rest updated Dec 23: - try now | No1005_Report_additional_comps_type_Sharan_N_P_16_12_2024
1006 | 2024-07-16 | ISSUE | Report | if we go into the detail page of an on market property and click on the back button, the user is redirected to the comparable page open the detail page in a new tab or return to the generation page (user shouldn't have to search the address again) |  | SHARAN | COMPLETED | MEDIUM |  |  |  | 2024-08-07
1007 | 2024-07-16 | ISSUE | Comparable Tool | sold comparable - sort by miles is not correct |  | SHARAN | COMPLETED | MEDIUM
1008 | 2024-07-16 | ISSUE | Comparable Tool | when we go into the property detail page of an on market property and click on the back button, all the filters selected and input given by the user is cleared and they will have to select it again |  | SHARAN | COMPLETED | LOW | [5 empty] | detail page opens in a new tab
1009 | 2024-07-16 | ISSUE | Comparable Tool | the alignment of the first row changes when we filter |  | SHARAN | COMPLETED | MEDIUM
1010 | 2024-07-16 | ISSUE | Report | the alignment of the first row changes in the comparable pop ups when we filter |  | SHARAN | COMPLETED | MEDIUM
1011 | 2024-07-17 | TASK | Detail Page | Off market Details for the following detail pages : ----------------------------------------------------- Probate Targeted Active Buyers display comparables in the detail page Data to be filled : --------------------- 1. Property images 2. Floor Plan Images 3. Property Type 4. Bedroom & Bathroom | Web | SANDEEP | IN PROGRESS | MEDIUM |  |  | 2024-07-25 | 2024-08-09 |  | New Homes (Planning) - need to confirm if detail page is required for planning --------------------------------- updated Aug 20: few issues added to the sheet with task type as Demo will resume this task after the new listing issue ----------------------------------- https://docs.google.com/spreadsheets/d/1AaCOrdvitkt4d-WI8p5NGNPSGnfMefASBvZgkHXOd80/edit?gid=51567162#gid=51567162&range=1135:1141 https://docs.google.com/spreadsheets/d/1AaCOrdvitkt4d-WI8p5NGNPSGnfMefASBvZgkHXOd80/edit?gid=51567162#gid=51567162&range=1143:1143 https://docs.google.com/spreadsheets/d/1AaCOrdvitkt4d-WI8p5NGNPSGnfMefASBvZgkHXOd80/edit?gid=51567162#gid=51567162&range=1163:1163
1012 | 2024-07-17 | ISSUE | Campaign History | shows server error when we view active buyer campaigns |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-07-17 | 2024-07-18 | 2024-07-18 |  | no960-tooltip-for-redo-campaign-button-sandeep-18jun2024
1013 | 2024-07-17 | ISSUE | Report | market analysis - Average Area Price/Sqft is not shown even if we have sold comparables |  | SHARAN | COMPLETED | MEDIUM
1014 | 2024-07-17 | SUGGESTION | Planning Application | Council has data but it's not active, it's still greyed out Bournemouth Christchurch And Poole Westminister Wakefield Stoke-on-Trent Southwark Shropshire Great Cambridge East Riding Of Yorkshire Doncaster Cheshire West And Chester Chelmsford Bexley | Data | DATA TEAM | NOT STARTED | MEDIUM | [5 empty] | will enable it only when it's fully completed @Vishnu - get updated sheet
1015 | 2024-07-17 | ISSUE | Comparable Tool | when exporting the comparables, only the first page is exported |  | SANDEEP | DUPLICATE TASK | MEDIUM
1016 | 2024-07-17 | ISSUE | Report | customize report takes time to load |  | SHARAN | COMPLETED | MEDIUM
1017 | 2024-07-17 | ISSUE | Report | property type is available, but when the user gives input for bed and continues in the comparable pop up the property type is not selected |  | SHARAN | COMPLETED | HIGH
1018 | 2024-07-17 | DISCUSS |  | do we need to increase the bed count from 5+? if the bed count of the property is 6, when generating the report the bed count is blank 37, Irvine Street, Liverpool, Merseyside, L7 8SY - https://www.prospectingtool.letsbidproperty.co.uk/properties/w-1912085 |  | RIJO | CLOSED | MEDIUM | [5 empty] | rightmove shows upto 5
1019 | 2024-07-18 | ISSUE | Report | Planning date error "Not yet determined" |  | SHARAN | COMPLETED | HIGH |  |  | 2024-07-18 | 2024-07-18 | 2024-07-18 |  | No1019_Report_planning_date_error_18_07_2024_Sharan_N_P
1020 | 2024-07-22 | ISSUE | Report | property type is available, but when the user gives input for bed and continues in the comparable pop up the property type is not selected (only if they input the type in the custom value section it is automatically shown) |  | SHARAN | COMPLETED | MEDIUM
1021 | 2024-07-22 | SUGGESTION | Detail Page | make comparables section collapsible |  | RIJO | CLOSED | LOW
1022 | 2024-07-23 | ISSUE | Withdrawn | property is still on market but we have marked it as withdrawn the rightmove listing does not have any sold history but on letsbid it's given 137, Auckland Road, Potters Bar, Hertsmere, Hertfordshire, EN6 3HF |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-09-23 |  |  | The property was already withdrawn, and reposted as "New Home" so which will ignore our system.
1023 | 2024-07-24 | ISSUE | Comparable Tool | bedroom count - given as property type, please change to Bedroom |  | SHARAN | COMPLETED | MEDIUM
1024 | 2024-07-25 | DISCUSS | Report | comparable pop up - when user selects addresses and then filters, the selected address should remain |  | SHARAN | COMPLETED | LOW
1025 | 2024-07-25 | DISCUSS | Report | comparable pop up - when we select addresses and close the pop up, then click on it again the selected addresses are cleared |  | SHARAN | COMPLETED | LOW
1026 | 2024-07-25 |  | Report | to check report download 64, Camborne Road, Morden, Surrey, SM4 4JJ |  |  | CLOSED
1027 | 2024-07-25 | ISSUE | Report | Additonal comparable page price/sqft format issue |  | SHARAN | TEST STAGING | HIGH | [6 empty] | No1027_Report_additional_comps_price_sqft_format_issue_Sharan_N_P_25_07_2024
1028 | 2024-07-25 | TASK | Report | Report generation page changes |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-07-25 |  |  |  | No1028_Report_generation_page_align_changes_Sharan_N_P_25_07_2024
1029 | 2024-07-25 | ISSUE | Report | on market comparable - open the links in a new tab |  | SHARAN | COMPLETED | LOW |  |  |  | 2024-08-07
1030 | 2024-07-25 | TASK | Report | the selected comparables shouldn't be cleared when users filter it or move to the next page. Letsbid - Comparable Enhancement |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-09-05 | 2024-09-26 | 2024-09-27 |  | No1030_Report_comparable_cart_Sharan_N_P_05_09_2024
1031 | 2024-07-25 | ISSUE | Report | if we search an address and select it, on clearing the searched keyword the selection also gets cleared |  | SHARAN | COMPLETED | LOW | [5 empty] | discuss with Rishika
1032 | 2024-07-25 | ISSUE | Report | not able to download report 41, Turner Street, London, E1 2AU 64, Camborne Road, Morden, Surrey, SM4 4JJ |  | SHARAN | CLOSED | MEDIUM
1033 | 2024-07-25 | ISSUE | Comparable Tool | remains at the bottom when we click on next or previous button |  | SHARAN | DUPLICATE TASK | LOW
1034 | 2024-07-25 | ISSUE | Report | comparables - remains at the bottom when we click on next or previous button |  | SHARAN | COMPLETED | LOW |  |  |  | 2024-08-07
1035 | 2024-08-01 | ISSUE | General | if we sign in and return to the page after a long time, instead of showing 419 ¦ PAGE EXPIRED can we not show someother page https://tinyurl.com/24gbh7e3 when the user is logged into their account and left idle for sometime, when they try to use their account sometimes it shows a warning pop up or shows the prospecting login page https://tinyurl.com/293uxcyd | Web | ANISHA | IN PROGRESS | MEDIUM |  | 2 hrs |  |  | 2024-12-31 | updated Dec 18: - when we go into New Homes listing, the user is automatically redirected to the session expired page when we select addresses | no1035_page_expiry_edit_Anisha_17dec2024
1036 | 2024-08-01 | ISSUE | Dashboard | preview is not working, it shows something went wrong |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-08-01 | 2024-08-01 | 2024-08-01
1037 | 2024-08-01 | ISSUE | Letter management | Planning text is not visible under Letter Management https://tinyurl.com/29bzfm7q Campaign Letter Management Campaign History |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-05 | 2024-12-05 | 2024-12-10 |  | No1037_campaign_tab_missing_Sharan_N_P_05_12_2024
1038 | 2024-08-01 | ISSUE | DMA Campaign | property has side panel but in the preview only the qr code is shown 56 Muswell Hill, London, N10 3ST | Web | RIJO | NOT STARTED | MEDIUM
1039 | 2024-08-03 | ISSUE | Report | comparable filtering issue |  | SHARAN | COMPLETED | URGENT
1040 | 2024-08-03 | ISSUE | Report | sold in street data is not correct in the report |  | SHARAN | COMPLETED | URGENT
1041 | 2024-08-03 | ISSUE | Withdrawn | the property is Under offer but on the platform it is marked as withdrawn Flat 404, Chalmers House, York Road, London, SW11 3QT - https://prospectingtool.letsbidproperty.co.uk/properties/w-388720 |  | UNASSIGNED | CLOSED | MEDIUM | [5 empty] | to check after posting
1042 | 2024-08-03 | ISSUE | Log Error | Undefined array key "proprietor_name_1" - Jobs/GetCompanyOwnedPropertyJob |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-01 | 2024-08-01 | 2024-08-01 |  | No1042_log_error_in_GetCompanyOwnedPropertyJob_Sharan_N_P_01_08_2024
1043 | 2024-08-03 | ISSUE | Log Error | Undefined property: stdClass::$result Commands/PortalAddressCorrection |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-01 | 2024-08-01 | 2024-08-22 |  | No1043_undefined_property_PortalAddressCorrection_Sharan_N_P_01_08_2024
1044 | 2024-08-03 | ISSUE | Log Error | Attempt to read property "clean_flag" on null PropertyTypeTrait |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-01 | 2024-08-01 | 2024-08-22 |  | No1044_log_error_clean_flag_null_propertytypetrait_Sharan_N_P_01_08_2024
1045 | 2024-08-03 | ISSUE | Log Error | Point data type error in PropertyService |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-01 | 2024-08-01 | 2024-08-22 |  | No1045_log_error_coord_type_propertyservice_Sharan_N_P_01_08_2024
1046 | 2024-08-05 | ISSUE | Log Error | log error |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-05 | 2024-08-05 | 2024-08-05 |  | No1046_log_error_Sharan_N_P_05_08_2024
1047 | 2024-08-05 | ISSUE | Report | reports are taking time to download |  | SHARAN | COMPLETED | HIGH
1048 | 2024-08-05 | SUGGESTION | Report | when the reports are being generated, the message shown is Report generated please change to Report generation is in progress https://tinyurl.com/2cw6u9gr |  | SHARAN | COMPLETED | LOW
1049 | 2024-08-05 | ISSUE | Report | after searching and selecting an address, it takes time to proceed |  | SHARAN | COMPLETED | HIGH |  |  |  | 2024-08-07
1050 | 2024-08-05 | ISSUE | Report | additional comparables - when we reset the filters, not able to select property type the check boxes are cleared |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-15 | 2024-08-15 |  |  | No1050_Report_additional_comparable_reset_Sharan_N_P_15_08_2024
1051 | 2024-08-05 | ISSUE | Probate properties | after clearing the outcodes by clicking on the selected outcodes (the green section), the outcodes are cleared but in the dropdown it shows the outcodes as selected https://tinyurl.com/2djqvnrp |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-08-06 | 2024-08-06 | 2024-09-12 |  | no1051-outcode-click-issue-sandeep-06aug2024
1052 | 2024-08-05 | ISSUE |  | search at the header - when we search with a house number, if that number is in the price it is shown in the results |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-08-06 | 2024-08-06 | 2024-11-07 | when we search, in the listing page the filter design is not correct and also the loader is not shown -------------- hide search feature, will proceed after confirmation | no1052-search-header-in-probate-sandeep-06aug2024 no1052-hide-search-bar-sandeep-06nov2024
1053 | 2024-08-05 | ISSUE |  | please make sure the letter management preview and the preview while sending the campaign is same |  | SANDEEP | DUPLICATE TASK | MEDIUM | [5 empty] | #679
1054 | 2024-08-05 | SUGGESTION | Listing Page | do we need to show the address in a box when we hover over it? |  | SHARAN | COMPLETED | LOW |  | 1hr | 2024-12-17 | 2024-12-17 | 2024-12-19 |  | No1054_Property_listing_hover_box_hide_Sharan_N_P_17_12_2024
1055 | 2024-08-06 | ISSUE | Report | EPC Issues: - epc rating is not correct in the report 223, CHINN BROOK ROAD, BIRMINGHAM, WEST MIDLANDS, B13 0NB - 88, FORBES AVENUE, POTTERS BAR, EN6 5NQ https://www.awesomescreenshot.com/image/51514223?key=73f41dd83d89271ba542124fa7e13dab https://www.awesomescreenshot.com/image/51514246?key=623b6190a6411278caae6af5e69a1b46 |  | SHARAN | DUPLICATE TASK | MEDIUM
1056 | 2024-08-06 | ISSUE | Listing Page | add loader for listing pages Pages : --------- probate normal properties withdrawn price drop sold under offer back to market planning targeted active buyer anniversary letters |  | SANDEEP | COMPLETED | MEDIUM |  | 3 hrs | 2024-08-07 | 2024-08-08 | 2024-08-16 |  | no1057-no-data-found-message-sandeep-07aug2024
1057 | 2024-08-06 | ISSUE | Listing Page | when we select filters, remove "No data found" message Pages : --------- probate normal properties withdrawn price drop sold under offer back to market planning targeted active buyer anniversary letters |  | SANDEEP | COMPLETED | MEDIUM |  | 3 hrs | 2024-08-07 | 2024-08-08 | 2024-08-16 |  | no1057-no-data-found-message-sandeep-07aug2024
1058 | 2024-08-06 | ISSUE | Listing Page | filtered by section - change the color |  | SANDEEP | COMPLETED | MEDIUM |  | 6 hrs | 2024-08-09 | 2024-08-10 | 2024-09-12 |  | no1058-filter-option-change-style-sandeep-09aug2024
1059 | 2024-08-06 | ISSUE | Probate Detail | delay in loading the map in the probate detail page, it loads only after all the data has been displayed | Web | SANDEEP | NOT STARTED | MEDIUM
1060 | 2024-08-06 | ISSUE | Report | EPC error |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-06 | 2024-08-06 |  |  | No1046_log_error_Sharan_N_P_05_08_2024
1061 | 2024-08-06 | TASK | Report | Add property type bungalow in custom values |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-06 | 2024-08-07 | 2024-08-14 |  | No_920_1_rework_Sharan_N_P_06_08_2024
1062 | 2024-08-06 | ISSUE | Listing Page | the postcode dropdown alignment changes when the page reloads Pages : --------- probate normal properties withdrawn price drop sold under offer back to market targeted |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-08-09 | 2024-08-09 |  |  | no1057-no-data-found-message-sandeep-07aug2024
1063 | 2024-08-06 | SUGGESTION | Detail Page | add loader before load map, images, floor plan | Web | SANDEEP | NOT STARTED | MEDIUM
1064 | 2024-08-06 | ISSUE | Planning Application | show more button issue |  | SANDEEP | COMPLETED | MEDIUM |  | 4 hrs | 2024-08-14 | 2024-08-14 | 2024-08-16 |  | no1064-read-more-btn-issue-sandeep-14aug2024
1065 | 2024-08-07 | ISSUE | Report | Remove pdf file from floor plan array if the floorplan is pdf, when we generate report it shows a blank page for floorplan 18, Hill View Gardens, Halifax, West Yorkshire HX3 7BT 23, Travellers Gate, Hartlepool, TS25 5TD 6, Symington Street, Leadhills, Biggar, Lanarkshire ML12 6YE 104 The Woodlands, London, N14 5RX |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-07 | 2024-08-07 | 2024-08-13 |  | No1065_Report_remove_pdf_format_floor_plan_array_Sharan_N_P_07_08_2024
1066 | 2024-08-07 | TASK | Report | Default page selection Buyers reports : about us property images property summary key details carbon footprint / Broadband Sellers reports: about us property summary key details floorplans property images property type analysis |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-07 | 2024-08-07 | 2024-08-13 |  | No1066_Report_default_page_selection_Sharan_N_P_07_08_2024
1067 | 2024-08-07 | ISSUE | Report | epc connection change to mongo db |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-07 | 2024-08-15 | 2024-10-03 | updated Aug 13: the sqft shown is not correct, even if the area is in sqft we are converting it again to sqft | No1067_EPC_data_collection_from_mongo_db_Sharan_N_P_07_08_2024
1068 | 2024-08-07 | ISSUE | Report | Without street name error covered 47, hull yorkshire, HU6 8HF - modify to 22 (check if we are able to generate report) |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-07 | 2024-08-07 | 2024-08-13 |  | No1068_Report_sold_in_street_without_street_name_handle_Sharan_N_P_07_08_2024
1069 | 2024-08-07 | ISSUE | Report | the latest sold history of the property is not shown in the report 116, Trent Gardens, London, Enfield, N14 4QG 21, Orchard Square, Broxbourne, Hertfordshire, EN10 6JA |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-09 | 2024-08-15 | 2024-09-12 | updated Aug 13: property has sold data but not shown in the reportx 63, The Mall, London, N14 6LR | No1069_Sold_history_update_Sharan_N_P_09_08_2024
1070 | 2024-08-08 | TASK | Report | Limit the comparable selection |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-08 | 2024-08-09 |  |  | No1070_Report_limit_comparables_Sharan_N_P_08_08_2024
1071 | 2024-08-08 | ISSUE | Report | Report Generation oops error |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-08 | 2024-08-08 | 2024-08-08 | updated Aug 13: monitoring for few days | No1071_Report_generation_oops_error_Sharan_N_P_08_08_2024
1072 | 2024-08-08 | TASK | Report | already selected properties should remain even if users filter https://docs.google.com/document/d/1lnXeye92-qO-j35tXrPSwm1WDM0qKAsgtIsD_n9--4Y/edit?usp=sharing |  | SHARAN | COMPLETED | MEDIUM
1073 | 2024-08-08 | TASK | Report | if no comparables are selected in the pop up, when they close the pop up the page should be unselected |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-08 | 2024-08-08 | 2024-08-13 |  | No1073_Report_comps_untick_empty_Sharan_N_P_09_08_2024
1074 | 2024-07-17 | TASK | Report | show a pop up if there is an error in case if any of the api's are not working | Web | SHARAN | NOT STARTED | MEDIUM | [5 empty] | - can manually alter the api key in live and test
1075 | 2024-07-17 | ENHANCEMENT | Report | show the comparable images and floor plan of the property in a pop up |  | SHARAN | CLOSED | MEDIUM
1076 | 2024-07-17 | ENHANCEMENT | Comparable Tool | show the comparable images and floor plan of the property in a pop up the user will remain in the comparable tool listing itself and they can view the images and floorplan in the comparable page itself |  | SHARAN | CLOSED | MEDIUM
1077 | 2024-08-05 | ISSUE | Price Drop | zoopla activity not updated 33, The Downs, Harlow, Essex, CM20 3RE 34, Steedman Avenue, Nottingham, Gedling, Nottinghamshire, NG3 6DL 69, Wyebank Road, Tutshill, Chepstow, Forest Of Dean, Gloucestershire, NP16 7FA 2A, Inner Loop Road, Beachley, Chepstow, Forest Of Dean, Gloucestershire, NP16 7HF |  | SANDEEP | COMPLETED | MEDIUM
1078 | 2024-08-08 | SUGGESTION | Report | sorting for all columns seperate button with highlight | UI | SATHEESH | NOT STARTED | LOW
1079 | 2024-08-08 | SUGGESTION | Comparable Tool | sorting for all columns seperate button with highlight | UI | SATHEESH | NOT STARTED | LOW
1080 | 2024-08-08 | SUGGESTION | Report | Selected values must me in bold in comparable filter | UI | SATHEESH | NOT STARTED | LOW
1081 | 2024-08-08 | SUGGESTION | Comparable Tool | Selected values must me in bold in comparable filter | UI | SATHEESH | NOT STARTED | LOW
1082 | 2024-08-08 | SUGGESTION | Report | multiple page check box - comparable |  | UNASSIGNED | COMPLETED | MEDIUM
1083 | 2024-08-08 | TASK | Report | sold on street - the same address is shown, but the format is different mostly in case of flats |  | SHARAN | COMPLETED | MEDIUM | [5 empty] | updated Aug 13: monitoring for few days
1084 | 2024-08-08 | TASK | Report | Front page for off market properties should be our map for standard and agents should have options to use that as standard |  | RIJO | COMPLETED | MEDIUM |  |  |  |  | 2024-08-12
1085 | 2024-08-08 | SUGGESTION | Comparable Tool | Multiple page export when exporting the comparables, only the first page is exported export the comparables in a pdf, exactly as shown in the tool show the property image and the details as it is in the comparable tool | Web | SHARAN | NOT STARTED | MEDIUM
1086 | 2024-08-08 | ISSUE | Comparable Tool | remains at the bottom when we click on next or previous button |  | SHARAN | COMPLETED | MEDIUM
1087 | 2024-08-08 | ISSUE | Report | when we go into the property detail page, remove comparable tool from the url |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-08-15 | 2024-08-15 | 2024-09-12 | still shows comparable tool in the url and also in the breadcrumb | No1087_Comparable_tool_correct_the_link_Sharan_N_P_15_08_2024
1088 | 2024-08-08 | SUGGESTION | Report | population - if the graph is not available, please move the table to the center or to the left https://tinyurl.com/223b92bu 25, HENRIETTA STREET, COVENTRY, WEST MIDLANDS, CV6 5EF |  | SHARAN | COMPLETED | MEDIUM |  | 1hr | 2024-12-17 | 2024-12-17 | 2024-12-19 |  | No1088_Report_population_blank_space_Sharan_N_P_17_12_2024
1089 | 2024-08-08 | ISSUE | Report | property type is available in the detail page, but when generating the report it's given as Not Available 35, Hall Lane, London, NW4 4TJ 1, Hall Lane, London, NW4 4TJ |  | SHARAN | DUPLICATE TASK | HIGH
1090 | 2024-08-08 | ISSUE | Report | market analysis - even if we select only one sold comparable, Avg area price/sqft is shown in the market analysis page |  | SHARAN | COMPLETED | HIGH |  |  | 2024-09-09 | 2024-09-11 | 2024-09-12 | done : please change the minimum comparable needed to calculate avg area price/sqft to greater than or equal to 3 | No1090_Report_market_analysis_avg_area_price_sqft_Sharan_N_P_09_09_2024
1091 | 2024-08-08 | TASK | Report | when the marker for map is enabled, show the marker on the map in the report generation page itself | Web | ANISHA | APPROVAL | LOW | [5 empty] | updated Jan 2: - on clicking next the rest of the pages are not shown - the floor plan is zoomed - generation process is not correct, sections are missing
1092 | 2024-08-08 | ISSUE | Report | sometimes when we generate the report, only the first page and last page is shown once the report is generated |  | SHARAN | COMPLETED | HIGH | [5 empty] | updated Aug 13: monitoring for few days
1093 | 2024-08-08 | ISSUE | Report | EPC - the certificate number goes outside the box 19, Myln Meadow, Ingatestone, Essex, CM4 9NE https://tinyurl.com/2a3btub6 https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14365_021220241318817962.pdf |  | SHARAN | COMPLETED | LOW |  |  | 2024-12-02 | 2024-12-02 | 2024-12-05 |  | No1409_Report_epc_certificate_number_overlaps_box_Sharan_N_P_02_12_2024
1094 |  | TASK | Report | Property Address should be in bold and the property type/bedrooms underneath. Basically the opposite format to what you have got at the minute: |  | SHARAN | COMPLETED | MEDIUM
1095 |  | TASK | Report | Buyers/ Seller's description needs to change to 'About us' so agents know its the page 2 about us section |  | SHARAN | COMPLETED | MEDIUM
1096 |  | TASK | Report | Market analysis - remove outcode because its showing the whole council, not just HG2. Either have the council or just the postcode as it does not read properly at all |  | SHARAN | COMPLETED | MEDIUM
1097 |  | TASK | Report | Primary / Secondary schools - easier to read on old report so need to add lines to make it clearer |  | SHARAN | COMPLETED | MEDIUM
1098 |  | TASK | Report | Carbon footprint and broadband mobile speed need to be separated. Agents don't like including carbon footprint so can it be a seperate box selection to tick on report customisation section so it appears on separate pages |  | SHARAN | COMPLETED | MEDIUM
1099 |  | ISSUE | Report | Sold prices on street - none of them are on the street? They should only be properties sold on the street the report has been generated for |  | SHARAN | COMPLETED | MEDIUM
1100 | 2024-08-08 | TASK | Report | report status should be according to the current property status if the property is withdrawn, it should show Withdrawn stc - STC under offer off market |  | RIJO | CLOSED | MEDIUM | [5 empty] | status not needed on the report
1101 | 2024-08-08 | ISSUE | Report | universities and college - in the title, the icon and heading is not aligned https://tinyurl.com/2yn9d74r |  | SHARAN | COMPLETED | LOW
1102 | 2024-08-08 | ISSUE | Report | additional property comparable - the marker colors on the map and listing are different this happens when we select 8 comparables of the same type |  | SHARAN | COMPLETED | LOW |  | 2hr | 2024-12-18 | 2024-12-18 | 2024-12-19 | Blue - single color | No1102_Report_additional_comparable_marker_color_Sharan_N_P_18_12_2024
1103 | 2024-08-08 | ISSUE | Report | transportation - the address sometimes overlap the marker 47, GLEBE ROAD, HARROGATE, NORTH YORKSHIRE, HG2 0LZ FLAT 4, 2, SOUTH DRIVE, HARROGATE, NORTH YORKSHIRE, HG28AU https://tinyurl.com/2a4luds https://tinyurl.com/2ysldzns " |  | SATHEESH | COMPLETED | LOW
1104 | 2024-08-08 | ISSUE | Report | when generating reports it shows the oops message but the report is shown in the Report History section |  | SHARAN | COMPLETED | HIGH
1105 | 2024-08-12 | TASK | Census 2021 | add census 2021 data |  | SANDEEP | COMPLETED | MEDIUM |  | 2 hrs | 2024-08-12 | 2024-08-12 | 2024-08-16 | updated Aug 13: please add New tag in menu | no1105-add-census2021-data-sandeep-12aug2024
1106 | 2024-08-12 | ISSUE | Comparable Tool | On market details page link error |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-12 | 2024-08-12 | 2024-08-12 |  | No1106_ComparbleTool_onmarket_details_page_link_error_Sharan_N_P_12_08_2024
1107 | 2024-08-12 | ISSUE | Report | Default report color changed as Letsbid blue |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-12 | 2024-08-12 | 2024-08-13 |  | No1107_Report_default_color_change_Sharan_N_P_12_08_2024
1108 |  | ISSUE | Report | issues reported by agents: On market comps not being pulled through sold comprables arent the best either the price estimation should be after the comprables so you can decide what youre going to value it as additional property comps should not be automatically ticked the comprables shouldnt all be ticked either the agents should have to select which comps they are going to include Bungalow and end terrace need to be an option on the property type where it says 'market price' this needs to change to Current Listing Price' there should be 2 pages for on market comps 1 page on market comps still for sale 1 page on market comps SSTC |  |  | CLOSED
1109 | 2024-08-12 | SUGGESTION | Comparable Tool | export the comparables in a pdf, exactly as shown in the tool show the property image and the details as it is in the comparable tool |  | SHARAN | DUPLICATE TASK | MEDIUM |  | 1 week
1110 | 2024-08-12 | DISCUSS | Back to Market | is this the correct back to market logic? Flat, 19A, Oakfield Road, London, Enfield, London, N14 6LT 86 The Mall, London, N14 6LP |  | RIJO | CLOSED | MEDIUM
1111 | 2024-08-12 | ISSUE | Report | the design shown in the first page of the report when no image is available looks stretched |  |  | COMPLETED | HIGH
1112 | 2024-08-12 | ISSUE | Report | API Error handling |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-12 |  | 2024-09-12 |  | No1112_Report_api_error_handling_Sharan_N_P_12_08_2024
1113 | 2024-08-12 | ISSUE | Report | the type shown in the report page and detail page is different 8, Stile Close, Preston, Lancashire, PR4 2SF | Web | SHARAN | NOT STARTED | MEDIUM
1114 | 2024-08-12 | TASK |  | Keytags | Web | UNASSIGNED | DISCUSS | MEDIUM
1115 | 2024-08-12 | TASK |  | Boundary Marked Map View in Letsbid | Web | UNASSIGNED | DISCUSS | MEDIUM
1116 | 2024-08-12 | SUGGESTION | Report | make the content page clickable like in the old report |  | SHARAN | COMPLETED | LOW |  | 3hr | 2024-12-17 | 2024-12-18 | 2024-12-19 | sorted in Propmarker report | No1320_Report_content_page_link_Sharan_N_P_17_12_2024
1117 | 2024-08-13 | ISSUE | Report | remove default selection of tenure |  | RIJO | COMPLETED | MEDIUM | [6 empty] | 1117_tenure_filter_remove_default_selection_Rijo_13Aug2024
1118 | 2024-08-13 | ISSUE | Report | when we change the report theme color to white or any light color, the page titles are still shown in White it doesnt change according to the color selected |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-03 | 2024-12-03 | 2024-12-05 |  | No1118_Report_title_color_issue_Sharan_N_P_03_12_2024
1119 | 2024-08-13 | ISSUE | Report | rental comparable - not much data is shown when the tenure is selected, unselect the tenure |  | RIJO | COMPLETED | HIGH | [6 empty] | 1117_tenure_filter_remove_default_selection_Rijo_13Aug2024
1120 | 2024-08-13 | TASK | Report | Default page selection Buyers reports : about us contents floor plan property images property summary key details carbon footprint / Broadband Sellers reports: about us property summary key details floorplans property images property type analysis historical planning on property historical planning on neighbouring |  | RIJO | COMPLETED | HIGH |  |  | 2024-08-13 | 2024-08-13 | 2024-08-13 |  | No1066_Report_default_page_selection_Sharan_N_P_07_08_2024
1121 | 2024-08-13 | ISSUE | Report | in the front page when the address is in 2 lines, property title text and estimate price is displayed the price gets cropped |  | RIJO | COMPLETED | HIGH |  |  | 2024-08-13 | 2024-08-13 | 2024-08-13 |  | no23_report_improvemrnts_front_page_static_map_edit_Rijo_7Aug24
1122 | 2024-08-14 | ISSUE | Report | if the property type is bungalow, it does not automatically show the type if the type is semi detached bungalow, it shows only bungalow 25, Byng Drive, Potters Bar, Hertsmere, Hertfordshire, EN6 1UP Viking Haven, Balne Croft Lane, Pollington, Goole, DN14 0EY 3 Cheviots, Hatfield, AL10 8JT - https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2328903 | Web | SHARAN | NOT STARTED | MEDIUM
1123 | 2024-08-14 | ISSUE | Report | property image array error, On market check 16, Downs Road, Luton LU1 1QR 6, DOWNS ROAD, LUTON, BEDFORDSHIRE, LU1 1QR 1, Cestrian Street, Deeside, Flintshire, CH5 4EF |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-14 | 2024-08-14 | 2024-08-16 | Check the properties on market or not and connected to mongo db | No1123_Report_images_array_error_Sharan_N_P_14_08_2024
1124 | 2024-08-14 | ISSUE | Report | for some address, the epc page does not look aligned https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_12315_140820241058768739.pdf |  | SATHEESH | COMPLETED | LOW
1125 | 2024-08-14 | ISSUE |  | left menu that is broken during the loading phase but displays correctly afterward | Web | SANDEEP | NOT STARTED | MEDIUM
1126 | 2024-08-15 | TASK | Report | remove the on market status from the report page change title to Property Sales in the area property type analysis - remove "total properties in" text crime rate - remove the postcode |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-08-15 | 2024-08-15 | 2024-08-16 |  | no1126_text_and-display_changes_in_report_Rijo_15aug24
1127 | 2024-08-15 | ISSUE | Report | showing the wrong images for some addresses, happens mostly in case of addresses that have the same building number as flat address |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-14 | 2024-08-14 | 2024-08-16 | Check the properties on market or not and connected to mongo db | No1123_Report_images_array_error_Sharan_N_P_14_08_2024
1128 | 2024-08-15 | ISSUE | Planning Application | when we clear the filter, in the filtered section the council changes back to Adur and in the council dropdown it changes only after the page is refreshed |  | SANDEEP | COMPLETED | LOW |  |  | 2024-10-16 | 2024-10-16 | 2024-11-08 | updated Oct 17: - the keywords selected are not cleared when we click on Clear filters ------------------- updated Oct 30: keywords are not cleared, it still shows the keyword ----------------- updated Nov 6: after clicking on clear filter and then selecting a keyword, the listing is not filtered accroding to the keyword selected | no1128-planning-application-clear-filter-issue-sandeep-16oct2024
1129 | 2024-08-19 | ISSUE | Report | environment data blank https://demo.devidiamober.com/report-preview-new/8740 |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-19 | 2024-08-19 | 2024-09-12 |  | No1129_Report_Environment_data_blank_page_Sharan_N_P_19_08_2024
1130 | 2024-08-16 | ISSUE | Report | Address matching by property details table 16, Downs Road, Luton LU1 1QR |  | SHARAN | COMPLETED | HIGH |  |  | 2024-08-16 | 2024-08-16 | 2024-09-12 |  | No1130_Report_property_details_address_match_Sharan_N_P_16_09_2024
1131 | 2024-08-20 | ISSUE | Listing Page | when we search an address or postcode using the search above the listing, the loader is not shown and also if there is no property found no message is shown |  | SANDEEP | COMPLETED | MEDIUM
1132 | 2024-08-20 | ISSUE | Report | boundary edit - if we zoom in while editing and then continue to generate report, the bounday will get cropped in the report https://tinyurl.com/2docwdjj |  | RIJO | COMPLETED | LOW
1133 | 2024-08-20 | TASK | Properties | If a property is withdrawn, marked as STC, or placed under offer and then comes on the market within 2 months, it will be listed as "Back to Market." However, if the property returns on the market after more than 5 months, it will be considered as a "New Listing." |  | SANDEEP | COMPLETED | HIGH |  | 8 days | 2024-08-21 | 2024-09-02 |  | Monitoring for a few days | no1133-sub-new-listing-date-detail-page-sandeep-29aug2024
1134 | 2024-08-20 | TASK | Back to Market | change the title to Back to Market/Fall Through |  | RIJO | COMPLETED | HIGH
1135 | 2024-08-20 | DEMO | Probate Detail | separate the property details from the Details of the deceased section | UI | SATHEESH | NOT STARTED | MEDIUM
1136 | 2024-08-20 | DEMO | Probate Detail | when images, floorplan and map are available for a property, there is a white space after the comment section | UI | SATHEESH | NOT STARTED | MEDIUM
1137 | 2024-08-20 | DEMO | Probate Detail | property type is blank 2 Ellenbrook Crescent, Hatfield, AL10 9RP | Web | SANDEEP | NOT STARTED | MEDIUM
1138 | 2024-08-20 | DEMO | Targeted Properties | images, bed count is available but it's not shown in the detail page 4, Bennett Close, Hounslow, TW4 5AE | Web | SHARAN | NOT STARTED | MEDIUM
1139 | 2024-08-20 | DEMO | Targeted Properties | please make sure the floor plan is also the same width as the rest | Web | SHARAN | NOT STARTED | LOW
1140 | 2024-08-20 | DEMO | Targeted Properties | when images, floorplan and map are available for a property, there is a white space after the comment section https://tinyurl.com/2a3dxpju | Web | SHARAN | NOT STARTED | MEDIUM
1141 | 2024-08-20 | DEMO | Targeted Properties | can we move the Generate Report button to the top, next to 20-20 campaign |  | SHARAN | TEST DEMO | MEDIUM |  | 1hr | 2024-12-17 | 2024-12-17 |  |  | No1141_Targeted_properties_report_button_Sharan_N_P_17_12_2024
1142 | 2024-08-20 | ISSUE | Targeted Properties | campaign history is not shown in the detail page |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-08-20 | 2024-08-21
1143 | 2024-08-20 | DEMO | Targeted Properties | even if images and floor plan is available, it is not shown in the report | Web | SANDEEP | NOT STARTED | MEDIUM
1144 | 2024-08-21 | ENHANCEMENT | Live campaign | increase the letter sending limit | Web | UNASSIGNED | NOT STARTED | MEDIUM | [5 empty] | getaddress limitation
1145 | 2024-08-21 | ENHANCEMENT | Detail Page | design for detail page to display extra info | UI | SATHEESH | DISCUSS | MEDIUM
1146 | 2024-08-21 | ENHANCEMENT | Report | extra page for report to display extra info | UI | SATHEESH | DISCUSS | MEDIUM
1147 | 2024-08-21 | ENHANCEMENT | Letter management | AI generated content | Web | UNASSIGNED | DISCUSS | MEDIUM
1148 | 2024-08-22 | SUGGESTION | Live campaign | when we are sending lots of letter, show a loader after clicking on local print and bulk mail | Web | SANDEEP | IN PROGRESS | LOW | [5 empty] | updated Oct 17: - probate - loader is not shown for local print (it's there for bulk mail) - probate bulk mail - after clicking on confirm and send button, the loader is not shown (check 2nd instruction) ------------ related to 883
1149 | 2024-08-23 | SUGGESTION | Report | report optimisation - reduce size of the pdf This PDF document probably uses a compression technique which is not supported by the free parser shipped with FPDI. (See https://www.setasign.com/fpdi-pdf-parser for more details) {"userId":640,"exception":"[object] (setasign\\Fpdi\\PdfParser\\CrossReference\\CrossReferenceException(code: 267): This PDF document probably uses a compression technique which is not supported by the free parser shipped with FPDI. (See https://www.setasign.com/fpdi-pdf-parser for more details) at /var/www/html/letsbid/vendor/setasign/fpdi/src/PdfParser/CrossReference/CrossReference.php:257) https://www.prospectingtool.letsbidproperty.co.uk/log-viewer?file=19330130-laravel-2024-08-23.log&query=log-index%3A6849 we are using a free version of fdpi and not all versions that agent uploads work with our free version plugin | Web | RIJO | NOT STARTED | LOW
1150 | 2024-08-27 | ISSUE | Quick Send | detail page - when we try quick send bulk mail for some addresses it just creates a blank campaign, but credits are deducted from the wallet 31, Constable Avenue, Lincoln, Lincolnshire, LN6 7JH |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-08-28 | 2024-08-28
1151 | 2024-08-27 | ISSUE | Report | modify address - when we try to generate report from the detail page, if we edit the address even if it's off market it's shown as On market and also shows the image, floor plans of the address which is on market |  | SHARAN | COMPLETED | HIGH
1152 | 2024-09-02 | UK TEAM | Summary | instruction received count | Web | SHARAN | NOT STARTED | HIGH |  | 1 week
1153 | 2024-09-03 | SUGGESTION | Report | the epc certificate number in the report and epc page is different ----- we are showing the lm key now, instead of that can we move the valid until date to the next line so the design looks aligned |  | SHARAN | COMPLETED | MEDIUM |  | 2 hr | 2024-12-17 | 2024-12-17 | 2024-12-19 | 17_12_2024 : Sharan remove the lmkey from epc page and valid until date is in the next line | No1153_Report_EPC_lmkey_Sharan_N_P_17_12_2024
1154 | 2024-09-04 | ISSUE | Detail Page | the bedroom count and bathroom count for some properties have interchanged https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2257119 5 Northaw Place, Coopers Lane, Northaw, Potters Bar, EN6 4NQ - https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3015384 |  | DATA TEAM | COMPLETED | URGENT
1155 | 2024-09-04 | ISSUE | Detail Page | the zoopla link is not correct, it's missing the / in between |  | DATA TEAM | COMPLETED | URGENT
1156 | 2024-09-04 | ISSUE | Live campaign | probate, DMA, 20-20 - letters are duplicating on reaching stannp |  | RIJO | COMPLETED | URGENT |  |  |  |  | 2024-09-10 |  | no1156_duplicate_property_stannp_fix_rijo_04_09_2024
1157 | 2024-09-04 | ISSUE | Back to Market | properties that are not still on the market is marked as withdrawn 17 Wood Vale, Hatfield, AL10 8TT - https://www.prospectingtool.letsbidproperty.co.uk/properties/b-3001547 |  | SANDEEP | COMPLETED | HIGH | [5 empty] | task no : 1022
1158 | 2024-09-04 | ISSUE | Report | Generation speed |  | SHARAN | COMPLETED | HIGH |  |  | 2024-09-04 | 2024-09-04 |  |  | No1158_Report_fetch_speed_check_Sharan_N_P_04_09_2024
1159 | 2024-09-04 | ISSUE | Detail Page | property is tagged as Company Owned but it's not shown in the detail page 43 Hatton Gardens, Newark, NG24 4BU 2 Clover Drive, Little Canfield, Dunmow, CM6 4AH |  | SANDEEP | DUPLICATE TASK | MEDIUM |  | 3 days
1160 | 2024-09-09 | ISSUE | Detail Page | days on the market in the detail page is not correct 4 Alexandra Road, Beccles, NR34 9UD - https://www.prospectingtool.letsbidproperty.co.uk/properties/p-123788 46, Alexandra Road, Beccles, Suffolk NR34 9UD - https://www.prospectingtool.letsbidproperty.co.uk/properties/p-648151 8, Holme Close, Hatfield, Welwyn Hatfield, Hertfordshire, AL10 9LQ - https://www.prospectingtool.letsbidproperty.co.uk/properties/w-2136849 |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-09-09 | 2024-09-09
1161 | 2024-09-09 | ISSUE | Detail Page | we are showing withdrawn activity for properties that are still on market Tauntons, Marks Hall Lane, White Roding, Dunmow, Uttlesford, Essex, CM6 1RT - https://www.prospectingtool.letsbidproperty.co.uk/properties/b-2729619 |  | SANDEEP | CLOSED | MEDIUM
1162 | 2024-09-09 | ISSUE | Probate Campaign | only the executor addresses are reaching stannp but credits are deducted for both |  | RIJO | COMPLETED | URGENT
1163 | 2024-09-09 | DEMO | Active Buyer | detail page - if property sold history is not available, please don't show that section or show No Data | Web | SANDEEP | NOT STARTED | MEDIUM
1164 | 2024-09-10 | ENHANCEMENT | Dashboard | loading dashboard – load page and then load each Api for faster performance |  | SANDEEP | COMPLETED | HIGH |  |  |  |  | 2024-09-12 |  | LE-dashboard-loading-performance-sandeep-10aug2024
1165 | 2024-09-10 | ENHANCEMENT |  | Property controller Query checks and Optimization | Web | UNASSIGNED | NOT STARTED | MEDIUM
1166 | 2024-09-10 | ENHANCEMENT |  | Unwanted resources and queries | Web | UNASSIGNED | NOT STARTED | MEDIUM
1167 | 2024-09-10 | ENHANCEMENT |  | Coding standard - sublime text editor need to be used with plugin (such as lint, etc.) that will auto identify code issue | Web | UNASSIGNED | NOT STARTED | MEDIUM
1168 | 2024-09-10 | ENHANCEMENT | Summary | Summary page enhancement |  | SANDEEP | COMPLETED | MEDIUM |  |  |  |  | 2024-11-26 |  | LE-summary-page-enhancement-sandeep-09sep2024
1169 | 2024-09-10 | ENHANCEMENT | Live campaign | Pagination in campaign |  | SANDEEP | CLOSED | MEDIUM
1170 | 2024-09-10 | ENHANCEMENT |  | Responsive interface | Web | UNASSIGNED | NOT STARTED | MEDIUM
1171 | 2024-09-10 | ENHANCEMENT | Report | Web view for reports | Web | UNASSIGNED | NOT STARTED | MEDIUM
1172 | 2024-09-10 | TASK |  | GIT for frontend | Web | JISHNU | IN PROGRESS | MEDIUM |  |  | 2024-11-27
1173 | 2024-09-10 | ENHANCEMENT | Live campaign | debit/credit card saving feature | Web | UNASSIGNED | NOT STARTED | MEDIUM
1174 | 2024-09-10 | ENHANCEMENT | Probate properties | Address correction | Web | UNASSIGNED | NOT STARTED | MEDIUM
1175 | 2024-09-10 | ENHANCEMENT | Probate properties | Improve code | Web | UNASSIGNED | NOT STARTED | MEDIUM
1176 | 2024-09-10 | UK TEAM | Report | there should be an option for the user to choose the primary image multiple images of the property will be listed and the agent can select from those |  | SHARAN | COMPLETED | HIGH |  |  | 2024-09-27 |  | 2024-10-10 |  | 1176_Satheesh_report_carosel_edits_Satheesh_01_10_24
1177 | 2024-09-10 | ISSUE | Report | If no data is available for population do we need to show the heading only? 4, Stephen Place, Aberdeen, Aberdeenshire, AB25 3XW 1, Stephen Place, Aberdeen, Aberdeenshire, AB25 3XW |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-09 | 2024-10-09 | 2024-10-10 |  | No1177_report_population_section_empty_Sharan_N_P_09_10_2024
1178 | 2024-09-12 | ISSUE | Properties | In the status drop down button, if "Letter Sent" option is selected, other addresses without status also appears https://tinyurl.com/2y4vfyqu | Web | SANDEEP | NOT STARTED | MEDIUM
1179 | 2024-09-12 | ENHANCEMENT | Report | add the NHS and CQ logos in the last page |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-09 | 2024-10-09 | 2024-10-10 |  | No1179_report_data_providers_added_Sharan_N_P_09_10_2024
1180 | 2024-09-12 | ISSUE | Report | Clicking anywhere on the map page triggers the image upload box for the primary image. |  | SHARAN | COMPLETED | HIGH |  | 1 day | 2024-12-09 | 2024-12-09 | 2024-12-12 |  | No1180_Report_map_click_Sharan_N_P_09_12_2024
1181 | 2024-09-13 | ISSUE | Withdrawn | Some properties listed under the withdrawn option do not have a floor plan available, however, it can be found on Rightmove. 12, Scholars Walk, Hatfield, Welwyn Hatfield, Hertfordshire 19, Veritys, Hatfield, Welwyn Hatfield, Hertfordshire, AL10 8HH | Web | SHARAN | NOT STARTED | MEDIUM |  | 2 days |  |  |  | check data in off market db in mongodb
1182 | 2024-09-17 | ISSUE | Withdrawn | When all the outcodes are selected on the withdrawn page, the page experiences significant loading delays. |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | takes time when there are many outcodes
1183 | 2024-09-23 | TASK | Report | comparables - shorten search radius to quarter and half mile. |  | SHARAN | COMPLETED | HIGH |  | 1hrs | 2024-09-24 | 2024-09-24 | 2024-09-26 |  | No1183_Comparable_distance_options_25_09_2024
1184 | 2024-09-23 | TASK | Comparable Tool | comparables - shorten search radius to quarter and half mile. |  | SHARAN | COMPLETED | HIGH |  | 1hrs | 2024-09-24 | 2024-09-24 | 2024-09-26 |  | No1183_Comparable_distance_options_25_09_2024
1185 | 2024-09-26 | ISSUE | Report | On market properties are shown as off market sometimes Creech House, Whitmore Vale Road, Hindhead, Surrey, GU26 6JA 35, Hall Lane, London, NW4 4TJ 1, Hall Lane, London, NW4 4TJ 49 Shaw Close, Cheshunt, Waltham Cross, EN8 0HD |  | SHARAN | COMPLETED | HIGH |  |  | 2024-09-26 | 2024-09-26 | 2024-10-03 | 1. house number and postcode 2. copy and paste address 3. generate from detail page | No1185_Report_onmarket_matching_26_09_2024_Sharan_N_P
1186 | 2024-09-26 | ISSUE | Listing Page | property is tagged as Company Owned but it's not shown in the detail page 43 Hatton Gardens, Newark, NG24 4BU 2 Clover Drive, Little Canfield, Dunmow, CM6 4AH 114 Guild Close, Birmingham, B16 8DX 3, Stanmore Road, Birmingham, West Midlands, B16 9ST 31 Rotton Park Street, Birmingham, B16 0AE 36 Vernon Road, Birmingham, B16 9SH 7, Lyttelton Road, Edgbaston, Birmingham, West Midlands, B16 9JN 37, Clare Street, Stoke-On-Trent, ST4 6EE |  | SHARAN | COMPLETED | MEDIUM |  | 2 days | 2024-11-04 | 2024-11-05 | 2024-11-06 |  | No1186_detail_page_company_owned_Sharan_N_P_05_11_2024
1187 | 2024-09-26 | ISSUE | Planning Application | if no data is available when we select keywords, please change the message to No data found. Instead we are showing Planning Data not available We are actively engaged in the process of integrating planning data from various councils across the UK. However, at this time, planning applications for wyre_forest Local Authority are not yet available within our system. We apologise for any inconvenience caused. For direct access to planning applications for the council, please refer to the following link: https://planningpa.wyreforestdc.gov.uk/online-applications/ |  | SANDEEP | CLOSED | MEDIUM |  |  | 2024-10-10 | 2024-10-10
1188 | 2024-09-26 | ISSUE | Planning Application | council names with 2 or 3 words, in the filter section are shown separately https://tinyurl.com/284mtdsc |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-10-07 | 2024-10-07
1189 | 2024-09-26 | ISSUE | Report | estimate value/range accepts - |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-09 | 2024-10-09 | 2024-10-10 |  | No1189_report_estimate_value_accepts_hyphen_Sharan_N_P_09_10_2024
1190 | 2024-09-27 | ISSUE | Report | the estate agent names are not shown in the reports in on market comparable page |  | SHARAN | COMPLETED | LOW |  |  | 2024-09-27 | 2024-09-27 |  |  | No1176_Report_primary_image_upload_Sharan_N_P_27_09_2024
1191 | 2024-09-30 | ISSUE | Report | In the LetsBid report section, some addresses on the market comparables properties list show the square footage as ‘not available,’ whereas on Rightmove, the square footage is available. The Ryde, Hatfield, Hertfordshire, AL9 5DQ 3, Cheviots, Hatfield, AL10 8JT | Web | SHARAN | NOT STARTED | LOW | [5 empty] | check with data team
1192 | 2024-10-01 | ISSUE | Withdrawn | to check stc/stc removed/under offer before withdrawn: 559, Aldermans Green Road, Coventry, West Midlands, CV2 1NL 39, Falmer Road, Enfield, London, EN1 1PZ 196 Elsinge Road, Enfield, EN1 4PA 8 Nursery Road, Broxbourne, EN10 6AL 28 Almond Way, Earl Shilton, Leicester, LE9 7HZ 51, Fernwood Avenue, Hartlepool TS25 5LU 27, Clarkson Court, Hartlepool TS25 5HP 7, Felixstowe Close, Hartlepool TS25 2RE 9, Bennett Road, Hartlepool TS25 4NR 21, Countisbury Avenue, Enfield, London, EN1 2NL 7, Philip Avenue, Bowburn, Durham, County Durham, DH6 5EQ 6, Foster Terrace, Croxdale, Durham, County Durham, DH6 5HP 1, Hawthorn View, Thornley, Durham, Easington, DH6 3HZ 33, Carlisle Street, Hartlepool, TS25 1BL CM20 - 69 ¦ EN1 - 193 ¦ CV2 - 210 ¦ EN10 - 92 ¦ HX3 - 156 ¦ LE9 - 249 ¦ TS25 - 260 ¦ DH6 - 213 |  | RISHIKA | COMPLETED | MEDIUM | [5 empty] | count has reduced, incorrect listing removed
1193 | 2024-10-01 | ISSUE | Listing Page | when we select multiple outcodes at a time sometimes no data is shown even if there are properties (If we apply filter to show properties by weeks and select one filter randomly, the default outcode displays "no data available" even though data is present) |  | SANDEEP | CLOSED | LOW
1194 | 2024-10-01 | ISSUE | Back to Market | properties are listed under back to market but it seems wrong we are showing a withdrawn status but the property is on market 28, Jaguar Drive, North Hykeham, Lincoln, North Kesteven, Lincolnshire, LN6 9SE 14, Brook View, Thaxted, Dunmow, Uttlesford, Essex, CM6 2LX Flat 21, Mulberry House, Victoria Park Square, London, Tower Hamlets, London, E2 9PQ 43, St Georges Road, Enfield, London, EN1 4TY - does this property need to be listed under back to market 91, Amethyst Road, Christchurch, Dorset, BH23 3ED 12A, Sycamore Close, Christchurch, Dorset, BH23 2EL |  | SANDEEP | COMPLETED | HIGH
1195 | 2024-10-01 | ISSUE | Detail Page | we are showing withdrawn activity for properties that are still on market 137, Auckland Road, Potters Bar, Hertsmere, Hertfordshire, EN6 3HF - when checked in rightmove it's shown as New Home 103, Kelsterton Road, Connahs Quay, Deeside, Flintshire, CH5 4BL |  | DATA TEAM | COMPLETED | HIGH
1196 | 2024-10-02 | TASK | Detail Page | for the listing activities before the Listed Date, grey out the activities that come before the listed date |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-10-02 | 2024-10-02 | 2024-10-03 |  | no1196-listing-activity-grey-out-sandeep-02oct2024
1197 | 2024-10-02 | TASK | Postcard | 2 credits for a postcard |  | RIJO | CLOSED | MEDIUM
1198 | 2024-10-02 | ISSUE | Listing Page | sort by list date is not correct please check in all listing pages |  | SANDEEP | COMPLETED | HIGH |  | 3 days | 2024-11-04 |  |  | updated Nov 5: - sort by date not correct in withdrawn, price drop, | no1198-sort-by-date-issue-sandeep-15oct2024 n01198-sorting-in-listing-pages-sandeep-04nov2024
1199 | 2024-10-04 | ISSUE | Probate Campaign | addresses are duplicating in stannp when sending 100+ letters fro probate |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-10-04
1200 | 2024-10-07 | UK TEAM | Report | utility supplies should be enabled by default when generating a report |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-10-09 | 2024-10-09
1201 | 2024-10-08 | UK TEAM | Report | for on market comparables, add the links to Rightmove/Zoopla so they can view the listing from there itself | Web | RIJO | NOT STARTED | LOW
1202 | 2024-10-09 | UK TEAM | Listing Page | new listing: If a property is withdrawn and re-listed after two months, mark it as a new listing and add the message "Previously on the market with another agent. https://www.prospectingtool.letsbidproperty.co.uk/properties/p-99201 |  |  | COMPLETED
1203 | 2024-10-09 | UK TEAM | Report | property image page - Display property images side by side, across two pages (similar to the old report) |  | SHARAN | COMPLETED | HIGH |  | 3 days | 2024-10-31 | 2024-10-31 | 2024-11-04 |  | No1203_report_property_image_Sharan_N_P_31_10_2024
1204 | 2024-10-09 | TASK |  | If there’s a gap of only two weeks between withdrawn and for-sale activities, remove both entries. add the logic to cron https://www.prospectingtool.letsbidproperty.co.uk/properties/p-319901 | Web | SANDEEP | NOT STARTED
1205 | 2024-10-09 | UK TEAM | Listing Page | Add filters for bedroom count and price range (values similar to Rightmove), allowing multiple selections remove the platform filter. property type filter: - show the types that are commonly used at the top - remove unwanted types from the dropdown -------------------- Implement in all the other listing pages - Withdrawn Price drop STC back to market |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-10-18 | 2024-10-28 | 2024-12-19 | updated Nov 5: - when we click on clear filter in Filter by weeks listing, week filters are removed but the user remains in the filtered by week listing eg: if we are in Filter by 16 weeks or more and then click on clear filter button, the user remains in 16 weeks or more listing but the title is Property Filtered in 16 Weeks or More and also all data is shown - if we filter the listing by Semi-Detached type, addresses that have the type Semi Detached (without -) are excluded please check Semi-Detached bungalow, semi-detached house EN6 - min price: for some prices the pound symbol is repeating -While giving filter for 4-8 weeks , properties displayed are from 8-16 weeks also there is a mistake while selecting 16 weeks or more (price drop)-check for AB25 -While giving filter for 4-8 weeks , property is present but it is not displayed under listing (sold/under offer)-check for AB25 | no1205-add-filters-bedroom-price-sandeep-17oct2024 ------------------------------------------------------------------- no1205-sub-withdrawn-sandeep-02dec2024 - testing no1205-sub-pricedrop-sandeep-03dec2024 - testing no1205-sub-backtomarket-sandeep-03dec2024 - testing no1205-sub-soldunderoffer-sandeep-06dec2024 - testing
1206 | 2024-10-09 | UK TEAM |  | onthemarket scraping | Data | DATA TEAM | NOT STARTED | LOW
1207 | 2024-10-09 | ISSUE |  | planning not getting property data api 90, Water Street, Kingswinford, DY6 7QD 59, Penzer Street, Kingswinford, West Midlands DY6 7AB 26, Moncrieffe Close, Dudley, West Midlands, DY2 7DF |  | SHARAN | COMPLETED | HIGH |  |  | 2024-10-09 | 2024-10-09 | 2024-10-10 |  | No1207_Report_property_data_api_planning_Sharan_N_P_09_10_2024
1208 | 2024-10-09 | ISSUE | Price Drop | rightmove activity not updated 84 Pemdevon Road, Croydon, CR0 3QP - reduced on oct 8 |  |  | COMPLETED | MEDIUM | [5 empty] | check after next run
1209 | 2024-10-09 | ENHANCEMENT | Live campaign | local print - the preview and letter generated is not same increase the address box height |  | SANDEEP | DUPLICATE TASK | LOW | [5 empty] | will be done with the editor task
1210 | 2024-10-09 | TASK | Postcard | postcard for DMA | Web | RIJO | DISCUSS | MEDIUM |  | 7 days
1211 | 2024-10-09 | ISSUE |  | the listed date is not correct https://www.prospectingtool.letsbidproperty.co.uk/properties/b-3001547 https://prospectingtool.letsbidproperty.co.uk/properties/p-2895666 |  | SANDEEP | DUPLICATE TASK | HIGH
1212 | 2024-10-09 | ISSUE |  | the bed room and bathroom count is not correct https://www.prospectingtool.letsbidproperty.co.uk/properties/b-3001547 | Data | DATA TEAM | TESTING | MEDIUM | [5 empty] | Data not updated from engine
1213 | 2024-10-10 | ISSUE | Report | when generating reports sometimes the floorplan is not shown even if it's available it is shown when we try again |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-10-25 | 2024-10-28 | 2024-10-29 |  | No1213_report_floor_plan_images_missing_28_10_2024_Sharan_N_P
1214 | 2024-10-10 | TASK | Report | change status of the property accordingly if property is withdrawn/stc/under offer show the status |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-10-10 | 2024-10-10 | 2024-10-22 |  | No1214_Report_property_status_change_Sharan_N_P_10_10_2024
1215 | 2024-10-10 | ISSUE | Planning Application | shows a warning message when we click on new homes https://tinyurl.com/yvoreemh |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-10-10 | 2024-10-10
1216 | 2024-10-14 | DEMO | Postcard | postcard management - can the 2 boxes be shown without having to scroll horizontally? the user might miss the scroll and it might seem as though it's cropped |  | RIJO | COMPLETED | MEDIUM
1217 | 2024-10-14 | DEMO | Postcard | after confirming the postcard bulk mail, show a loader after confirming or grey out the address. |  | RIJO | COMPLETED | MEDIUM
1218 | 2024-10-14 | DEMO | Wallet/Credit | postcard - the amount deducted for postcard bulk mail is not correct, only 1 credit is debited |  | RIJO | CLOSED | MEDIUM
1219 | 2024-10-14 | DEMO | Wallet/Credit | postcard - show a proper title for credits deducted for postcard it shows Twenty Bulk Mail Payment |  | RIJO | COMPLETED | MEDIUM
1220 | 2024-10-14 | DEMO | Campaign History | if postcard was sent do we need to mention it in the campaign history? |  | RIJO | COMPLETED | MEDIUM
1221 | 2024-10-14 | DEMO | 20-20 Targeted Campaign | the page keeps loading after clicking on bulk mail for letter and postcard |  | RIJO | COMPLETED | HIGH
1222 | 2024-10-14 | DEMO | Postcard Management | 20-20 targeted - increase the trigger width https://tinyurl.com/2x9vn55b |  | RIJO | COMPLETED | LOW
1223 | 2024-10-16 | UK TEAM | Planning Application | an agent has asked whether for new homes we can add another key word as “Reserve matters” he has specialised in land and new homes and said this is definitely a key word all of them look for |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-05 | 2024-12-05 | 2024-12-12 |  | No1223_New_homes_keyword_reserve_matters_Sharan_N_P_05_12_2024
1224 | 2024-10-17 | UK TEAM |  | Option to send email instead of letters feedback from a few agents I’ve called today is can we somehow implement an email feature? So instead of sending a letter can they have the option to insert an email address? I guess this is more so for vendors/landlord details they have already and maybe went on with another agent | Web | UNASSIGNED | DISCUSS | MEDIUM
1225 | 2024-10-17 | DEMO | Postcard Management | change the text to: This content will be populated based on the selected address in the live campaign. |  | RIJO | COMPLETED | MEDIUM
1226 | 2024-10-17 | DEMO | Postcard | when we preview the postcard, the contents are move a bit down. there is a space at the top in the front of postcard and the contact details get cut off https://tinyurl.com/2c236d4c |  | RIJO | CLOSED | MEDIUM
1227 | 2024-10-17 | DEMO | Postcard | in the campaign history for the postcard, the status is Pending |  | RIJO | COMPLETED | MEDIUM
1228 | 2024-10-17 | DEMO | Wallet/Credit | postcard - show a proper title for credits deducted for 20-20 Targeted postcard |  | RIJO | COMPLETED | MEDIUM
1229 | 2024-10-17 | DEMO | Postcard | the Credits you own shown is different when we are sending letter and postcard |  | RIJO | COMPLETED | MEDIUM
1230 | 2024-10-18 | ISSUE | Report | When the address is modified and the "Modify the selected property address" button is unchecked, the modified address is displayed . |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-10-28 | 2024-10-28 | 2024-11-04 | 28th Oct : when we select the modified address again ,it is still showing modified address | No1230_report_modify_address_Sharan_N_P_24_10_2024
1231 | 2024-10-18 | DEMO | Postcard | was able to send the postcard without previewing |  | RIJO | CLOSED | MEDIUM
1232 | 2024-10-18 | DEMO | Postcard | if the url has been added or removed, it does not reflect in the already existing postcard templates. If we have already added a postcard template and then add in the url, the qr code is not shown in the existing postcard only in the newly added ones it's shown. same for when the url is removed |  | RIJO | CLOSED | MEDIUM
1233 | 2024-10-18 | DEMO | Postcard | qr code on postcard: - reduce the box size - the text gets cropped - too much space below the qr code https://tinyurl.com/2xous4m8 |  | RIJO | COMPLETED | MEDIUM
1234 | 2024-10-18 | DEMO | Postcard | postcard back - the text above the contact details, please center it https://tinyurl.com/226jr3m5 |  | RIJO | COMPLETED | MEDIUM
1235 | 2024-10-18 | DEMO | Postcard | getting an error page https://tinyurl.com/25x8m5pj |  | RIJO | COMPLETED | MEDIUM
1236 | 2024-10-18 | DEMO | Postcard | the tag shown sometimes gets a bit cropped, if the maximum characters are added https://tinyurl.com/2bv6k2ex |  | RIJO | COMPLETED | MEDIUM
1237 | 2024-10-18 | DEMO | Postcard | please make sure _ is not shown in the postcard for property type https://tinyurl.com/27zv4q2s |  | RIJO | COMPLETED | MEDIUM
1238 | 2024-10-18 | DEMO | Postcard | after sending a postcard, the page keeps loading for sometime it does not refresh after confirming |  | RIJO | COMPLETED | MEDIUM
1239 | 2024-10-18 | DEMO | 20-20 Targeted Campaign | when we send letter bulk mail the page just keeps loading |  | RIJO | COMPLETED | HIGH
1240 | 2024-10-18 | DEMO | Summary | do we need to show the postcard count separately? |  | RIJO | COMPLETED | MEDIUM
1241 | 2024-10-18 | UK TEAM | Anniversary Letter | option to remove side panel from the anniversary letters |  | RIJO | DUPLICATE TASK | MEDIUM | [6 empty] | no1253_anniversary_letter_enable_toggle_Rijo_05Nov24
1242 | 2024-10-18 | UK TEAM |  | website not responsive - ipad |  | SATHEESH | DUPLICATE TASK | MEDIUM | [5 empty] | 1254
1243 | 2024-10-22 | ISSUE | Report | Error while generating report North End Villa, Wingate, County Durham, TS28 5AP |  | SHARAN | COMPLETED | HIGH |  |  | 2024-10-22 | 2024-10-22 | 2024-10-22 |  | No1243_report_generating_issue_Sharan_N_P_22_10_2024
1244 | 2024-10-23 | DEMO | 20-20 Campaign | postcard - for some addresses when we preview the postcard it shows Forbidden when editing the postcard is not shown 2, Croft Gardens, Whitley, Goole, North Yorkshire DN14 0HA 25, Broompark Road, Goole, East Riding Of Yorkshire DN14 6YF |  | RIJO | CLOSED | MEDIUM
1245 | 2024-10-23 | DEMO | Postcard | qr code on postcard: the text gets cropped (please check in the preview) https://tinyurl.com/2yegyb72 |  | RIJO | COMPLETED | MEDIUM
1246 | 2024-10-23 | DEMO | 20-20 Targeted Campaign | 20-20 targeted postcard - getting an error page when sending postcard |  | RIJO | COMPLETED | MEDIUM
1247 | 2024-10-23 | UK TEAM | Report | On the reports section in customer values please add on bedroom count the option ‘studio’ Studio in property type as well |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-10-28 | 2024-10-28 | 2024-10-29 |  | No1248_comparable_tool_added_option_studio_Sharan_N_P_24_10_2024
1248 | 2024-10-23 | UK TEAM | Comparable Tool | please add on bedroom count the option ‘studio’ |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-10-24 | 2024-10-24 | 2024-10-29 |  | Don't merge seperatly No1248_comparable_tool_added_option_studio_Sharan_N_P_24_10_2024
1249 | 2024-10-25 | UK TEAM | Letter management | when creating or editing content, show a message asking them to choose the fonts | Web | UNASSIGNED | NOT STARTED | MEDIUM | [5 empty] | will do with the letter editor update
1250 | 2024-10-25 | UK TEAM | Report | shows sqft not available for the property but it's available in the epc or RM/Z listing | Web | SHARAN | NOT STARTED | HIGH | [5 empty] | 30-10-2024 Sample address
1251 | 2024-10-25 | UK TEAM | Report | boundary editor - close editor move it to the right box | Web | SHARAN | COMPLETED | MEDIUM |  | 2 days | 2024-12-23 | 2024-12-23 | 2024-12-24 |  | No1251_Report_os_map_layer_edit_close_btn_Sharan_N_P_23_12_2024
1252 | 2024-10-25 | UK TEAM | Live campaign | local print - add a toggle to add or remove The Homeowner above the address except for probate | Web | SANDEEP | DISCUSS | HIGH
1253 | 2024-10-25 | UK TEAM |  | option to remove side panel from the anniversary letters |  | RIJO | COMPLETED | HIGH |  | 4 days | 2024-11-05 | 2024-11-06 | 2024-11-07 |  | no1253_anniversary_letter_enable_toggle_Rijo_05Nov24
1254 | 2024-10-25 | UK TEAM |  | ipad responsive | UI | SATHEESH | NOT STARTED | MEDIUM
1255 | 2024-10-25 | UK TEAM | Report | property images and floor plan missing in report for on market properties when we search 4 Kaymar Court BL1 6BA 16 Heaton Court BL1 5DG 5 The Starkies BL9 9QR 91 Broad O Th Lane BL1 6RU 32 Embsay Close BL1 7EJ |  | SHARAN | COMPLETED | HIGH |  |  | 2024-10-28 | 2024-10-28 | 2024-10-29 |  | No1213_report_floor_plan_images_missing_28_10_2024_Sharan_N_P
1256 | 2024-10-25 | UK TEAM | Local Print | if mulitple local prints are done and the user doesn't print the letter, show only the last local print letters don't show the older campaigns |  | RIJO | COMPLETED | HIGH |  |  | 2024-11-05 | 2024-11-06 | 2024-11-07 |  | no1312_user_local_print_notification_update_Rijo_05Nov2024
1257 | 2024-10-25 | DEMO | Postcard Management | delete confirmation message - it's given as Delete Comment https://tinyurl.com/26pt6nyq |  | RIJO | COMPLETED | MEDIUM
1258 | 2024-10-25 | DEMO | Postcard Management | when we click on the preview button, it shows 404 page |  | RIJO | CLOSED | MEDIUM
1259 | 2024-10-25 | DEMO | Postcard | do we need to show the text above the confirmation? https://tinyurl.com/2akb5ux8 |  | RIJO | COMPLETED | MEDIUM
1260 | 2024-10-25 | DEMO | Postcard | confirm the credits when sending postcard |  | RIJO | COMPLETED | MEDIUM | [5 empty] | 2 credits per postcard
1261 | 2024-10-25 | DEMO | Postcard | change the confirmation message: I have reviewed the postcard generation using the print preview option and confirmed that everything is correct. https://tinyurl.com/22ew8qoa |  | RIJO | COMPLETED | MEDIUM
1262 | 2024-10-25 | DEMO | Postcard Management | 20-20 targeted - chnage the message to This content will be populated based on the selected address in the live campaign. |  | RIJO | COMPLETED | MEDIUM
1263 | 2024-10-25 | DEMO | 20-20 Campaign | postcard - will the text for property price be always "Sold on your street for" If the user enters another text, can't we show that with the price? Also the property price shown is the listed price right? |  | RIJO | COMPLETED | MEDIUM | [5 empty] | its last sold price of the property fetched from mongosold Db
1264 | 2024-10-25 | DEMO | Postcard Management | 20-20 targeted - when we preview the postcard, the contents are move a bit down. there is a space at the top in the front of postcard and the contact details get cut off | Web | RIJO | IN PROGRESS | MEDIUM
1265 | 2024-10-25 | DEMO | Postcard | do we need to mention that the user has the option to upload image, the user might not know that there is an option to upload image |  | RIJO | COMPLETED | MEDIUM
1266 | 2024-10-28 | DEMO | Campaign History | postcard - the trigger is given as 20-20 Letter |  | RIJO | COMPLETED | MEDIUM
1267 | 2024-10-29 | UK TEAM | Report | On the front page of the report, when you input a property photo, there ends up being a large gap at the page bottom. To fill this, can we have the address formatted so that it is centralised and line by line? Can the price also fall in line with this and be larger to highlight it? |  | SHARAN | CLOSED | MEDIUM
1268 | 2024-10-29 | UK TEAM | Report | For buyer report, the price to appear as 'Asking Price' |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-01 | 2024-11-01 | 2024-11-06 |  | No1268_report_text_change_Sharan_N_P_01_11_2024
1269 | 2024-10-29 | ISSUE | Report | even if we remove the floorplan and add our own image, the removed floorplan is shown in the report |  | SHARAN | COMPLETED | HIGH |  |  | 2024-10-29 | 2024-10-29 | 2024-10-29 | https://demo.devidiamober.com/view-report/report_8866_291020240653999481.pdf | No1213_report_floor_plan_images_missing_28_10_2024_Sharan_N_P
1270 | 2024-10-29 | ISSUE | Properties | Match the detail page property type and report type | Web | SHARAN | HOLD | HIGH |  |  | 2024-10-29 | 2024-10-29 |  |  | 1270_properties_property_type_title_Sharan_N_P_29_10_2024
1271 | 2024-10-29 | ISSUE | Listing Page | search in property type does not work when the page first loads, only after selecting a type we can search |  | SANDEEP | CLOSED | MEDIUM | [5 empty] | search removed, common types are listed at the top
1272 | 2024-10-29 | ISSUE | Report | even if we don't select any property in Additional Property Comparable, the page is still selected |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-29 | 2024-10-29 | 2024-11-04 |  | Check the entire branch name while merge No1271_report_additional_comparable_tool_Sharan_N_P_29_10_2024
1273 | 2024-10-29 | SUGGESTION | Report | when we enlarge the floorplan, the close button is not visible can we show it closer to the floorplan or make the button a bit more prominent? |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-30 | 2024-10-30 | 2024-11-04 |  | No1273__1_report_floor_plan_Sharan_N_P_31_10_2024
1274 | 2024-10-29 | ISSUE |  | estate agent name is shown as Unknown there are few properties with estate agent name as Unknown 4 Kaymar Court, Chorley Old Road, Bolton, BL1 6BA 22, Riseley Road, Stoke-On-Trent, ST4 6AU | Data | DATA TEAM | DISCUSS | MEDIUM | [5 empty] | Data not came from engine
1275 | 2024-10-29 | ISSUE | Postcard | postcard - for some addresses when we preview the postcard it shows Forbidden when we click on edit pdf and then preview, it works 25, Broompark Road, Goole, East Riding Of Yorkshire DN14 6YF 12 Henry Street, Goole, DN14 6TG 2, Lime Tree Drive, Whitley, Goole, Selby, North Yorkshire, DN14 0GF 32, Abbey Walk, Halifax, Calderdale, West Yorkshire, HX3 0AJ #additional fixes : fix postcard image fetch call if no resource available fix preview toolbar added title to front and back preview button |  | RIJO | COMPLETED | MEDIUM |  |  | 2024-10-28 | 2024-10-30 | 2024-11-04 |  | no322_postcard_feature_Nikila_26Apr24
1276 | 2024-10-29 | SUGGESTION | Postcard | if bed count is not available can we hide it, instead of just showing the icon and bedroom text https://tinyurl.com/2apgt46q option to remove bedroom icon |  | RIJO | CLOSED | MEDIUM |  | 2 days
1277 | 2024-10-29 | ISSUE | Listing Page | When the property type "Studio" is selected, the bed count for some addresses is missing. |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-02 | 2024-11-02 | 2024-11-06 |  | No1277_Property_listing_studio_bed_null_Sharan_N_P_02_11_2024
1278 | 2024-10-29 | ISSUE | Listing Page | The dropdown box for property type should be slightly larger so that all property types can be properly aligned. |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-30 | 2024-10-30 | 2024-10-30
1279 | 2024-10-29 | SUGGESTION | Postcard Management | when adding a trigger for postcard, do we need to mention that the user has the option to upload image in the live campaign the user might not know that there is an option to upload image it's only given when we click on edit pdf in the live campaign |  | RIJO | COMPLETED | MEDIUM
1280 | 2024-10-29 | TASK | Listing Page | property type filter: - show the types that are commonly used at the top - remove unwanted types from the dropdown |  | SANDEEP | CLOSED | MEDIUM
1281 | 2024-10-29 | ISSUE | Postcard | when we preview the postcard, the contents are move a bit down. there is a space at the top in the front of postcard and the contact details get cut off https://tinyurl.com/2c236d4c |  | RIJO | COMPLETED | MEDIUM
1282 | 2024-10-30 | ISSUE | Campaign History | redo campaign button not working - all addresses should get added to the campaign some addresses are not getting added to the campaign (are we only adding the address back to campaign only if we are subscribed) | Web | SANDEEP | NOT STARTED | MEDIUM |  | 2 days
1283 | 2024-10-30 | ISSUE | Comparable Tool | Presence of an underscore ('_') between the words. https://www.awesomescreenshot.com/image/51335975?key=35657cc547e8407b0957e7889ef0b2a1 |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-31 | 2024-10-31 | 2024-11-04 |  | No1283_1_comparable_tenure_underscore_Sharan_N_P_31_10_2024
1284 | 2024-10-30 | SUGGESTION | Detail Page | change the title to Sold Comparables or Sold property comparables |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-01 | 2024-11-01 | 2024-11-04 |  | No1284_detail_page_comparable_text_change_Sharan_N_P_01_11_2024
1285 | 2024-10-30 | SUGGESTION | Probate Detail | change the title to Sold Comparables or Sold property comparables |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-01 | 2024-11-01 | 2024-11-04 |  | No1284_detail_page_comparable_text_change_Sharan_N_P_01_11_2024
1286 | 2024-10-30 | ISSUE | Postcard | the bedroom, bathroon icon and the arrow is not shown in the postcard (noticed this after we logout and then log back in, it was there when the template was first added) |  | RIJO | COMPLETED | MEDIUM
1287 | 2024-10-30 | ISSUE | Postcard Management | 20-20 targeted - after saving/editing 20-20 targeted trigger, the user is taken to the 20-20 tab | Web | SHARAN | COMPLETED | LOW |  | 1 day | 2024-12-30 | 2024-12-30 | 2024-12-31 |  | No1287_Postcards_tabs_Sharan_N_P_30_12_2024
1288 | 2024-10-30 | ISSUE | Postcard Management | 20-20 targeted - once the template is saved and when we edit, the changes are not shown when we preview it after saving |  | RIJO | COMPLETED | MEDIUM
1289 | 2024-10-30 | SUGGESTION | Postcard | when sending a postcard, if no image is available for the property do we need to show a default image there? if user tries to send a postcard without an image, show a pop up asking them to upload an image | Web | ANISHA | APPROVAL | MEDIUM |  | 2 days |  |  |  | updated Jan 2: - change the message to An image is required to proceed with sending the postcard. Please use the 'Edit PDF' button to upload your image. - not able to send postcards even after uploading an image, on clicking on Confirm & Send it shows the warning message
1290 | 2024-10-30 | ISSUE | 20-20 Targeted Campaign | all addresses are not reaching stannp (if we send 80 letters only 40 are reaching stannp, the rest is shown as pending) the full amount is debited from wallet https://www.prospectingtool.letsbidproperty.co.uk/twenty-targeted-campaign-history/41577?from=twenty_targeted_campaign_history https://www.prospectingtool.letsbidproperty.co.uk/twenty-targeted-campaign-history/41677?from=twenty_targeted_campaign_history |  | SANDEEP | DUPLICATE TASK | HIGH | [5 empty] | check if this happens again with 100+ letters
1291 | 2024-10-30 | ISSUE | 20-20 Targeted Campaign | when letters are being sent to multiple addresses, the addresses are not greyed out like the rest when processing |  | SANDEEP | COMPLETED | MEDIUM |  | 1 day |  |  | 2024-11-27 | check 20-20 also --------------------- updated Nov 21: - the addresses remain greyed out, when checked in the campaign history the status is Pending for the addresses | no1291-twenty20-targeted-greyout-issue-sandeep-14nov2024
1292 | 2024-10-30 | ISSUE | Live campaign | qr code is not shown for some addresses https://www.prospectingtool.letsbidproperty.co.uk/directmail-campaign-history/41583 https://www.prospectingtool.letsbidproperty.co.uk/targeted-campaign-history/41590?from=targeted_campaign_history |  | RIJO | COMPLETED | MEDIUM | [5 empty] | check again
1293 | 2024-10-30 | ISSUE | Targeted Campaign | when letters are being sent to multiple addresses, the addresses are not greyed out like the rest when processing only the address that is being sent is greyed out |  | SANDEEP | COMPLETED | MEDIUM |  | 1 day | 2024-11-12 |  | 2024-11-27 | updated Nov 19: - getting an error page when we do bulk mail - | no1293-greyout-issue-in-targeted-sandeep-08nov2024
1294 | 2024-10-30 | SUGGESTION | Live campaign | edit address - if the address is shown in a single line, please show the message Address needs to be atleast 3 lines. we are showing Address cannot be single line and then if we make it in 2 lines we are showing it needs to be atleast 3 lines | Web | SANDEEP | NOT STARTED | LOW |  | 1 day
1295 | 2024-10-30 | DISCUSS | Active Buyer | Are we only displaying a company under "Active Buyers" if they have purchased a property in the selected outcode? DE14 - LEINSTER PROPERTY INVESTMENTS LIMITED |  | RIJO | CLOSED | MEDIUM
1296 | 2024-10-30 | ISSUE | Comparable Tool | on market comparable - the sort by price and miles is not working |  | SHARAN | COMPLETED | LOW |  |  | 2024-10-31 | 2024-11-01 | 2024-11-04 |  | No1296_Comparable_tool_sorting_loader_missing_31_10_2024
1297 | 2024-10-30 | ISSUE | Sold- Under offer | the stc activity is repeating in the listing 59 Welbeck Street, Hull, HU5 3SA 41, Mons Street, Hull, City Of Kingston Upon Hull, HU5 3SZ 11 Kirklands Road, Hull, HU5 5AX 78, Curzon Avenue, Enfield, London, EN3 4UE 33 Dairy Close, Enfield, EN3 6PS | Web | SANDEEP | NOT STARTED | LOW |  | 2 days
1298 | 2024-10-31 | ISSUE | Report | the title number shown in the report is not correct 1, MOULTON RISE, LUTON, LU2 0AF 5, MOULTON RISE, LUTON, LU2 0AF title number missing in the report 116a, St. Marks Road, Enfield, Greater London, EN1 1BB 116 EN1 1BB |  | SHARAN | COMPLETED | HIGH |  | 3 days | 2024-11-04 | 2024-11-06 | 2024-11-13 | 4 Nov 2024 Can't check in demo or staging, only available on live --------------------- Nov 6: title number not correct | No1298_report_title_number_error_Sharan_N_P_04_11_2024
1299 | 2024-10-31 | ISSUE | Report | title number missing in the report 116a, St. Marks Road, Enfield, Greater London, EN1 1BB 116 EN1 1BB |  | SHARAN | DUPLICATE TASK | HIGH
1300 | 2024-10-31 | ISSUE | Properties | listed date is not correct - there are properties that have come on the market 5 months after they were withdrawn - property was withdrawn in october and listed back in october but the previous listings in october are greyed out https://www.prospectingtool.letsbidproperty.co.uk/properties/p-742024 https://www.prospectingtool.letsbidproperty.co.uk/properties/b-3001547 https://prospectingtool.letsbidproperty.co.uk/properties/p-2895666 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2090101 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-299094 |  | SANDEEP | COMPLETED | HIGH
1301 | 2024-10-31 | ISSUE | Properties | zoopla link issue for some of the old listings the / is missing in the zoopla url https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3003742 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3027793 |  | SHARAN | COMPLETED | MEDIUM |  | 2 days | 2024-11-02 | 2024-11-02 | 2024-11-06 | 02/11/2024 Scrapping error | No1301_properties_details_page_zoopla_url_issue_Sharan_N_P_02_11_2024
1302 | 2024-10-31 | ISSUE | Postcard Management | what if the user wants to select a color below the background color box |  | RIJO | CLOSED | LOW
1303 | 2024-10-31 | SUGGESTION | Postcard Management | Address section - instead of leaving it blank. mark the address box in the preview and when adding the postcard so the user know that it's for the address | Web | RIJO | NOT STARTED | LOW |  | 1 day
1304 | 2024-10-31 | ISSUE | Report | floor plans are repeating (taken from different sources but it's the same image) 1, St Marys Road, Rochester, ME2 4DF |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-01 | 2024-11-01 | 2024-11-04 | Sharan Live | No1304_Report_floor_plan_single_source_Sharan_N_P_01_11_2024
1305 | 2024-11-01 | ISSUE | Report | alignment issues: - planning application pages - make sure the title and the boxes are aligned https://tinyurl.com/26luo8ha - epc page - make the fonts a bit bigger - property summary - make sure the maps are aligned with the title section - |  | RIJO | DUPLICATE TASK | MEDIUM
1306 | 2024-11-01 | ISSUE | Report | floor plan - make the floor plan bigger |  | RIJO | DUPLICATE TASK | MEDIUM
1307 | 2024-11-01 | ISSUE | Report | epc page - make the fonts a bit bigger |  | RIJO | DUPLICATE TASK | MEDIUM
1308 | 2024-11-01 | ISSUE | Report | takes time to load after clicking on confirm after selecting an address |  | SHARAN | COMPLETED | MEDIUM
1309 | 2024-11-01 | UK TEAM | Postcard | increase the count for postcard - can we make it 50, 75, 100 | Web | RIJO | NOT STARTED | MEDIUM
1310 | 2024-11-01 | UK TEAM | Postcard | send postcards to the closest 40 similar property types, not just the neighbours | Web | RIJO | NOT STARTED | MEDIUM
1311 | 2024-11-01 | UK TEAM | Report | report design changes: - increase the font size - increase the title boxes - avoid blank spaces, instead show images or other data - add spaces |  | RIJO | COMPLETED | HIGH
1312 | 2024-11-04 | SUGGESTION | Live campaign | local print pop up to print - if user does it for lettings, do we need to show the pop up when they are on sales and vice versa? |  | RIJO | CLOSED | MEDIUM | [5 empty] | updated Nov 5: pop ups are shown | no1312_user_local_print_notification_update_Rijo_05Nov2024
1313 | 2024-11-04 | ISSUE | DMA Campaign | local print - letters for only some addresses are generated I had edited few addresses when doing both the campaigns https://www.prospectingtool.letsbidproperty.co.uk/directmail-campaign-history/41666 https://www.prospectingtool.letsbidproperty.co.uk/directmail-campaign-history/41664 Delivery status in campaign history - camel case |  | SANDEEP | CLOSED | HIGH
1314 | 2024-11-04 | ISSUE | Listing Page | The estate agent's name appears in a different format. https://www.awesomescreenshot.com/image/51383640?key=925ff2fc17691d3c6a58cd4311e0e4d5 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3036070 | Data | DATA TEAM | NOT STARTED | LOW
1315 | 2024-11-04 | ISSUE | Report | comparables - the price/sqft is not correct for some | Data | DATA TEAM | NOT STARTED | MEDIUM | [5 empty] | mongo db issue - please confirm
1316 | 2024-11-04 | ISSUE | Report | modify address: - not able to generate report for modified address - the modified tag is not shown after editing the address |  | SHARAN | COMPLETED | HIGH |  |  | 2024-11-04 | 2024-11-04
1317 | 2024-11-04 | ISSUE | Report | when we search an address directly in the report section, the status shown are not correct 83 Trinity Avenue, Enfield, EN1 1HT - withdrawn but when we search it shows sold stc https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3191110 - shown as off market | Web | SHARAN | TESTING | MEDIUM |  |  | 2024-12-09 | 2024-12-09 | 2024-12-31 |  | No1317_Report_status_change_Sharan_N_P_09_12_2024
1318 | 2024-11-04 | ISSUE | Report | Additional property comparables - after selecting comparables and clicking on Save and close, the page is not selected |  | SHARAN | COMPLETED | HIGH |  |  | 2024-11-04 | 2024-11-04 | 2024-11-07 |  | No1318_Report_addictional_comps_Sharan_N_P_04_11_2024
1319 | 2024-11-04 |  | Report | only 2 properties are listed under Sold in street 24, Abbeyville Walk, Manchester, M15 5ER |  | UNASSIGNED | CLOSED | MEDIUM | [5 empty] | only 2 sold properties for the postcode out of 6 properties in the postcode How to overcome this issue?
1320 | 2024-11-04 | ISSUE | Report | The header titles are not clickable when an address is confirmed. | Web | ANISHA | COMPLETED | LOW |  | 5hr |  |  | 2024-12-31 |  | no1320_headertitle_notclickable_address_confirm_Anisha30Dec2024
1321 | 2024-11-04 | ISSUE | Listing Page | There is a grammar error: "days" is used instead of "day." https://www.awesomescreenshot.com/image/51391569?key=aac7245c2b24bf3faba2487058ebf238 |  | SHARAN | COMPLETED | LOW
1322 | 2024-11-05 | ISSUE | Withdrawn | property is still on market but shown as withdrawn Flat 11, Stifford House, Stepney Way, London, Tower Hamlets, London, E1 3EF 2, Blakeys Crossing, Howden, Goole, East Riding Of Yorkshire, DN14 7GE (new home) 63 Russell Street, Luton, LU1 5EB 162, Darnley Road, Rochester, Rochester Upon Medway, Kent, ME2 2UN 19, Hillborough Road, Luton, LU1 5EY - stc but marked as withdrawn |  | UNASSIGNED | CLOSED | HIGH
1323 | 2024-11-05 | ISSUE | Report | in the sub titles of a page make sure the selected color is the same as the color chosen by the agent |  | SHARAN | CLOSED | MEDIUM | [5 empty] | 03/12/2024 sub headings design changed by new report
1324 | 2024-11-05 | ISSUE | 20-20 Targeted Campaign | local print - when the letter is generated the addresses and content are not proper https://www.prospectingtool.letsbidproperty.co.uk/twenty-targeted-campaign-history/41750?from=twenty_targeted_campaign_history https://tinyurl.com/249h4lwl -------------- bulk mail - all addresses are not reaching stannp (if we send 80 letters only 40 are reaching stannp, the rest is shown as pending) the full amount is debited from wallet https://www.prospectingtool.letsbidproperty.co.uk/twenty-targeted-campaign-history/41577?from=twenty_targeted_campaign_history https://www.prospectingtool.letsbidproperty.co.uk/twenty-targeted-campaign-history/41677?from=twenty_targeted_campaign_history |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-11-05 | 2024-11-06 | 2024-11-07 | updated Nov 5: - local print is working but not all letters are sent for bulk mail | no1324-twenty20-targeted-generated-letters-issue-sandeep-05nov2024
1325 | 2024-11-06 | ISSUE | Properties | Property withdrawn but we are not showing as withdrawn https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2400872 https://drive.google.com/file/d/1FGJWDiRCvCyWV841P2zOrJC3dqJWO4WP/view?usp=sharing , https://drive.google.com/file/d/1Rsf9TNcHoD0s_I9wdxSAzWwl1Lj6at0a/view?usp=sharing |  | UNASSIGNED | COMPLETED | MEDIUM
1326 | 2024-11-06 | ISSUE | Properties | Property type in listing page is detached and property type in detail page is semi detached https://drive.google.com/file/d/1aHiYNQRcYLzdsxag9Agv3ypQgvcT_UTV/view?usp=sharing, https://drive.google.com/file/d/1uMmAqmpaNLQGRNfItf6RJ5LumykMqnXX/view?usp=sharing Property type in listing page is town house and property type in detail page is terraced 61, Siddal Lane, Halifax, Calderdale, West Yorkshire, HX3 9JS https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3210901 |  | SHARAN | CLOSED | MEDIUM | [5 empty] | in the listing we are showing the data from R/Z and in the detail page the type is taken from epc
1327 | 2024-11-06 | ISSUE | Properties | Under report section we are showing floor plan and sold comparable but under detail page above details are not provided https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3211526 https://drive.google.com/file/d/17uaXA17jYUH_hAixyN25sIPir0M5Pi_m/view?usp=sharing, https://drive.google.com/file/d/1BQAkjY-ULU_xXaU85mOEkwZ4Z6lBlLwQ/view, https://drive.google.com/file/d/1jBMUD0VxsQVBitlaq1-ODLIj9PX0l36y/view?usp=sharing | Web | SHARAN | TESTING | MEDIUM |  |  | 2024-12-06 | 2024-12-09 | 2024-12-31 |  | No1327_detail_page_floorplan_offmarket_Sharan_N_P_09_12_2024
1328 | 2024-11-06 | ISSUE | Export csv | when we filter and export, all properties are shown in the exported file |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-11-13 |  | 2024-11-26 | updated Nov 19: - mismatch in count in the exported file and listing | no1328-export-csv-issue-sandeep-13nov2024
1329 | 2024-11-06 | ISSUE | 20-20 Campaign | not able to send letters to some addresses (whatsapp) 20 Elton Road, TS22 |  | RIJO | CLOSED | MEDIUM | [5 empty] | no neighbouring addresses found
1330 | 2024-11-06 | ISSUE | Properties | In report neighbouring planning history list is shown but the properties are not from NE21 5NQ postcode https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3211526 2, Berkley Avenue, Blaydon-On-Tyne, Gateshead, Tyne And Wear, NE21 5NQ https://drive.google.com/file/d/1L8flJiPTT_9K3vgdKywXXYlNfJZAEMwT/view?usp=sharing , https://drive.google.com/file/d/1MksdIBw9OD0apN7yZ6ifsr8lAEr-QOKl/view?usp=sharing , https://drive.google.com/file/d/1YT3olp3Ek7K3tugmFE_PlJ7l_ESvucLg/view?usp=sharing when checked in the council wesbite there were properties in NE21 5NQ |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-11-06 | 2024-11-06 |  | please check the planning data in mongodb 06/12/2024 Sharan N P Sorted by decision_issued_date descending order
1331 | 2024-11-06 | ISSUE | Report | marked as company owned in the reports 43 Hatton Gardens, Newark, NG24 4BU 2 Clover Drive, Little Canfield, Dunmow, CM6 4AH 114 Guild Close, Birmingham, B16 8DX 3, Stanmore Road, Birmingham, West Midlands, B16 9ST 31 Rotton Park Street, Birmingham, B16 0AE 36 Vernon Road, Birmingham, B16 9SH 7, Lyttelton Road, Edgbaston, Birmingham, West Midlands, B16 9JN 37, Clare Street, Stoke-On-Trent, ST4 6EE | Web | SHARAN | NOT STARTED | MEDIUM | [5 empty] | check after cron run | No1331_Report_company_owned_tag_Sharan_N_P_21_11_2024
1332 | 2024-11-06 | SUGGESTION | Detail Page | clear the icon and NA text from the detail page if bed count is not available do we need to show NA Bedroom https://tinyurl.com/28sqk6b9 https://prospectingtool.letsbidproperty.co.uk/properties/s-3007668 | Web | ANISHA | APPROVAL | MEDIUM
1333 | 2024-11-06 | ISSUE | Withdrawn | check new listing date logic also Price is displayed as 5000 but in rightmove it is displayed as 440000 and the agent name is also different https://www.prospectingtool.letsbidproperty.co.uk/properties/w-1990926 63 Moorfield Road, Enfield, EN3 5XW https://drive.google.com/file/d/1sjkL-KRCbntwAhWvb3aJ-_SUNz3-9oAq/view?usp=drive_link, https://drive.google.com/file/d/1IOV62Ch-7xYy45g4AbtYXusSBtHmWTqM/view?usp=drive_link | Web | SANDEEP | NOT STARTED | MEDIUM
1334 | 2024-11-06 | ISSUE | Properties | 2 Listing are provided under Listing Activity but when we navigate to both rightmove it displays only under offer with date 4 Nov https://drive.google.com/file/d/1F7_QJUdw3xL7d6PsJ7RlXqabulIiIDTn/view?usp=drive_link https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3210900 12, Knowle Top Drive, Halifax, Calderdale, West Yorkshire, HX3 8SL |  | SHARAN | CLOSED | MEDIUM
1335 | 2024-11-06 | ISSUE | Active Buyer | Company address is shown is different https://drive.google.com/file/d/18b-MFCQAOkwe8fzNQ39zMUOfBIrb1LM8/view?usp=sharing |  | UNASSIGNED | DUPLICATE TASK | MEDIUM
1336 | 2024-11-06 | ISSUE | Planning Application | multiple keywords not working even if we select multiple keywords, the listing gets filtered according to the last keyword selected |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-11-07 | 2024-11-07 | 2024-11-08 |  | no1336-muliple-keyword-issue-planning-sandeep-07nov2024
1337 | 2024-11-07 | ISSUE | Report | Mismatch in epc energy rating https://www.awesomescreenshot.com/image/51443925?key=db08ac12e2d7fadef95daf8da5dcb3f1 https://www.awesomescreenshot.com/image/51443972?key=93c335c4e67a7896f879fdf9c9f4c671 |  | VISHNU | DUPLICATE TASK | LOW | [5 empty] | need to update epc
1338 | 2024-11-07 | ISSUE | Anniversary Letter | Grammatical error https://www.awesomescreenshot.com/image/51451279?key=7a55ab769c0da4199b37a9e3c95dad8d |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-26 | 2024-11-26 | 2024-11-27 | Instead of 'a property ' it is written as an property | No1338_Anniversary_letter_msg_correction_Sharan_N_P_26_11_2024
1339 | 2024-11-07 | ISSUE | Listing Page | Todays date shown as 1 day https://drive.google.com/file/d/1G__fA8ESsjugFBcZz8AC7QhbBwmuque2/view?usp=sharing |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-20 | 2024-11-20 | 2024-11-22 |  | No1339_Properties_days_count_Sharan_N_P_20_11_2024
1340 | 2024-11-08 | ISSUE | Properties | Under listing the property type is shown as '2' https://drive.google.com/file/d/19Ef7Br5TH2GSvQ_b9XJiutHTG-C0eFr3/view?usp=drive_link |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-03 | 2024-12-03 | 2024-12-05 | 28/11/2024 This address property type not mentioned in rightmove/zoopla listing | No1340_Listing_property_type_unwanted_string_Sharan_N_P_03_12_2024
1341 | 2024-11-08 | SUGGESTION | Planning Application | Should we need to display the heading panel if planning data not available https://drive.google.com/file/d/1Ut5pzhbhKTbXanLHUcrbMz-0NoeI94nk/view?usp=drive_link |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-29 | 2024-11-29 | 2024-12-05 |  | No1341_planning_thead_when_empty_Sharan_N_P_28_11_2024
1342 | 2024-11-08 | ISSUE | Price Drop | Property type is mentioned in listing but in detail page it is not mentioned https://www.prospectingtool.letsbidproperty.co.uk/properties/d-3147077 74A Huddersfield Road, Elland, HX5 9AA Property type is mentioned as flat in listing but in detail page it is mentioned as terraced and comparables are listed based on terraced 35, Garrick Close, Coventry, West Midlands, CV5 7NQ https://www.prospectingtool.letsbidproperty.co.uk/properties/d-2590219https://www.prospectingtool.letsbidproperty.co.uk/properties/d-2590219 | Web | SHARAN | NOT STARTED | LOW | [5 empty] | updated Nov 29: check available property type in other listings
1343 | 2024-11-08 | ISSUE | Report | Sqft,EPC mentioned in report is wrong https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14095_081120240548853988.pdf https://www.prospectingtool.letsbidproperty.co.uk/properties/d-3147077 74A Huddersfield Road, Elland, HX5 9AA |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-28 | 2024-11-28 | 2024-12-05 |  | No1343_Report_updated_epc_sqft_value_Sharan_N_P_28_11_2024
1344 | 2024-11-08 | ISSUE | Detail Page | Comparables are available but we are not displaying in detail page https://www.prospectingtool.letsbidproperty.co.uk/properties/d-3147077 74A Huddersfield Road, Elland, HX5 9AA |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-03 | 2024-12-03 | 2024-12-12 | 28/11/2024 No property type without type can't provide comparables -------------------- updated Nov 29: check available property type in other listings | No1344_Details_page_property_type_Sharan_N_P_03_12_2024
1345 | 2024-11-08 | ISSUE | Sold- Under offer | estate agent name is displayed is wrong and the property type is shown as unknown in detail page https://www.prospectingtool.letsbidproperty.co.uk/properties/s-3214035 10 Palstone Lodges, Palstone Lane, South Brent, TQ10 9NU | Web | SANDEEP | NOT STARTED | MEDIUM | [5 empty] | check in json file whether it's an engine issue
1346 | 2024-11-08 | ISSUE | Withdrawn | Property type field is empty, but property type is available in epc 22 Bradford Road, Drighlington, Bradford, BD11 1AB |  | SHARAN | CLOSED | MEDIUM |  |  | 2024-11-28 | 2024-11-28 |  | 28/11/2024 EPC type is House | No1346_details_page_type_missing_Sharan_N_P_28_11_2024
1347 | 2024-11-08 | ISSUE | Report | When the "Modify Address" feature is enabled and random inputs are provided, and then the feature is disabled, the property image does not display, and the property status is incorrect. |  | SHARAN | DUPLICATE TASK | LOW | [5 empty] | Task no.1355 duplicate task
1348 | 2024-11-08 | ISSUE | Comparable Tool | The correct result is not displayed if only the "Price To" field is provided. |  | SHARAN | COMPLETED | MEDIUM
1349 | 2024-11-08 | ISSUE | Planning Application | For some addresses, the agent name and address fields are blank. Additionally, no data is displayed when clicking on the planning details for the Basingstoke and Deane council. |  | SHARAN | CLOSED | LOW |  |  | 2024-11-26 | 2024-11-26
1350 | 2024-11-11 | ISSUE | Comparable Tool | Error message displayed is wrong https://drive.google.com/file/d/19TEPlW9FsiC_SaA_wVMBzNZEJJYwy1kF/view?usp=sharing |  | SHARAN | COMPLETED | MEDIUM | Linta |  | 2024-11-26 | 2024-11-26
1351 | 2024-11-11 | ISSUE | Comparable Tool | The "Price From" and "Price To" fields do not function as expected when the reset button is clicked. |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-19 | 2024-11-19 | 2024-11-22 |  | No1351_comparable_tool_reset_Sharan_N_P_19_11_2024
1352 | 2024-11-11 | ISSUE | Report | Valid until' date is different in EPC site and in report https://www.awesomescreenshot.com/image/51503723?key=0c081b39d55e024130150cee97ee2b6b https://www.awesomescreenshot.com/image/51503753?key=654ba17f803ba158a10113ecddd8b8d4 https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14491_041220240621921047.pdf |  | VISHNU | DUPLICATE TASK | LOW | Aayisha
1353 | 2024-11-11 | ISSUE | Report | "Incorrect address Format: 30, ENDYMION ROAD, HATFIELD, HERTFORDSHIRE, AL10 8AR Address in epc site : 30 Malting Mead Endymion Road HATFIELD AL10 8AR" | Web | SHARAN | NOT STARTED | LOW | Aayisha |  |  |  |  | getaddress limitation
1354 | 2024-11-11 | ISSUE | Outcodes | on double clicking on submit when adding outcode, disable the submit button after clicking once Postcode 'YO32' is repeated under dropdown https://drive.google.com/file/d/1opaJav9iJNG_XWpzqBH6ExPMwK7ZQE4c/view?usp=drive_link | Web | SHARAN | COMPLETED | LOW | Linta |  | 2024-12-23 | 2024-12-23 | 2024-12-31 |  | No1354_Outcode_submit_double_click_disable_Sharan_N_P_23_12_2024
1355 | 2024-11-12 | ISSUE | Report | When an address is modified and then unchecked, the status of the property changes. 88, Forbes Avenue, Potters Bar, EN6 5NQ |  | SHARAN | COMPLETED | LOW | Aayisha
1356 | 2024-11-12 | ISSUE | Report | EPC ISSUES: - Mismatch in epc energy rating https://www.awesomescreenshot.com/image/51443925?key=db08ac12e2d7fadef95daf8da5dcb3f1 https://www.awesomescreenshot.com/image/51443972?key=93c335c4e67a7896f879fdf9c9f4c671 - 'Valid until' date is different in EPC site and in report https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14491_041220240621921047.pdf - epc Valid until date, area and certificate number is different in report and in epc site 88, FORBES AVENUE, POTTERS BAR, EN6 5NQ https://www.awesomescreenshot.com/image/51514223?key=73f41dd83d89271ba542124fa7e13dab https://www.awesomescreenshot.com/image/51514246?key=623b6190a6411278caae6af5e69a1b46 - - epc rating is not correct in the report 223, CHINN BROOK ROAD, BIRMINGHAM, WEST MIDLANDS, B13 0NB | Data | VISHNU | NOT STARTED | LOW | Aayisha |  |  |  |  | mongodb not updated
1357 | 2024-11-12 | ISSUE | Detail Page | Blank spaces in company detail 47, Tudor Close, Hatfield, Welwyn Hatfield, Hertfordshire, AL10 9EJ https://www.awesomescreenshot.com/image/51525581?key=ad4f869af89b288ecfa0cf9e9c3869cc |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-19 | 2024-11-19 | 2024-11-22 |  | No1357_details_page_company_details_empty_Sharan_N_P_19_11_2024
1358 | 2024-11-13 | ISSUE | Report | In the "custom values" , the square feet field is currently accepting alphabets and special characters. It should only accept numerical input. |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-19 | 2024-11-19 | 2024-11-22 |  | No1358_Report_custom_values_Sharan_N_P_19_11_2024
1359 | 2024-11-15 | ISSUE | Withdrawn | Company owned tag in listing page, but not in detail page 4 Elm Place, Gooderstone, King's Lynn, PE33 9BX | Web | SHARAN | NOT STARTED | LOW | Aayisha |  | 2024-11-20 | 2024-11-20 |  | check after cron is run | No1362_Properties_listing_company_owned_tag_Sharan_N_P_20_11_2024
1360 | 2024-11-15 | ISSUE | Comparable Tool | When the Property Type "Unknown" option is selected, it displays all the properties within that postcode. Postcode : EN1 1HD |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-20 | 2024-11-20 | 2024-11-22 |  | No1360_Comparable_tool_unknown_Sharan_N_P_20_11_2024
1361 | 2024-11-15 | ISSUE | Price Drop | Company owned tag in listing page, but not in detail page 31 Hartismere Road, Wallasey, CH44 9DT | Web | SHARAN | NOT STARTED | LOW | Aayisha |  | 2024-11-20 | 2024-11-20 |  | check after cron is run | No1362_Properties_listing_company_owned_tag_Sharan_N_P_20_11_2024
1362 | 2024-11-15 | ISSUE | Sold- Under offer | Company owned tag in listing page, but not in detail page 19, Casterton Road, Stamford, South Kesteven, Lincolnshire, PE9 2YL | Web | SHARAN | NOT STARTED | LOW | Aayisha |  | 2024-11-20 | 2024-11-20 |  | check after cron is run | No1362_Properties_listing_company_owned_tag_Sharan_N_P_20_11_2024
1363 | 2024-11-15 | ISSUE | Planning Application | Agent name and address repeating . Council Name : Wokingham https://www.awesomescreenshot.com/image/51580242?key=766cce7bd3ec79cc84ebde0dfa3db422 |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-11-19 | 2024-11-19 | 2024-11-22 |  | No1363_Planning_applications_agent_duplicate_Sharan_N_P_19_11_2024
1364 | 2024-11-18 | UK TEAM | Report | Delete the property Image without seclect a thumbnail |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-19 | 2024-11-19 | 2024-11-22 |  | No1364_report_delete_primary_image_Sharan_N_P_19_11_2024
1365 | 2024-11-19 | ISSUE | Comparable Tool | The "Price From" and "Price To" fields accept multiple full stops and commas, and there is no limit to the digits that can be entered. should accept only numbers |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-26 | 2024-11-26
1366 | 2024-11-20 | ISSUE | Detail Page | its given last sold date but its written last sold year https://prospectingtool.letsbidproperty.co.uk/properties/p-3254644 https://prospectingtool.letsbidproperty.co.uk/properties/p-3254645 |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-26 | 2024-11-26 | 2024-12-05 |  | No1366_details_last_sold_date_Sharan_N_P_26_11_2024
1367 | 2024-11-20 | ISSUE | Report | getting a warning pop up when we click on some addresses in the Sold comparable list 59, Warren Road, Worthing, BN14 9QN - when we select 28, A'becket Gardens, Worthing, West Sussex BN13 2BW |  | SHARAN | COMPLETED | HIGH |  |  | 2024-11-20 | 2024-11-20 | 2024-11-22 |  | No1367_Report_sold_comparable_datatable_warning_Sharan_N_P_20_11_2024
1368 | 2024-11-20 | ISSUE | Letter management | When side panel is enabled when editing letter the page refreshes, content changes |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-10 | 2024-12-10 | 2024-12-24 |  | No1368_Letter_mngmt_trigger_Sharan_N_P_09_12_2024
1369 | 2024-11-20 | DISCUSS | Report | for off market reports, do we need to show the current market price, bedroom and bathroom |  | RIJO | CLOSED | LOW
1370 | 2024-11-20 | SUGGESTION | Comparable Tool | If no properties are available across all three comparables, please display a warning message stating, "No properties available." show a default message No properties available for the selected filters. | Web | SHARAN | APPROVAL | LOW |  |  | 2024-12-24 | 2024-12-25 |  |  | No1370_Comparable_tool_empty_case_Sharan_N_P_24_12_2024
1371 | 2024-11-19 | UK TEAM | Report | Key information list when generating report - we will display the data and the agents will have the option to edit these data, if no data is available we will show - or NA in the report |  | RIJO | DUPLICATE TASK | MEDIUM
1371 | 2024-11-19 | UK TEAM | Report | Key information list when generating report - we will display the data and the agents will have the option to edit these data, if no data is available we will show - or NA in the report | Web | RIJO | NOT STARTED | MEDIUM
1373 | 2024-11-19 | ISSUE | Postcard | 20-20 targeted and 20-20 postcards - when postcards are being sent to multiple addresses, the addresses are not greyed out like the rest when processing |  | SANDEEP | COMPLETED | MEDIUM
1374 | 2024-11-19 | TASK | Targeted Properties | Muliple seclection for year and property type | Web | SANDEEP | NOT STARTED | MEDIUM
1375 | 2024-11-20 | ISSUE | Report | in the On Market Comparable list only postcode is shown Apartment 42, 10, Arthur Place, Birmingham, West Midlands, B1 3DB - https://prospectingtool.letsbidproperty.co.uk/properties/p-2369544 https://tinyurl.com/2yvl6k2r | Web | SHARAN | DISCUSS | MEDIUM | [5 empty] | Need to confirm whether to add a text for incomplete addresses
1376 | 2024-11-20 | ISSUE | Report | ui issues in some pages: - neighbouring planning - some details are getting cropped at the bottom - planning data - the font size is not similar to the neighbouring page - market analysis - the boxes doesn't look aligned - property type analysis - the boxes around the types look incomplete - on market comparables - the data gets cropped at the bottom in some reports - primary/secondary schools - the text size for pupils etc looks too big - university: align the icon and heading in the title section - university - reduce the font size of miles |  | SATHEESH | COMPLETED | MEDIUM
1377 | 2024-11-20 | ISSUE | Report | title number is not correct 116a, St. Marks Road, Enfield, Greater London, EN1 1BB - showing the title number of 116 EN1 1BB 205, Station Street, Burton-on-Trent, Staffordshire, DE14 1AN |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-02 | 2024-12-02 | 2024-12-05 | updated Nov 3: checked few other addresses but the title number is not correct 1, Moulton Rise, Luton, Bedfordshire, LU2 0AF - in live it's correct | No1377_Report_title_number_duplicate_Sharan_N_P_02_12_2024
1378 | 2024-11-20 | ISSUE | 20-20 Targeted Campaign | bulk mail - addresses are repeating in stannp | Web | SANDEEP | TESTING | HIGH | [5 empty] | to check after #1291 is made live -------- updated Nov 27: addresses are repeating in stannp | no1378-t20targeted-stannp-issue-sandeep-29nov2024
1379 | 2024-11-21 | ISSUE | Withdrawn | showing server error when we click on some addresses /Controllers/PropertyController.php(3943): Illuminate\\Database\\Eloquent\\Builder->where() rs/PropertyController.php(822): App\\Http\\Controllers\\PropertyController->removeTypeFromHistory() https://prospectingtool.letsbidproperty.co.uk/properties/w-47120 |  | SANDEEP | COMPLETED | HIGH |  |  | 2024-11-21 |  | 2024-11-21
1380 | 2024-11-21 | ISSUE | Report | transport page - when airport, train, bus, underground stations and tram datas are available, trams are not shown in the pdf https://prospectingtool.letsbidproperty.co.uk/view-report/report_12137_031220241134861837.pdf |  | SATHEESH | CLOSED | MEDIUM |  |  | 2024-12-09 | 2024-12-09 |  | 9 Dec 2024 Tram will display if data have try with other address Sample tram data available https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_12137_051220240909452813.pdf
1381 | 2024-11-21 | ISSUE | Report | for some addresses the postcode is shown in multiple lines even though there is space in primary, secondary and universities & colleges |  | RIJO | COMPLETED | MEDIUM
1382 | 2024-11-21 | TASK | Company Owned | Cron : Collect the Company owned details and store into db based on properties |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-21 | 2024-11-23 | 2024-12-05 | 23/11/2024 Need developer tesing only | No1331_Report_company_owned_tag_Sharan_N_P_21_11_2024
1383 | 2024-11-21 | ISSUE | Vonage SMS | Vonage error Exception fail : Missing to param, Exception fail : Undefined variable $userOutcode |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-21 | 2024-11-21 | 2024-11-21 | To Approval | No1383_vonage_sms_exception_Sharan_N_P_21_11_2024
1384 | 2024-11-21 | ISSUE | Planning Application | Incorrect Council name 1. Bristol City of 2. Blackburn with Warwen , Correct name is Blackburn with Darwen | Data | SHARAN | NOT STARTED | LOW | Aayisha |  |  |  |  | Mail send for confirmation of wording
1385 | 2024-11-21 | ISSUE | Comparable Tool | The "Price From" and "Price To" columns are exhibiting some issue. https://www.awesomescreenshot.com/image/51698825?key=e3c0ec8037b4653e48dd638d3c09cf7d When the "Next Page" option is selected, the content of the next page is loaded in the lower portion of the screen. However, the upper portion of the next page should be displayed. https://www.awesomescreenshot.com/image/51737962?key=dabfec27095267c407f61900b23622a7 |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-11-25 | 2024-11-25 | 2024-11-27 |  | No1385_comparable_tool_price_field_error_Sharan_N_P_25_11_2024
1386 | 2024-11-19 | ISSUE | Wallet/Credit | Negative balance issue |  | RIJO | COMPLETED | HIGH |  |  |  |  | 2024-12-05 | update : 21-11-2024 check active buyer section in demo ------------------------- updated Nov 21: active buyer - working | no1486_negative_balance_issue_Rijo_20nov2024
1387 | 2024-11-22 | SUGGESTION | Active Buyer | option to add the address to campaign from the listing page itself, we have to click on an address first and then add to campaign |  | RIJO | CLOSED | LOW
1388 | 2024-11-22 | ISSUE | Report | last page - the boxes around the logos look incomplete | UI | SATHEESH | NOT STARTED | LOW
1389 | 2024-11-22 | ISSUE | Report | when generating a report, the info text gets cropped when the user scrolls https://tinyurl.com/25mena4u |  | SHARAN | COMPLETED | LOW |  |  | 2024-11-25 | 2024-11-25 | 2024-11-27 |  | No1389_report_info_content_Sharan_N_P_25_11_2024
1390 | 2024-11-22 | ISSUE | Properties | listing date issue: the listed date is shown as 06 Sep 2024 but in RM/Z the listed date is in August https://prospectingtool.letsbidproperty.co.uk/properties/b-3001547 property was withdrawn in october and listed back in october but the previous listings in october are greyed out https://prospectingtool.letsbidproperty.co.uk/properties/p-2895666 |  | UNASSIGNED | CLOSED | HIGH
1391 | 2024-11-22 | ISSUE | Listing Page | sort by price is not correct *Properties *Withdrawn *Pricedrop *Backtomarket *Soldunderoffer |  | SANDEEP | COMPLETED | HIGH |  |  |  |  | 2024-11-27 |  | no1391-sort-by-price-issue-sandeep-26nov2024
1392 | 2024-11-22 | UK TEAM | Letter management | content overlapping Reference address, line height was too much |  | RIJO | COMPLETED | MEDIUM
1393 | 2024-11-25 | SUGGESTION | Report | Key details - for planning application, if no application is available instead of Nil show - | Web | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-24 | 2024-12-24 | 2024-12-31 |  | No1393_Report_key_details_planning_Sharan_N_P_24_12_2024
1394 | 2024-11-25 | UK TEAM |  | ROI work | Web | RIJO | DISCUSS
1395 | 2024-11-25 | UK TEAM | Report | Interactive reports – If comps need to go over 2 pages pr more make sure the map is on all pages. | Web | RIJO | DISCUSS |  |  | 3 days
1396 | 2024-11-26 | ISSUE | Planning Application | The name starts with a lowercase letter, but it should be capitalized. https://www.awesomescreenshot.com/image/51751101?key=fda198b3bacdde6e6204bf60341a2786 |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-29 | 2024-11-29 | 2024-12-05 |  | No1396_Planning_letter_capital_Sharan_N_P_29_11_2024
1397 | 2024-11-26 | ISSUE | Report | change the count to 8 in the comparable pop ups Sold Comparable Additional Property Comparables On Market Rental Comparables |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-11-27 | 2024-11-27 | 2024-12-05 |  | No1397_Report_comparable_count_change_Sharan_N_P_27_11_2024
1398 | 2024-11-26 | ISSUE | Report | If the property is not company-owned, explicitly specify it instead of using a hyphen ("-"). https://www.awesomescreenshot.com/image/51760096?key=f3dc54f774875dbe07871f40e1aea49b https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14362_261120241118635734.pdf |  | SHARAN | CLOSED | LOW | Aayisha
1399 | 2024-11-26 | ISSUE | Anniversary Letter | When creating a new sold property, upon selecting a date from the date picker, the date picker should close automatically after the selection. However, it remains open instead of dismissing as expected. When we click outside the pop-up box, it closes. This behavior should be modified so that the pop-up box only closes when the "Close" or "Save" button is clicked. |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-11-29 | 2024-11-29 | 2024-12-05 |  | No1399_Anniversary_letter_datepicker_Sharan_N_P_29_11_2024
1400 | 2024-11-27 | ISSUE | Listing Page | Postcode given "Unknown" Flat 208, 1 Merino Gardens, London, E1W 2DF https://www.awesomescreenshot.com/image/51782530?key=f17f7442f2a4da1b8c52e5f662c29ba7 | Data | DATA TEAM | DISCUSS | HIGH | Aayisha |  | 2024-11-28 | 2024-11-28 |  | 28 Nov 2024 Issue in data engine side reported to data team
1401 | 2024-11-27 | ISSUE | 20-20 Campaign | bulk mail - addresses are repeating in stannp |  | SANDEEP | TESTING | HIGH |  |  |  |  | 2024-12-19 | updated Dec 2: local print - the edit address keeps loading | no1378-t20targeted-stannp-issue-sandeep-29nov2024
1402 | 2024-11-27 | ISSUE | Direct Mail Anywhere | bulk mail - addresses are repeating in stannp | Web | SANDEEP | IN PROGRESS | HIGH | [6 empty] | no1378-t20targeted-stannp-issue-sandeep-29nov2024
1403 | 2024-11-28 | ISSUE | 20-20 Campaign | In the 20-20 campaign, when using the postcard feature, if multiple addresses are selected and the edit option is chosen, the edit icon does not appear. | Web | RIJO | NOT STARTED | MEDIUM | Aayisha
1404 | 2024-11-28 | ISSUE | Sold- Under offer | stc/offer date sort is not correct | Web | SANDEEP | IN PROGRESS | MEDIUM |  |  | 2024-12-30 |  |  | updated Dec 30: - sort by price is not correct ---------------------- updated Jan 2: - sort by sold/under offer date is not correct ---------- updated Jan 7: - sort by sold/under offer date is correct but sort by price is not correct (it works in live)
1405 | 2024-11-28 | ISSUE | Summary | counts are not correct: - total campaign count is not correct - second instruction: count for local print and bulk mail is not correct | Web | SANDEEP | NOT STARTED | MEDIUM
1406 | 2024-11-28 | ISSUE | Summary | in the selected tab, the highlight and the count does not look aligned https://tinyurl.com/2xqtg7wu |  | SANDEEP | DUPLICATE TASK | MEDIUM
1407 | 2024-11-28 | ISSUE | 20-20 Targeted Campaign | In the 20-20 targeted campaign, when using the postcard feature, if multiple addresses are selected and the edit option is chosen, the edit icon does not appear. | Web | RIJO | NOT STARTED | MEDIUM | Aayisha
1408 | 2024-11-29 | ISSUE | Withdrawn | The property type is not available on the listing page, but it is displayed on the detail page. https://www.awesomescreenshot.com/image/51808790 https://www.prospectingtool.letsbidproperty.co.uk/properties/w-2704243 https://www.prospectingtool.letsbidproperty.co.uk/properties/w-530923 |  | SHARAN | CLOSED | LOW | Aayisha
1409 | 2024-11-29 | ISSUE | Report | In the report, the "Valid Until" date is listed as one day later than the date provided on the EPC site. 5, Spring Glen, Hatfield, AL10 8HD https://www.awesomescreenshot.com/image/51812078?key=42128a179259046b9cfd82c3cafca3ac https://www.awesomescreenshot.com/image/51812111?key=619108837e54ac6d26056eae3171dffe | Web | SHARAN | CLOSED | LOW | Aayisha |  | 2024-12-24 | 2024-12-24 |  | Nothing to do
1410 | 2024-11-28 | ISSUE | Report | neighboring planning - if the planning application is less than 6 the image shown is very prominent, please make the image lighter |  | RIJO | COMPLETED | MEDIUM
1411 | 2024-12-02 | ISSUE | Report | EPC Certificate Number exceeding box EPC energy rating add br tag |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-12-02 | 2024-12-02 | 2024-12-10 |  | No1409_Report_epc_certificate_number_overlaps_box_Sharan_N_P_02_12_2024
1412 | 2024-12-03 | ISSUE | Outcodes | Need to remove few suggestions under dropdown Gre Zimba JMBT Argent DH22 O CO NOR SP cyp sk gre x2 https://drive.google.com/file/d/1fU_1GSf05-L6D809NfzbxWoYhY4Xkqmw/view?usp=sharing |  | SHARAN | COMPLETED | MEDIUM | Linta |  | 2024-12-03 | 2024-12-05 | 2024-12-10 |  | No1412_Outcodes_select_valid_outcodes_Sharan_N_P_03_12_2024
1413 | 2024-12-03 | ISSUE | Live campaign | Receiving random error pop-up messages. https://www.awesomescreenshot.com/image/51855572?key=d14dc278cdd700fcb0b9d70b6b6c364d | Web | RIJO | NOT STARTED | LOW | Aayisha
1414 | 2024-12-03 | ISSUE | Withdrawn | -Properties which is sold STC,on market are listed under withdrawn https://www.prospectingtool.letsbidproperty.co.uk/properties/w-3099259 https://www.rightmove.co.uk/properties/152856086#/?channel=RES_BUY https://www.prospectingtool.letsbidproperty.co.uk/properties/w-2596579 Flat 1003, 1A Spinners Way, Manchester, M15 4UY 24 Augustus Way, Manchester, M15 5PP 18, Sugar Mill Square, Salford, Greater Manchester, M5 5EB 24 Nash Street, Manchester, M15 5NZ -There is a difference in price displayed https://www.prospectingtool.letsbidproperty.co.uk/properties/w-2596579 https://www.zoopla.co.uk/for-sale/details/66907035/ | Web | RIJO | NOT STARTED | MEDIUM | Linta
1415 | 2024-12-03 | ISSUE | Settings | Need to remove dot and space for the message 'profile updated successfully' https://drive.google.com/file/d/1t2Q3Rkt0_-1edezRYc0xDgSPQBuzt2hk/view?usp=drive_link |  | SHARAN | COMPLETED | LOW | Linta |  | 2024-12-18 | 2024-12-18 | 2024-12-24 |  | No1415_Alert_msg_style_correction_Sharan_N_P_18_12_2024
1416 | 2024-12-03 | ISSUE | Back to Market | properties that are not supposed to be under back to market gets removed from the listing only after we go into the detail page and then refresh | Web | SANDEEP | NOT STARTED | MEDIUM
1417 | 2024-12-03 | ISSUE | Detail Page | Align all headings in Sold Property comparables uniformly to maintain a neat and professional layout . https://www.awesomescreenshot.com/image/51864354?key=8e7429b1c32b9926793f9817627bf347 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3260493 | Web | SHARAN | APPROVAL | LOW | Aayisha |  | 2024-12-30 | 2024-12-30 |  |  | No1417_Details_page_comparable_layout_Sharan_N_P_30_12_2024
1418 | 2024-12-04 | ISSUE | Notification | Redesign the error pages like 404 and 500 | Web | RIJO | NOT STARTED | LOW
1419 | 2024-12-04 | ISSUE | Price Drop | The property sold history is missing on the detail page of LetsBid but is available on Zoopla. https://www.prospectingtool.letsbidproperty.co.uk/properties/d-3060747 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3268941 | Data | SHARAN | NOT STARTED | LOW | Aayisha
1420 | 2024-12-04 | ISSUE | Price Drop | Not every time, but occasionally, when we click on "List of Agents" in the detail pages, it simply reloads the page. However, when we try again, it displays the list of agents. | Web | SHARAN | CLOSED | LOW | Aayisha
1421 | 2024-12-04 | TASK |  | New Home removal from MYSQL database |  | RIJO | TESTING | HIGH
1422 | 2024-12-04 | ISSUE | Live campaign | was able to send letters to invalid addresses targeted active buyer planning | Web | SANDEEP | NOT STARTED | MEDIUM |  | 16 hrs |  |  |  | check if postcode is available in edit address
1423 | 2024-12-04 | SUGGESTION | Report | do we need to show the decimals for sqft? | Web | RIJO | DISCUSS | LOW
1424 | 2024-12-05 | ISSUE | Report | planning data on property - the reference number goes outside the box 25, Henrietta Street, Coventry, CV6 5EF |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-06 | 2024-12-06 | 2024-12-10 |  | No1424_Report_planning_referene_number_Sharan_N_P_06_12_2024
1425 | 2024-12-05 | DISCUSS | DMA Campaign | When properties are selected and added to a campaign, the screen refreshes, and the postcode field becomes empty. |  | SHARAN | DUPLICATE TASK | LOW | Aayisha
1426 | 2024-12-05 | ISSUE | Targeted Properties | Address in single line |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-12-05 | 2024-12-05 | 2024-12-10 |  | No1427_Targeted_address_alignment_Sharan_N_P_05_12_2024
1427 | 2024-12-05 | ISSUE | Listing Page | The "Company Owned" tag is visible in the live campaign but not on the property listing or detail page. https://www.awesomescreenshot.com/image/51899418?key=5d054f9f1d845aad880e854ffb11640a https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3219247 | Web | SHARAN | NOT STARTED | LOW | Aayisha |  |  |  |  | To check after cron run is completed
1428 | 2024-12-05 | ENHANCEMENT | Detail Page | Reduce the font size of the title and increase the font size of the address. | Web | SHARAN | DISCUSS | LOW | Aayisha
1429 | 2024-12-05 | ISSUE | Detail Page | Update the bedroom and bathroom icons and adjust their alignment to match the layout on Rightmove. https://www.awesomescreenshot.com/image/51906905?key=43418785c343049d7728597fbd404f52 | Web | ANISHA | APPROVAL | LOW | Aayisha | [5 empty] | no1429_detailpage_bedroom_bathroom_icon_Anisha02Jan
1430 | 2024-12-05 | ISSUE | Planning Application | in campaign tag is shown in the listing only after refreshing the page |  | SHARAN | COMPLETED | MEDIUM |  |  | 2024-12-06 | 2024-12-06 | 2024-12-10 |  | No1430_Planning_applications_campaign_tag_Sharan_N_P_06_12_2024
1431 | 2024-12-05 | SUGGESTION | Live campaign | Replace the option 'print' with 'open PDF' in local print https://www.awesomescreenshot.com/image/51910357?key=22833cc5a5a9878cb8295e40c257dd04 | Web | SHARAN | COMPLETED | LOW | Aayisha | 1 hr | 2024-12-18 | 2024-12-18 | 2024-12-31 |  | No1431_Letter_open_popup_Sharan_N_P_18_12_2024
1432 | 2024-12-05 | ISSUE | Active Buyer | The addresses in the transacted property list are being duplicated. https://www.awesomescreenshot.com/image/51918284?key=b38ff0d3f7cd9b932dc45e8fb917db40 | Data | DATA TEAM | NOT STARTED | LOW | Aayisha |  |  |  |  | Transction table needs to be updated - Sharan please send a mail
1433 | 2024-12-06 | ISSUE | Quick Send | dashboard - quick send in dashboard is not working, it's showing no properties in live. |  | RIJO | COMPLETED | HIGH
1434 | 2024-12-06 | ISSUE | Detail Page | Detail page quick send - credits are available but it shows low balance message |  | RIJO | COMPLETED | HIGH
1435 | 2024-12-06 | ISSUE | Live campaign | Credits shown in the folllowing campaign are not correct, we are showing the amount instead of credits - detail page quick send - 20-20 - 20-20 targeted |  | RIJO | COMPLETED | HIGH
1436 | 2024-12-06 | UK TEAM | Summary | report summary - the links have been opened but the details are not shown in the summary section the report details are not shown when there are no other data in the summary page |  | SANDEEP | COMPLETED | HIGH |  |  |  |  | 2024-12-10 |  | LE-summary-sub-10dec2024
1437 | 2024-12-06 | TASK |  | stamp duty rate change |  | RIJO | TESTING | HIGH
1438 | 2024-12-09 | ISSUE | Targeted Properties | The following address has an invalid postcode, and neighboring areas could not be found. https://www.awesomescreenshot.com/image/51951131?key=d6d1f90f4f4a91ad9411285ed5b571c9 26, Bernard Street, St. Albans, St Albans, Hertfordshire, AL3 5QN | Web | SHARAN | TESTING | LOW | Aayisha |  | 2024-12-18 | 2024-12-18 | 2024-12-24
1439 | 2024-12-09 | ISSUE |  | update the bedroom and bathroom icons and adjust their alignment to match the layout on Rightmove. https://www.awesomescreenshot.com/image/51906905?key=43418785c343049d7728597fbd404f52 |  |  | DUPLICATE TASK
1440 | 2024-12-09 | TASK |  | design - improve ui for auction listing and detail page refer iamsold.co.uk | UI | SATHEESH | IN PROGRESS | HIGH
1441 | 2024-12-09 | TASK |  | iframes api - listing all properties on the agents website | Web |  | DISCUSS | MEDIUM
1442 | 2024-12-09 | ISSUE | Targeted Properties | Need to change the text 'Group' to 'range' https://drive.google.com/file/d/1d_kz8Jked89IMYcLlcdUA1cUYYDtPxBA/view?usp=drive_link |  | SHARAN | COMPLETED | LOW | Linta |  | 2024-12-10 | 2024-12-10 | 2024-12-10 |  | No1442_Targeted_Selected_filter_tag_Sharan_N_P_10_12_2024
1443 | 2024-12-09 | DISCUSS | Probate Detail | Property type is displayed as terraced in land registry but the comparables displayed in detail page is of ''detached' https://www.prospectingtool.letsbidproperty.co.uk/probate-property-details/p-eyJpdiI6IlFCQUJNSmNKS1pIL3FjQ2pFZmg2Y2c9PSIsInZhbHVlIjoiSEh0UEg1RStXMzR0b21BbHpVSlFzZz09IiwibWFjIjoiODBkOWFlYWQxYjQ1YmM1M2FkMWFhMzhkMTNkNWY0OWZjZGU0ZDQwNzQyNzE0NmQxNzMwYmI1MmQ2ZjQxYWEyNiIsInRhZyI6IiJ9 31 Orchardleigh Avenue, Enfield, EN3 5BG | Web | SHARAN | NOT STARTED | LOW | Linta | 8 hrs
1444 | 2024-12-09 | UK TEAM | Summary | the report details are not shown when there are no other data in the summary page |  |  | DUPLICATE TASK | HIGH
1445 | 2024-12-10 | DISCUSS | Report | planning data - For neighbouring planning, do we need to show the applications nearest to the postcode or sort according to the latest decision issued date? 2, Berkley Avenue, Blaydon-On-Tyne, Gateshead, Tyne And Wear, NE21 5NQ when checked in the council wesbite there were properties in NE21 5NQ | Web | RIJO | DISCUSS | MEDIUM |  | 8 hrs
1446 | 2024-12-10 | ISSUE | Detail Page | sold history - the data is repeating https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3275095 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3277056 https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3225609 |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-10 | 2024-12-10 | 2024-12-19 |  | No1446_Details_page_sold_data_repeating_Sharan_N_P_10_12_2024
1447 | 2024-12-10 | ISSUE | Report | The bathroom count is not available on the report page but is displayed on the detail page. 100, Calley Down Crescent, Croydon, CR0 0EG - https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14579_101220240710170179.pdf Flat 28, Cuff Point, Columbia Road, London, Tower Hamlets, London, E2 7PP https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_711_121220240632400229.pdf | Web | SHARAN | NOT STARTED | MEDIUM | Aayisha | 4hrs
1448 | 2024-12-10 | ISSUE | Targeted Properties | addresses are repeating in the listing |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-10 | 2024-12-10
1449 | 2024-12-10 | ISSUE | Targeted Properties | Letter sent count in targeted listing | Web | SHARAN | TEST DEMO | HIGH |  |  | 2024-12-11 | 2024-12-11 |  | updated Dec 11: - on viewing the campaign history, the campaign details are not shown https://tinyurl.com/22dsnlc9 -------------------------------------- Updated Dec 18: - targeted 20-20 campaign and postcard details are not shown when we click on View, only the count is shown - targeted 20-20 and postcard campaign history is not shown in the history section in the detail page - campaign history missing in the pop up | No1449_Targeted_listing_letter_count_Sharan_N_P_10_12_2024
1450 | 2024-12-11 | ISSUE | Live campaign | Incorrect address handling property address : Land Adjacent To The Black Horse Inn The Street Thorndon Eye Suffolk IP23 7JR Agent address: Church Farm Barn The Street Thorndon IP23 7JR |  | SANDEEP | COMPLETED | HIGH | Aayisha |  |  |  | 2024-12-19 |  | no1450-incorrect-address-planning-sandeep-11dec2024
1451 | 2024-12-11 | DEMO | Targeted Properties | There are no neighboring properties, and the postcode is invalid; however, the property was successfully added to the 20-20 campaign. 50, Cannon Street Road, London, Tower Hamlets, E1 0B Flat 18, Betts House, Betts Street, London, Tower Hamlets, E1 8HN Flat 4, 228, Cable Street, London, Tower Hamlets, E1 0DR Flat 2, Mariana Court, 29, Assembly Passage, London, Tower Hamlets, E1 4GQ |  | SHARAN | TESTING | MEDIUM | Aayisha |  | 2024-12-12 | 2024-12-13 | 2024-12-24 |  | No1451_Targeted_20_20_neighbour_Sharan_N_P_12_12_2024
1452 | 2024-12-11 | ISSUE | Targeted Properties | property type https://www.awesomescreenshot.com/image/52000878?key=a0be966bdb13d7743dbf882784e775db |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-12-11 | 2024-12-11 | 2024-12-19 |  | No1452_Targeted_properties_property_type_Sharan_N_P_11_12_2024
1453 | 2024-12-11 | ISSUE | Planning Application | In reserved total pages are 4(entries are 50) ,extension contains 21 pages when we click both extension and reserved it displays only 16 pages | Web | SHARAN | NOT STARTED | MEDIUM | Linta
1454 | 2024-12-12 | ISSUE | Targeted Properties | while selecting property type in filter there is no space in between Data table warning message is displayed while selecting filter |  | SHARAN | COMPLETED | HIGH | Linta
1455 | 2024-12-12 | ISSUE | Live campaign | Was able to send letters and postcard even when we don't have enough balance |  | RIJO | COMPLETED | HIGH |  |  |  |  | 2024-12-17 |  | no1486_negative_balance_issue_Rijo_20nov2024
1456 | 2024-12-12 | ISSUE | Targeted Properties | Few properties are repeating |  | SHARAN | DUPLICATE TASK | MEDIUM | Linta
1457 | 2024-12-12 | ISSUE | Summary | when we change the date filter, please make sure the month shown beside also changes accordingly https://tinyurl.com/2chaqh3n |  | ANISHA | COMPLETED | MEDIUM |  | 1 hr | 2024-12-23 | 2024-12-23 | 2024-12-24 |  | no1457_date_filter_summary_Anisha23Dec
1458 | 2024-12-12 | ISSUE | Anniversary Letter | There is unnecessary white space in the address suggestion box, obstructing the "Cancel" and "Add Property" buttons. https://www.awesomescreenshot.com/image/52016005?key=d5ef7da4725f01693788847395ccfa8c |  | SHARAN | COMPLETED | LOW | Aayisha | 1 hr | 2024-12-18 | 2024-12-18 | 2024-12-19 |  | No1458_Anniversary_address_suggestion_Sharan_N_P_18_12_2024
1459 | 2024-12-12 | ISSUE | Listing Page | when we filter the targeted listing with min and max price, all the other listings also gets filterd |  | SANDEEP | COMPLETED | HIGH |  | 1 day | 2024-12-12 | 2024-12-13 | 2024-12-19 | updated Dec 19: - Withdrawn listing gets filtered with the min and max price from targeted listing | no1463-filter-session-issue-sandeep-12dec2024
1460 | 2024-12-12 | ISSUE | Listing Page | the weeks and bedroom filters given in All properties/filter by weeks listing is automatically applied to withdrawn/back to market/price drop pages and vice versa |  | SANDEEP | COMPLETED | HIGH |  | 1 day | 2024-12-12 | 2024-12-13 | 2024-12-17 | updated Dec 19: - week filter applied in withdrawn gets applied to all properties - the week filter in all properties and filter by listings gets applied to Withdrawn | no1463-filter-session-issue-sandeep-12dec2024
1461 | 2024-12-12 | ISSUE | Letter management | text is overlapping the side panel |  | SHARAN | COMPLETED | LOW | Linta | 1 hr | 2024-12-18 | 2024-12-18 | 2024-12-24
1462 | 2024-12-12 | ISSUE | Listing Page | while selecting property type,contacted in filter there is no space in between Back to market https://drive.google.com/file/d/1DtOlRZBGvOH2lw3Qz0f7KMj2Uf_3HAOL/view?usp=drive_link |  | SANDEEP | COMPLETED | MEDIUM | Linta | 1 day | 2024-12-12 | 2024-12-13 | 2024-12-17 |  | no1463-filter-session-issue-sandeep-12dec2024
1463 | 2024-12-12 | ISSUE | Listing Page | After applying a filter and returning from the detail page to the listing, the filter is removed All properties,filter by,Withdrawn,back to market-property type,price Sold/under offer-all filters are removed Price drop |  | SANDEEP | COMPLETED | HIGH | Linta | 1 day | 2024-12-12 | 2024-12-13 | 2024-12-17 | updated Dec 19: - not cleared in Withdrawn | no1463-filter-session-issue-sandeep-12dec2024
1464 | 2024-12-12 | ISSUE | Listing Page | When the "Clear Filter" action is triggered, the search input field is not reset. |  | SANDEEP | TESTING | MEDIUM | Aayisha | 1 day | 2024-12-12 | 2024-12-13 | 2024-12-17 | updated Dec 30: - not working in withdrawn, back to market | no1463-filter-session-issue-sandeep-12dec2024
1465 | 2024-12-13 | ISSUE | Anniversary Letter | The error message displayed when a trigger is not selected has grammatical errors. The correct message should be "Select an anniversary trigger from the list". https://www.awesomescreenshot.com/image/52034227?key=8283f516d94dd5d91572e356b5483e0e |  | SHARAN | COMPLETED | LOW | Aayisha | 1 hr | 2024-12-18 | 2024-12-18 | 2024-12-19 |  | No1465_Anniversary_trigger_select_msg_Sharan_N_P_18_12_2024
1466 | 2024-12-13 | ISSUE | Price Drop | Price Drop section is experiencing significant delay in loading |  | SANDEEP | COMPLETED | HIGH | Aayisha | 1 day | 2024-12-13 |  | 2024-12-17 |  | no1466-pricedrop-loading-issue-sandeep-16dec2024
1467 | 2024-12-16 | ISSUE | DMA Campaign | Address repeating in postcode : E1 3JH https://www.awesomescreenshot.com/image/52065536?key=c587bd14ff16675e8b2ea091a2947694 |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-12-18 | 2024-12-18 | 2024-12-19 |  | No1467_DMA_suggestions_duplicates_Sharan_N_P_18_12_2024
1468 | 2024-12-16 | ISSUE | Report | Property Image Address : 2, Crooked Billet, London, SW19 4RQ https://www.awesomescreenshot.com/image/52068091?key=28a7029850c7487d1b7b663c5acc412c |  | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-12-18 | 2024-12-18
1469 | 2024-12-17 | ISSUE | Postcard | 20-20 and 20-20 targeted postcards - was able to send more than the available balance Steps to recreate: - select an address - click on show list - select few properties from the list, it should exceed the available balance - send bulk mail |  | RIJO | COMPLETED | HIGH |  |  | 2024-11-20 | 2024-12-20 | 2024-12-24 |  | no1486_negative_balance_issue_Rijo_20nov2024
1470 | 2024-12-17 | ISSUE | Probate properties | quick send - even if we have balance the letters are not going through |  | RIJO | COMPLETED | HIGH |  |  | 2024-11-20 | 2024-12-20 | 2024-12-24 |  | no1486_negative_balance_issue_Rijo_20nov2024
1471 | 2024-12-17 | ISSUE | Log Error | log error : https://www.prospectingtool.letsbidproperty.co.uk/log-viewer?file=f064571f-laravel-2024-12-17.log&query=log-index%3A4149 |  | SHARAN | COMPLETED | HIGH |  |  | 2024-12-17 | 2024-12-17 | 2024-12-24 |  | No1471_Log_error_cleaned_address_array_Sharan_N_P_17_12_2024
1472 | 2024-12-17 | ISSUE | Export csv | not working properly, when we select filters and export data is missing in the exported file check in all listing pages - if we have selected multiple filters, only the first property type is considered - if we filter the listing by Semi-Detached type, addresses that have the type Semi Detached (without -) are excluded from the exported file please check Semi-Detached bungalow, semi-detached house, semi detached, end of terrace, semi detached bungalow example - price drop: B16 - semi detached, detached --------------------------------------------------------- Check in: - All Properties - Filter by - Withdrawn - Back to market - Price drop - Sold/under offer |  | SANDEEP | COMPLETED | MEDIUM |  |  | 2024-12-19 | 2024-12-20 | 2024-12-24 |  | no1472-csv-export-issue-sandeep-19dec2024
1473 | 2024-12-17 | ISSUE | Withdrawn | property is on market/under offer but shown as Withdrawn Homewaters, Braintree Road, Felsted, Dunmow, CM6 3DY 44 Berry Hill Crescent, Cirencester, GL7 2HG 30, Chesterton House, Chesterton Lane, Cirencester, Cotswold, Gloucestershire, GL7 1XQ 26 Clappen Close, Cirencester, GL7 1WQ | Data | DATA TEAM | NOT STARTED | HIGH
1474 | 2024-12-17 | UK TEAM | Quick Send | Agents should be able to do local print even if they don't have balance to do quick send |  | RIJO | COMPLETED | HIGH |  |  | 2024-11-20 | 2024-12-20 | 2024-12-24 |  | no1486_negative_balance_issue_Rijo_20nov2024
1475 | 2024-12-18 | ISSUE | Detail Page | Floor plan image error https://www.prospectingtool.letsbidproperty.co.uk/properties/p-2595424 https://www.prospectingtool.letsbidproperty.co.uk/properties/b-2526929 Flat 37, Granville Point, Granville Road, London, Barnet, London, NW2 2LJ Flat 39, Hillsborough Court, Mortimer Crescent, London, Camden, London, NW6 5NS src=" https://www.foxtons.co.uk/properties-for-sale/nw2/chpk0317418/large_floorplan" |  | SHARAN | TESTING | LOW | Aayisha |  | 2024-12-23 | 2024-12-23 | 2024-12-24 |  | No1475_Detail_page_floor_image_error_Sharan_N_P_23_12_2024
1476 | 2024-12-18 | ISSUE | Properties | while filtering for 4-8 weeks all properties are not listing (CB25) | Web | SANDEEP | NOT STARTED | MEDIUM | Linta
1477 | 2024-12-18 | ISSUE | Targeted Properties | campaign history section in detail page - even if letters have been sent to an address, in the detail page the campaign details are not shown | Web | SHARAN | NOT STARTED | MEDIUM | [5 empty] | 23/12/2024 Sharan Sample address
1478 | 2024-12-19 | ISSUE |  | NEW HOMES - 150, Woodlands Park Drive, Dunmow, Uttlesford, Essex, CM6 1XZ - https://www.rightmove.co.uk/properties/155571413#/?channel=RES_NEW 1, The Causeway, Dunmow, Uttlesford, Essex, CM6 2AA - https://www.rightmove.co.uk/properties/155701766#/?channel=RES_NEW | Data | DATA TEAM | NOT STARTED
1479 | 2024-12-19 | ISSUE | 20-20 Campaign | Address repeating in Neighbouring Properties list Flat 4, 142 Worple Road, Raynes Park, SW20 8QA https://www.awesomescreenshot.com/image/52128454?key=41fdc8e69c19fa3168363cd1f6370bda |  | SHARAN | COMPLETED | MEDIUM | Aayisha |  | 2024-12-23 | 2024-12-23 | 2024-12-24 |  | No1479_20_20_campaign_address_issue_Sharan_N_P_23_12_2024
1480 | 2024-12-19 | ISSUE | Report | additional property comparables - are we not separating it by property type? |  | SHARAN | COMPLETED | LOW | [5 empty] | 23/12/2024 Sharan In new design not seperating by type
1481 | 2024-12-20 | ISSUE | Withdrawn | export csv not working properly, when we select filters and export data is missing in the exported file | Web | SANDEEP | NOT STARTED | MEDIUM
1482 | 2024-12-20 | ISSUE | Back to Market | export csv not working properly, when we select filters and export data is missing in the exported file | Web | SANDEEP | NOT STARTED | MEDIUM
1483 | 2024-12-20 | ISSUE | Price Drop | export csv not working properly, when we select filters and export data is missing in the exported file | Web | SANDEEP | NOT STARTED | MEDIUM
1484 | 2024-12-20 | ISSUE | Sold- Under offer | export csv not working properly, when we select filters and export data is missing in the exported file | Web | SANDEEP | NOT STARTED | MEDIUM
1485 | 2024-12-20 | ISSUE | Sold- Under offer | sold/under offer date shown in the listing and detail page is different 5, Fairlawn Road, Lytham St Annes, Fylde, Lancashire, FY8 5PT - https://www.prospectingtool.letsbidproperty.co.uk/properties/s-3257819 36, Redfern Way, Lytham St Annes, Fylde, Lancashire, FY8 2FN 2 Braidwood Court, 90 St Andrews Road North, Lytham St. Annes, FY8 2JT 67 Coppetts Road, London, N10 1JH 212, Alexandra Road, London, Barnet, London, N10 2ES | Web | SANDEEP | APPROVAL | HIGH |  |  | 2024-12-30 | 2024-12-30
1486 | 2024-12-20 | ISSUE | Sold- Under offer | if for sale and stc/under date is the same, stc is shown first 2 Victoria Avenue, Cheadle Hulme, Cheadle, SK8 5DL - https://www.prospectingtool.letsbidproperty.co.uk/properties/s-3291575 | Web | UNASSIGNED | NOT STARTED | MEDIUM
1487 | 2024-12-20 | ISSUE | Company Owned | check if the company details are correct 7, Langton Road, Kirkham, Preston, Fylde, Lancashire, PR4 2AR | Data | SHARAN | NOT STARTED | HIGH
1488 | 2024-12-23 | ISSUE | Detail Page | Alignment issue 10 Gillespie Place, Aberdeen, AB25 3BE https://www.awesomescreenshot.com/image/52176752?key=b9c85eaae6995fad9ed40aeed3cc1100 | Web | SHARAN | COMPLETED | LOW | Aayisha |  | 2024-12-24 | 2024-12-24 | 2024-12-24 |  | No1488_datatable_thead_align_Sharan_N_P_24_12_2024
1489 | 2024-12-23 | ISSUE | DMA Campaign | The "edit address" is not loading for local print https://www.awesomescreenshot.com/image/52177669?key=d85ba90382db551d2318652cb35aab9d |  | RIJO | COMPLETED | HIGH | Aayisha |  | 2024-12-23 | 2024-12-23 | 2024-12-23
1490 | 2024-12-24 | DISCUSS | Comparable Tool | on market comparable - do we need to show the under offer and stc tags | Web | SHARAN | DISCUSS
1491 | 2024-12-24 | ISSUE | Quick Send | detail page - the page keeps loading when we do quick send bulk mail | Web | RIJO | COMPLETED | HIGH
1492 | 2024-12-24 | ISSUE | Active Buyer Campaign | not able to send letters even if we have credits | Web | RIJO | NOT STARTED | HIGH
1493 | 2024-12-30 | ISSUE | Detail Page | for zoopla listing instead of floorplan we are showing the property images itself. | Data | DATA TEAM | NOT STARTED | HIGH
1494 | 2024-12-30 | ISSUE | Report | Bathroom and bedroom count not available in the report, but it is there in detail page, floor plan same as property image in detail page https://www.prospectingtool.letsbidproperty.co.uk/properties/p-3298960 https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14743_301220240551585289.pdf property is on market but when generating the report it's off market 3, Roe Green Lane, Hatfield, AL10 0SH | Data | VISHNU | NOT STARTED | LOW | Aayisha |  | 2024-12-30 | 2024-12-30 |  | 30 Dec 2024 Sharan Inform to Vishnu for update the mong db I think no need any code correction
1495 | 2024-12-30 | ISSUE | Back to Market | List of agents duplicating in detail page https://www.prospectingtool.letsbidproperty.co.uk/properties/b-2773018 https://www.awesomescreenshot.com/image/52245749?key=e48358fd8e9928fe189f368afbb154ea | Web | SANDEEP | CLOSED | LOW | Aayisha |  |  |  |  | - listings are different
1496 | 2024-12-30 | ISSUE | 20-20 Targeted Campaign | Address repeating in 20-20 Targeted campaign https://www.awesomescreenshot.com/image/52246312?key=d0005e353dfc3adc9095871b4e801173 | Web | SHARAN | APPROVAL | MEDIUM | Aayisha |  | 2024-12-30 | 2024-12-30 |  |  | No1496_Campaign_duplicates_Sharan_N_P_30_12_2024
1497 | 2024-12-30 | ISSUE | Properties | Address repeating https://www.awesomescreenshot.com/image/52246918?key=1de5a68d3fdc70907b047a7b0811b0e7 12 Martini Drive, Enfield, EN3 6GW 12, Martini Drive, Enfield, London, EN3 6GW | Web | SANDEEP | NOT STARTED | MEDIUM | Aayisha
1498 | 2024-12-30 | ISSUE | Targeted Properties | Need a space between the boxes https://drive.google.com/file/d/1dTpFdalvX6cugugBDEc1_lToITbznOtM/view?usp=drive_link | UI | RIJO | APPROVAL | LOW | Linta | [5 empty] | console_and_campaign_edits_Rijo_30dec24
1499 | 2024-12-30 | ISSUE | Active Buyer | Property is repeated (PE33) https://drive.google.com/file/d/1VLOEDUgzAS_cqRJjMMR_R8IWZqPi8Odj/view?usp=drive_link | Web | SHARAN | NOT STARTED | MEDIUM | Linta
1500 | 2024-12-30 | ISSUE | Listing Page | Filter by status - data shown for multi selection is not correct, data shown is based on the first selection | Web | SANDEEP | APPROVAL | MEDIUM |  |  | 2024-12-30
1501 | 2024-12-30 | ISSUE | Settings | Change password option is not working as expected | Web | SHARAN | IN PROGRESS | LOW | Aayisha |  | 2025-01-05 | 2025-01-06 |  | 06/01/2025 Sharan Change password option removed | No1501_Settings_change_password_option_hide_Sharan_N_P_05_01_2025
1502 | 2024-12-30 | ISSUE | Live campaign | style in all letter campaigns changed from anchor tag to normal | Web | RIJO | TEST DEMO | LOW | [6 empty] | console_and_campaign_edits_Rijo_30dec24
1503 | 2024-12-31 | ISSUE | Detail Page | the property title is not shown for zoopla properties 5, Claremont Road, Barnet, Enfield, London, EN4 0HR | Data | DATA TEAM | NOT STARTED | HIGH
1504 | 2024-12-31 | ISSUE | Report | epc - no data is shown for the Secondary Heating Efficiency and Floors if no data is available show - instead of leaving it blank | Web | SHARAN | NOT STARTED | MEDIUM
1505 | 2024-12-31 | ISSUE | Listing Page | filter by weeks listing - if we select mulitple weeks, the title shown is that of the listing which was selected by the user | Web | SANDEEP | NOT STARTED | MEDIUM
1506 | 2024-12-31 | ISSUE | Listing Page | when we filter the listing with multiple outcodes the loader is not shown, only when we select the first filter the loader is displayed | Web | SANDEEP | NOT STARTED | MEDIUM
1507 | 2025-01-02 | ISSUE | Listing Page | When the status is updated on the detail page, it is not reflecting on the listing page |  | SANDEEP | TEST DEMO | MEDIUM | Aayisha |  | 2025-01-03
1508 | 2025-01-02 | ISSUE | Report | for some off market properties we are getting the bed count but it's not shown in the report 4, South Drive, Worthing, West Sussex, BN12 5QS |  | SHARAN | NOT STARTED | MEDIUM
1509 | 2025-01-02 | ISSUE | Report | on market comparables - the tags are getting cropped for some https://tinyurl.com/2cu2yqt8 4, South Drive, Worthing, West Sussex, BN12 5QS` |  | SHARAN | NOT STARTED | MEDIUM
1510 | 2025-01-03 | ISSUE | Listing Page | -The property type is displayed as "link detached" on the listing page, but on the detail page, it is shown as "semi detached," "detached," or "unknown." -When filtering for "link detached house" properties, not all listings are filtered out because the term "house" is missing. -3 bedroom for sale,4 bedroom for sale,character property text are shown under property type in listing https://drive.google.com/file/d/12VAh-mSgvC47rPksSO8skYRJYjnfAFkN/view?usp=drive_link, https://drive.google.com/file/d/1R67IFksdCByHBZReU1vQ4E0YR9ie8fBs/view?usp=drive_link, https://drive.google.com/file/d/1O8oX8er35Jts6wPBaJvpYXr8BPOFWnUF/view?usp=drive_link, https://drive.google.com/file/d/1bG6rpHXPsoM2FnOdUA4gjzkHTstBpgvh/view?usp=drive_link | Web | SHARAN | NOT STARTED | MEDIUM | Linta
1511 | 2025-01-03 | ISSUE | Price Drop | Floor plan is not available on the detail page, but it is present on Zoopla and Rightmove https://www.prospectingtool.letsbidproperty.co.uk/properties/d-2844574 | Web | SHARAN | NOT STARTED | LOW | Aayisha
1512 | 2025-01-03 | ISSUE | Report | Can't generate report 3, Roe Green Lane, Hatfield, AL10 0SH | Web | SHARAN | COMPLETED | HIGH |  |  | 2025-01-03 | 2025-01-03 | 2025-01-03 |  | No1512_Report_generating_error_Sharan_N_P_03_01_2025
1513 | 2025-01-03 | ISSUE | Summary | qr codes scanned and qr froms completed data is not shown, only the count is shown if there is no data in the current month, even if we filter to the previous month that has data only the count is shown |  | SANDEEP | NOT STARTED | HIGH
1514 | 2025-01-06 | ISSUE | Letter management | when we enable/disable the Side Panel from the letter management listing, the content gets cleared |  | SHARAN | COMPLETED | URGENT
1515 | 2025-01-06 | ISSUE | Targeted Properties | if there are addresses that are already contacted, when we try to add the address again it just shows a blank pop up N10 B1 https://www.awesomescreenshot.com/image/52313030?key=ab8f63e365d87245b0d0c2f117b12110 |  | SHARAN | NOT STARTED | MEDIUM
1516 | 2025-01-06 | ISSUE | Properties | address issue for zoopla properties - latitude and longitude are shown with the address https://tinyurl.com/26bffpy3 AL10, M16 | Data | DATA TEAM | IN PROGRESS | URGENT
1517 | 2025-01-06 | DISCUSS |  | removing New tag in the menu for Property Report, Comparable tool, Census 2021 |  | RIJO | NOT STARTED | MEDIUM
1518 | 2025-01-06 | ISSUE | Report | The outline of the picture is displayed on the map under the planning data in the property section. https://www.prospectingtool.letsbidproperty.co.uk/view-report/report_14813_060120250607584484.pdf | Web | RIJO | NOT STARTED | MEDIUM | Linta
1519 | 2025-01-06 | ISSUE | Comparable Tool | Price/Sqft calculation is wrong https://www.awesomescreenshot.com/image/52316147?key=50adf6942eae4ee8b1765e3792d3f740 | Data | DATA TEAM | NOT STARTED | HIGH | Aayisha
1520 | 2025-01-06 | ISSUE | Campaign History | when no addresses are selected in the show list, the status displayed in the 20-20 targeted campaign history is "Sent" https://www.awesomescreenshot.com/image/52319887?key=aa13adbc949de63b64a6dfc48fbd6f6c |  | SANDEEP | NOT STARTED | LOW | Aayisha
1521 | 2025-01-06 | ISSUE | Report | bathroom count is missing in the report |  | SHARAN | NOT STARTED | MEDIUM
1522 | 2025-01-07 | ISSUE | Properties | properties without full address and only the outcode is shown in the listing EN10, CV3 |  | DATA TEAM | NOT STARTED | HIGH
1523 | 2025-01-07 | ISSUE | DMA Campaign | not able to send bulk mail, shows an error for Edit Address on inspecting |  | SANDEEP | NOT STARTED | HIGH
1524 | 2025-01-07 | ISSUE | DMA Campaign | local print - the addresses are shown in a single line https://tinyurl.com/24w3r6lf |  | SANDEEP | NOT STARTED | HIGH
1525 | 2025-01-07 | ISSUE | Summary | date filter - the years are overlapping https://tinyurl.com/297zo9re |  | SANDEEP | NOT STARTED | MEDIUM

## Lettings - TasksIssue Tracker
| Date | Task Type | Platform | Modules | Description | Team | Assigned | Status | Priority | Tester | Expected Duration | Start Date | End Date | Live Date | Required Hours | Comments | Branch Name | Tester
1 |  | Task |  | Admin |  |  | Rijo | Completed |  |  |  | 2023-10-26
2 |  | Task |  | Admin |  |  | Ashik | Completed
3 |  | Task |  | Admin |  |  | Ashik | Completed
4 |  | Task |  | Dashboard |  |  | Ashik | Completed
5 |  | Task |  | Dashboard |  |  | Ashik | Completed
6 |  | Task |  | Dashboard |  |  | Ashik | Completed
7 |  | Task |  | Property Report | Tenant Report - default selections should be content, epc, on market rental comparables, primary school, secondary school, universities and college, transportation, broadband, population, hospitals, carbon footprint, crime rates Landlord Report - default selections should be content, epc, market information, sold price on street, comparable property, on market comparable, on market rental comparable, planning data Estimate section text changes - Estimated Rental Value, Estimated Rental Range |  | Sharan | Completed |  |  |  | 2023-08-21 | 2023-08-22 |  |  |  | No_7_Property_report_21_08_2023_Sharan-N-P
8 |  | Task |  | Property Report |  |  | Ashik | Completed
9 |  | Task |  | Property Report |  |  | Ashik | Completed
10 |  | Task |  | Summary |  |  | Sharan | Completed
11 |  | Task |  | Summary |  |  | Not Assigned | Completed
12 |  | Task |  | Summary |  |  | Not Assigned | Completed
13 |  | Task |  | Outcodes |  |  | Ashik | Completed
14 |  | Task |  | Outcodes |  |  | Ashik | Completed
15 |  | Task |  | Outcodes |  |  | Ashik | Completed
16 |  | Task |  | All Properties |  |  | Ashik | Completed | [7 empty] | Updated Sep 6: - shows a warning pop up when we click on sort by price - shows something went wrong when we click on Add to 20-20 campaign
17 |  | Task |  | All Properties |  |  | Ashik | Completed
18 |  | Task |  | All Properties |  |  | Ashik | Completed
19 |  | Task |  | Filter By 0-7 Days |  |  | Ashik | Completed
20 |  | Task |  | Filter By 0-7 Days |  |  | Ashik | Completed
21 |  | Task |  | Filter By 0-7 Days |  |  | Ashik | Completed
22 |  | Task |  | Filter By 7-14 Days |  |  | Ashik | Completed
23 |  | Task |  | Filter By 7-14 Days |  |  | Ashik | Completed
24 |  | Task |  | Filter By 7-14 Days |  |  | Ashik | Completed
25 |  | Task |  | Filter By 14-30 Days |  |  | Ashik | Completed
26 |  | Task |  | Filter By 14-30 Days |  |  | Ashik | Completed
27 |  | Task |  | Filter By 14-30 Days |  |  | Ashik | Completed
28 |  | Task |  | Filter By 30+ Days |  |  | Ashik | Completed
29 |  | Task |  | Filter By 30+ Days |  |  | Ashik | Completed
30 |  | Task |  | Filter By 30+ Days |  |  | Ashik | Completed
31 |  | Task |  | Targeted |  |  | Sharan | Completed |  |  |  | 2023-08-23 | 2023-09-05 |  |  |  | ui-august
32 |  | Task |  | Targeted |  |  | Not Assigned | Completed
33 |  | Task |  | Targeted |  |  | Not Assigned | Completed
34 |  | Task |  | Rental Reduced |  |  | Ashik | Completed
35 |  | Task |  | Rental Reduced |  |  | Ashik | Completed
36 |  | Task |  | Rental Reduced |  |  | Ashik | Completed
37 |  | Task |  | Let Agreed | if one agent makes the property Let agreed, it will move to Let Agreed listing |  | Ashik | Completed
38 |  | Task |  | Let Agreed |  |  | Ashik | Completed
39 |  | Task |  | Let Agreed |  |  | Ashik | Completed
40 |  | Task |  | Live Campaign |  |  | Ashik | Completed
41 |  | Task |  | Live Campaign |  |  | Ashik | Completed
42 |  | Task |  | Live Campaign |  |  | Ashik | Completed
43 |  | Task |  | Campaign History |  |  | Ashik | Completed
44 |  | Task |  | Campaign History |  |  | Not Assigned | Completed
45 |  | Task |  | Campaign History |  |  | Not Assigned | Completed
46 |  | Task |  | Letter Management |  |  | Ashik | Completed
47 |  | Task |  | Letter Management |  |  | Not Assigned | Completed
48 |  | Task |  | Letter Management |  |  | Not Assigned | Completed
49 |  | Task |  | Settings |  |  | Ashik | Completed
50 |  | Task |  | Settings |  |  | Not Assigned | Completed
51 |  | Task |  | Settings |  |  | Not Assigned | Completed
52 |  | Task |  | QR |  |  | Rijo | Completed
53 |  | Task |  | QR |  |  | Rijo | Completed
54 |  | Task |  | QR |  |  | Rijo | Completed
55 |  | Task |  | Letsbid Connection | posting route in prospecting |  | Ashik | Completed
56 |  | Task |  | Letsbid Connection |  |  | Not Assigned | Completed
57 |  | Task |  | UI Changes |  |  | Not Assigned | Completed
58 |  | Task |  | Targeted |  |  | Rahul | Completed
59 |  | Task |  | Side Panel | how many years Letting experience does the agency have? how much rental collection are you taking every month/year? how many rentals have been agreed in the last 6 months? agents will enter these data and it will be shown in the side panel |  | Rijo | Completed |  |  |  | 2023-08-23 | 2023-09-05 |  |  |  | no59_sidepanel_text_change_Rijo_9oct2023
60 |  | Task |  | Side Panel |  |  | Rijo | Completed
61 |  | Task |  | Side Panel |  |  | Rijo | Completed
62 |  | Task |  | Targeted | if the company owns other properties, in the detail page there will be a section displaying all other properties under the ownership of that company. |  | Sharan | Completed |  |  |  | 2023-09-06 | 2023-09-12 |  |  |  | ui-august
63 |  | Task |  | Admin | option for admin to activate lettings for an Agent |  | Rijo | Completed
65 |  | Task |  | Targeted | In the targeted listing page - show the company name and address in the listing - add min and max filter |  | Sharan | Completed |  |  |  | 2023-09-06 | 2023-09-12 |  |  |  | ui-august
66 |  | Task |  | Targeted | in the targeted detail page please show the company details (like in Letsbid Sales) |  | Sharan | Completed |  |  |  | 2023-09-06 | 2023-09-12 |  |  |  | ui-august
67 |  | Task |  | Targeted | when sending letters to targeted addresses, they should have the option to send letter to the property address and the company address |  | Sharan | Completed |  |  |  | 2023-09-13 | 2023-09-14 |  |  |  | No67_sending letter_to_company_address_in_targeted_campaign_13_09_2023_Sharan_N_P
68 |  | Discuss |  | Property Detail Page | in listing activity it's given as For Sale, shouldn't it be For Let or For Rent |  | Rijo | Completed
69 |  | Issue |  | Settings | shows an error page when we click on settings in the menu |  | Not Assigned | Completed
70 |  | Task |  | Property Report | remove the satellite image feature (cover image) and change the wording and title for satellite image section to Title - Map Marker wording - Click here to add markers on the map page |  | Sharan | Completed |  |  |  | 2023-09-18 | 2023-09-18 |  |  |  | No70_remove_the_satellite_image_feature_18_09_2023_Sharan_N_P
71 |  | Issue |  | Property Report | not showing comparables in the report |  | Sharan | Completed |  |  |  | 2023-09-19 | 2023-09-19
72 |  | Issue |  | Property Report | not able to generate reports |  | Sharan | Completed |  |  |  | 2023-09-19 | 2023-09-19
73 |  | Issue |  | Property Report | in report history section please change the report types to Landlord Report and Tenant Report |  | Sharan | Completed |  |  |  | 2023-09-18 | 2023-09-18 |  |  |  | No73_text_change_landlord_report_and_tenant_report_18_06_2023_Sharan-N-P
74 |  | Suggestion | Live | Targeted | not able to drag and move the map |  | Rijo | Hold | Low
75 |  | Issue | Live | Targeted | in targeted listing the company address is same as the property address 328, Lincoln Road, Enfield, EN3 4AA 326, Lincoln Road, Enfield, EN3 4AA | Data | Vishnu | Not Started | Medium | [6 empty] | Rahul & Vishnu
76 |  | Issue |  | Targeted | targeted detail page - shows something went wrong when we click on Add to targeted campaign button |  | Sharan | Completed |  |  |  | 2023-09-19 | 2023-09-19
77 |  | Task |  | Targeted | company properties - change the title to Other properties owned by the company |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No77_text_change_to_other_properties_owned_by_the_company_03_10_2023_Sharan_N_P
78 |  | Issue | Demo | Targeted | company properties takes sometime to load |  | Sharan | Completed | [7 empty] | takes time to load
79 |  | Issue |  | All Properties | shows something went wrong when we click on Add to 20-20 campaign |  | Sharan | Completed
80 |  | Issue |  | Let Agreed | shows 404 page when we click on the back button in Let agreed detail page |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No80_-shows_404_page_LetAgreed_detail_page_back_button_03_10_2023_Sharan_N_P
81 |  | Task |  | Let Agreed | in listing activity section in the detail page it only shows For let data, is let agreed data not required in the listing Let Agreed date is given |  | Not Assigned | Closed | [7 empty] | please confirm
82 |  | Issue |  | Live Campaign | not able to close Generating Your Letter with Sidebar Option pop up |  |  | Completed
83 |  | Issue |  | Live Campaign | print letter pop up is not shown |  |  | Completed
84 |  | Issue |  | Live Campaign | remove button does not work |  |  | Completed
85 |  | Issue |  | Live Campaign | second instruction marketing does not work |  |  | Completed
86 |  | Issue |  | Settings | hide Mobile Number to Send Notification field in settings page |  | Rijo | Completed | [7 empty] | no86_hide_notification_message_send_settings_Rijo29Sep23
87 |  | Issue |  | Settings | change the field name to Tenant Report Description and Landlord Report Description |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No87_Description_title_change_in_settings_page_20_09_2023_Sharan_N_P
88 |  | Issue |  | Side Panel | all 3 fields accepts alphabets and characters |  | Rijo | Completed
89 |  | Task |  |  | company owned cron |  | Not Assigned | Hold | [7 empty] | was assigned to Ashik
90 |  | Task |  | Live Campaign | 20-20 campaign |  | Sharan | Completed |  |  |  | 2023-09-19 | 2023-09-19 |  |  |  | No90_Twenty_twenty_feature_19_09_2023_Sharan_N_P
91 |  | Issue |  | Property Report | report cover page - please make sure the map on the cover page is centered when map marker is enabled (similar to prospecting report) https://tinyurl.com/2387chlm |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No91_report_cover_page_map_dislocated_20_09_2023_Sharan_N_P
92 |  | Issue |  | Live Campaign | targeted campaign - for some properties the company address is available but it's not shown in the campaign eg: 4, Strawberry Field, Hatfield, Welwyn Hatfield, Hertfordshire, AL10 8LS 26, South Road, Sparkbrook, Birmingham, West Midlands, B11 1ER |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20
93 |  | Task |  | Letter Management | confirm the trigger types for instruction marketing, 20-20, targeted |  | Rijo | Completed | [7 empty] | Oct 4 - Rosie =============== General letter 2 and 3 Withdrawn Both for second instruction templates 20/20 and targeted fine
94 |  | Issue |  | Live Campaign | targeted bulk mail list - if letters are being sent to both the property address and the company address, the bulk mail list displays only the property address for all entries https://tinyurl.com/27hfuypr |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No94_targeted_bulk_mail_list_20_09_2023_Sharan_N_P
95 |  | Suggestion | Demo | Live Campaign | targeted bulk mail list - please show Company Owned and Company Address tags |  | Sharan | Completed |  |  |  | 2023-10-23 | 2023-10-23 |  |  |  | No95_Targeted_campaign_edits_23_10_2023_Sharan_N_P
96 |  | Issue |  | Live Campaign | for company owned properties, even if we remove either the property address or company address in the local print preview both addresses are shown |  | Sharan | Completed |  |  |  | 2023-09-21 | 2023-09-21 |  |  |  | No96_Local_print_preview_targeted_campaign_21_09_2023_Sharan_N_P
97 |  | Suggestion |  | Targeted | show In Campaign tag when properties are added to campaign |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No97_In_campaign_tag_added_in_targeted_listing_20_09_2023_Sharan_N_P
98 |  | Issue | Demo | Campaign History | shows a warning pop up when we view the campaign |  | Rijo | Completed
99 |  | Issue |  | Property Detail Page | in the property detail page even if letters have been sent campaign history section is missing |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-04 |  |  |  | No99_campaign_history_in-property_detail_03_10_2023_Sharan_N_P
100 |  | Issue |  | Property Detail Page | in the detail page when we click on Add to campaign and Add to 20-20 Campaign, the button does not change to Added to campaign and Added to 20-20 campaign |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04 |  |  |  | No100_Added_to_campaign_and_Added_to_20-20_campaign_04_10_2023_Sharan_N_P
101 |  | Issue |  | Targeted | if the property is already added to targeted campaign, please make sure Added to Targeted Campaign button is disabled |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No102_Already_added_to_campaign_button_disable_details_20_09_2023_Sharan_N_P
102 |  | Issue |  | Targeted | if the agent attempts to add a property that has already been included in the targeted campaign, it shows something went wrong from listing |  | Sharan | Completed |  |  |  | 2023-09-21 | 2023-09-21 |  |  |  | No101_Error_msg_while_adding_already_in_campaign_properties_in_targeted_campaign_21_09_2023_Sharan_N_P
103 |  | Issue |  | Targeted | if the listing was filtered using minimum and maximum price, upon returning to the listing page from the detail page, the minimum/maximum filters will be cleared. |  | Sharan | Completed |  |  |  | 2023-09-20 | 2023-09-20 |  |  |  | No103_min_max_price_cleared_targeted_listing_20_09_2023_Sharan_N_P
104 |  | Issue |  | Targeted | if the user is on a page other than the first one and clicks on select all button, they will be redirected to the first page |  | Sharan | Completed |  |  |  | 2023-09-21 | 2023-09-21 |  |  |  | No104_Select_all_issue_in_targeted_listing_21_09_2023_Sharan_N_P
105 |  | Issue |  | Settings | rightmove and zoopla branch id fields - when we type it just shows processing, no suggestions are shown |  | Sharan | Completed |  |  |  | 2023-09-21 | 2023-09-21 |  |  |  | No105_agents_branch_id_suggestion_21_09_2023_Sharan_N_P
106 |  | Task |  | Property Report | option to remove Estate agent names from comparable pages |  | Sharan | Completed |  |  |  | 2023-10-10 | 2023-10-10 |  |  |  | No106_option_remove_estate_agent_names_from_comparable_pages_10_10_2023_Sharan_N_P
107 |  | Task |  | Live Campaign | show the total campaign count in all 3 campaign tabs |  | Sharan | Completed |  |  |  | 2023-09-22 | 2023-09-22 |  |  |  | No107_campaign_count_22_09_2023_Sharan_N_P
108 |  | Issue |  | Property Report | title number is missing in the report eg: 9, Peach Ley Road, Birmingham, West Midlands, B29 4ES 14, Cornbrook Road, Birmingham, West Midlands, B29 4EP |  | Sharan | Completed | [7 empty] | Title number will not work in our staging and demo servers
109 |  | Task |  | Targeted | in "other properties owned by company section", if there are properties in outcodes to which the agent has not subscribed can they send campaigns to those addresses |  | Sharan | Completed |  |  |  | 2023-09-22 | 2023-09-25 |  |  | agents can send letters to subscribed outcodes property address | No109_only_subscribed_outcode_properties_owned_company_section_25_09_2023_Sharan_N_P
110 |  | Issue |  | Dashboard | campaigns in last 30 days section - please remove probate |  | Sharan | Completed |  |  |  | 2023-09-22 | 2023-09-22 |  |  |  | 110_111_remove_probate_related_tags_dashboard_22_09_2023_Sharan_N_P
111 |  | Issue |  | Dashboard | Campaign - Activity Summary - please remove probate |  | Sharan | Completed |  |  |  | 2023-09-22 | 2023-09-22 |  |  |  | 110_111_remove_probate_related_tags_dashboard_22_09_2023_Sharan_N_P
112 |  | Issue |  | Settings | after editing the profile, the address then changes on the reports and comes out in one line |  | Sharan | Completed |  |  |  | 2023-09-21 | 2023-09-21 |  |  |  | No112_Address_comes-out-in-one-line_21_09_2023_Sharan_N_P
113 |  | Discuss |  | Targeted | export csv in targeted |  | Rijo | Hold
114 | 2023-09-25 | Task |  | Property Detail Page | in RM if the deposit is given as Ask Agent, on the platform it's given as £0 please display as null |  | Ashik | Completed | [7 empty] | need to check with Ashik is Ask Agent flag available in posting data?
115 | 2023-09-25 | Task |  | Property Report | in RM if Let Available Date is given as Now, what should be shown in the detail page? |  | Ashik | Completed | [7 empty] | Now changed to current date of scapping
116 | 2023-09-25 | Task |  |  | in the menu change Lets Agreed to Let Agreed |  | Sharan | Completed |  |  |  | 2023-09-26 | 2023-09-26 |  |  |  | No116_Lets_Agreed_to_Let_Agreed_26_09_2023_Sharan_N_P
117 | 2023-09-25 | Issue |  | All Properties | please add £ before deposit amount |  | Sharan | Completed |  |  |  | 2023-09-26 | 2023-09-26 |  |  |  | No117_add_£_before_deposit_amount_26_09_2023_Sharan_N_P
118 | 2023-09-25 | Discuss |  | Property Detail Page | confirm the text To Rent |  | Rijo | Completed
119 | 2023-09-26 | Issue |  | Targeted | in the targeted detail page please change the comparable title to Sold Comparables |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04
120 | 2023-09-26 | Task |  | Letter Management | change the triggers 2nd instruction -------------------- General letter Price reduction letter 7 day letter 14 day letter 21 day plus letter Targeted marketing -------------------------- General letter 1 General letter 2 AdHoc letter 20 20 marketing ---------------------- 20/20 letter 1 20/20 letter 2 20/20 letter 3 |  | Rijo | Completed |  |  |  | 2023-09-26 | 2023-09-27
121 | 2023-09-26 | Task |  | Main Dashboard | in the main dashboard please make sure the summary box is now Lettings |  | Rijo | Completed |  |  |  | 2023-09-26 | 2023-09-26
122 | 2023-09-26 | Issue |  | Targeted | shows something went wrong when we click on Add to targeted campaign |  | Sharan | Completed
123 | 2023-09-26 | Issue |  | All Properties | exclude my agencies toggle does not work |  | Sharan | Completed |  |  |  | 2023-10-06 | 2023-10-06 |  |  |  | No123_exclude_my_agencies_toggle_does_not_work_06_10_2023_Sharan_N_P
124 | 2023-09-26 | Issue |  | Live Campaign | second instruction marketing and 20-20 campaign - agency is blank for some addresses |  | Sharan | Completed |  |  |  | 2023-10-11 | 2023-10-11 |  |  |  | No124_Agency_address_blank_11_10_2023_Sharan_N_P
125 | 2023-09-26 | Issue |  | QR | shows 404 page when we scan the qr code |  | Rijo | Completed
126 | 2023-09-26 | Issue |  | Summary | when local printing company owned property, the no. of letter sent count is not correct |  | Sharan | Completed |  |  |  | 2023-10-12 | 2023-10-12 |  |  |  | No126_letter_sent_count_mismatch_dashboard_12_10_2023_Sharan_N_P
127 | 2023-09-26 | Issue |  | Property Detail Page | quick send does not work - shows something went wrong |  | Ashik | Completed
128 | 2023-09-26 | Issue |  | Dashboard | quick send does not work - shows something went wrong |  | Ashik | Completed
129 | 2023-09-26 | Task |  | Wallet | wallet configuration |  | Ashik | Completed
130 | 2023-09-26 | Issue |  | Rental Reduced | shows 404 page when we click on the back button in Rental reduced detail page |  | Sharan | Completed |  |  |  | 2023-10-06 | 2023-10-06 |  |  |  | No130_404_Rental_reduced_detail_page_06_10_2023_Sharan_N_P
131 | 2023-09-27 | Task |  | Property Detail Page | lettings comparables in all detail pages add a section Rental comparable |  | Sharan | Completed |  |  |  | 2023-09-27 | 2023-10-03 |  |  |  | No131_lettings_comparables_integration_in_all_detail_pages_28_09_2023_Sharan_N_P
132 | 2023-09-27 | Task |  |  | AWS integration |  | Anisha | Completed |  |  |  | 2023-09-27 | 2023-10-03
133 | 2023-09-28 | Issue |  | Letter Management | triggers of targeted letters are shown for 20-20 letters and vice versa |  | Rijo | Completed
134 | 2023-09-28 | Suggestion |  | Letter Management | change / to - in between 20-20 triggers |  | Rijo | Completed
135 | 2023-09-28 | Issue |  | Let Agreed | please change the title and breadcrumb to Let Agreed |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No135_please_change_the_title_and_breadcrumb_to_Let_Agreed_03_10_2023_Sharan_N_P
136 | 2023-09-28 | Issue |  | Let Agreed | in the detail page the breadcrumb is given as Sold under offer, please change it to Let Agreed |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No135_please_change_the_title_and_breadcrumb_to_Let_Agreed_03_10_2023_Sharan_N_P
137 | 2023-09-28 | Issue |  | Rental Reduced | in the detail page the breadcrumb is given as Price Drop, please change it to Rental Reduced |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No135_please_change_the_title_and_breadcrumb_to_Let_Agreed_03_10_2023_Sharan_N_P
138 | 2023-09-28 | Issue |  | Targeted | in the addresses listed under "other properties owned by the company" section, the house/ flat number is repeating https://tinyurl.com/2d9mz28z |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No138_house_number_repeating_other_properties_owned_by_the_company_03_10_2023_Sharan_N_P
139 | 2023-09-28 | Issue |  | Live Campaign | letterhead has been uploaded but when we click on bulk mail or local print button it shows Letterhead does not exist pop up |  | Rijo | Completed
140 | 2023-09-28 | Issue |  |  | need help form - shows something went wrong when we submit |  | Ashik | Completed
141 | 2023-09-28 | Issue |  | Live Campaign | when we first preview the letters for company owned properties it shows more than 2 previews |  | Sharan | Completed |  |  |  | 2023-10-11 | 2023-10-11
142 | 2023-09-29 | Task |  | Property Report | tenant description and landlord description in lettings |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No142_tenant_description_and_landlord_description_in_lettings_03_10_2023_Sharan_N_P
143 | 2023-09-29 | Task |  | Admin | lettings toggle to enable |  | Rijo | Completed | [7 empty] | work done in CMS and prospecting route side - now connected to DEMO lettings update 16oct ------------------- CMS toggle connected to live lettings
144 | 2023-09-29 | Issue |  | Property Listing | even if letters have been sent to properties the count of letters sent for that property does not increase it remains 0 |  | Ashik | Completed
145 | 2023-09-29 | Issue |  | Live Campaign | targeted campaign - letters have been added for the triggers but none are shown |  | Rijo | Completed
146 | 2023-09-29 | Issue |  | Live Campaign | 20-20 campaign - triggers added for targeted are shown for 20-20 |  | Rijo | Completed
147 | 2023-09-29 | Issue |  | Live Campaign | please check if the correct triggers are shown for 20-20 and targeted campaigns |  | Rijo | Completed
148 | 2023-09-29 | Suggestion |  | Property Listing | remove the i icon beside the no. of letter count |  | Ashik | Completed
149 | 2023-09-29 | Suggestion |  | Property Listing | add a button in the listing page for letter history, on clicking the button a pop up will be shown with the campaign history of the property in All properties, Rental Reduced, Let Agreed |  | Ashik | Completed
150 | 2023-09-29 | Issue |  | Targeted | detail page - should we display the property currently being viewed by the user in the "Other properties owned by the company" section? eg: 22, Sandringham Road, Potters Bar, Hertsmere, Hertfordshire, EN6 1EX |  | Rijo | Hold
151 | 2023-09-29 | Task |  | Admin | login to lettings account |  | Ashik | Completed | [8 empty] | no151_login_using_token_Rijo5oct2023
152 | 2023-10-02 | Discuss |  | Property Detail Page | if the Let available date is given as "Now", what date is shown in the detail page |  | Ashik | Completed
153 | 2023-10-02 | Issue |  | Targeted | if the user is on a page other than the first one and adds properties to targeted campaign, they are redirected to the first page |  | Sharan | Completed |  |  |  | 2023-10-03 | 2023-10-03 |  |  |  | No153_redirected_to_the_first_page_03_10_2023_Sharan_N_P
154 | 2023-10-02 | Issue | Demo | Live Campaign | 20-20 campaign - 20-20 edit address is not working properly, the changes made are not reflected on the letters |  | Sharan | Completed |  |  |  | 2023-10-11 | 2023-10-12 |  |  |  | No154_changes_not_reflected_letters_11_10_2023_Sharan_N_P
155 | 2023-10-02 | Issue | Demo | Live Campaign | 20-20 campaign - the house number is not on the same line as the road name |  | Sharan | Completed |  |  |  | 2023-10-12 | 2023-10-12 |  |  |  | No154_changes_not_reflected_letters_11_10_2023_Sharan_N_P
156 | 2023-10-02 | Task |  |  | add a Lettings button in the prospecting tool - on clicking they will be redirected to their lettings platform and vice versa |  | Ashik | Completed
157 | 2023-10-03 | Discuss |  | Let Agreed | are we getting the let agreed date from somewhere? |  | Ashik | Completed | [7 empty] | Lets agrred date is current date of scapping
158 | 2023-10-03 | Issue |  | Let Agreed | for some addresses the reduced on date is taken as let agreed date 410, Hilton Drive, Aberdeen AB24 4PS - https://demolettings.devidiamober.com/properties/s-41 |  | Ashik | Completed | [7 empty] | Reduced and then lets agreed at the time of scapping. so both show same date
159 | 2023-10-03 | Issue |  | Property Detail Page | sold comparables are not shown, but we are getting comparables in the report 12, Pumphouse Close, Longford, Coventry, Warwickshire CV6 6RE 90, London Road, London, E13 0DD |  | Sharan | Completed |  |  |  | 2023-10-06 | 2023-10-06 |  |  | https://demolettings.devidiamober.com/report/report_storage/report_7_061020230713699653.pdf https://demolettings.devidiamober.com/report/report_storage/report_8_061020230726804867.pdf
160 | 2023-10-03 | Issue | Live | Let Agreed | property is still on the market but it's listed under Let agreed |  | Ashik | Completed
161 | 2023-10-03 | Issue |  | Let Agreed | shows a warning pop up when we click on sort by price |  | Sharan | Completed |  |  |  | 2023-10-12 | 2023-10-12 |  |  |  | No161_warning_pop_up_sort_price_12_10_2023_Sharan_N_P
162 | 2023-10-03 | Issue |  | Let Agreed | sort by List Date and Let Agreed Date is not correct |  | Sharan | Completed |  |  |  | 2023-10-12 | 2023-10-12 |  |  |  | No162_Sort_date_issues_12_10_2023_Sharan_N_P
163 | 2023-10-03 | Issue | Demo | Rental Reduced | shows a warning pop up when we click on sort by Price and List Date |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No163_sort_Price_Drop_Date_13_10_2023_Sharan_N_P
164 | 2023-10-03 | Issue | Demo | Rental Reduced | sort by Price Drop Date is not correct |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No163_sort_Price_Drop_Date_13_10_2023_Sharan_N_P
165 | 2023-10-03 | Issue | Demo | Property Detail Page | update status does not work |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  | Already fixed
166 | 2023-10-03 | Issue | Demo | Property Detail Page | sold history section is missing for some addresses |  | Ashik | Completed
167 | 2023-10-03 | Issue |  | Property Detail Page | please change the title for comparable i.e whether it's Sold Comparable or Rental Comparable |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04
168 | 2023-10-03 | Issue | Demo | Property Detail Page | rental comparable - the property currently being viewed by the user is shown in the rental comparable listing 27, Tillydrone Avenue, Aberdeen AB24 2TE |  | Sharan | Completed |  |  |  | 2023-10-16 | 2023-10-19 |  |  |  | No168_Comparables_tool_added_16_10_2023_Sharan_N_P
169 | 2023-10-03 | Discuss |  | Property Detail Page | for rental comparables since Tenure, Sqft, Price/Sqft and Sold Date is not available do we need to show these data? these are not shown in the report |  | Rijo | Completed | [7 empty] | need to check targeted
170 | 2023-10-03 | Discuss |  | Property Detail Page | rental comparable in detail page - shouldnt all the data displayed in the report be shown in the detail page as well Property Address, Type, Rent, List Date, Bedrooms, Miles |  | Sharan | Completed
171 | 2023-10-03 | Issue |  | Property Detail Page | rental comparable - change the text price to Rent |  | Sharan | Completed |  |  |  | 2023-10-06 | 2023-10-06 |  |  |  | No171_text_change_06_10_2023_Sharan_N_P
172 | 2023-10-03 | Task |  |  | instead of Price change it to Rent in the listing, detail page etc |  | Sharan | Completed |  |  |  | 2023-10-06 | 2023-10-06 |  |  | updated oct 11: not changed in Rental Reduced listing and Let Agreed listing | No171_text_change_06_10_2023_Sharan_N_P
173 | 2023-10-03 | Issue |  | Property Report | property does not have epc but it's still shown in the report 36, Flempton Road, London, E10 7NH 27, Tillydrone Avenue, Aberdeen, Aberdeenshire, AB24 2TE 916, Wilmslow Road, Manchester, M20 5PG |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04 |  |  |  | No173_property_doesn't_have_epc_in_report_04_10_2023_Sharan_N_P
174 | 2023-10-04 | Task |  | Rental Reduced | exclude Let Agreed properties in the Rental Reduced listing |  | Ashik | Completed
175 | 2023-10-04 | Task |  |  | exclude withdrawn properties in both the Rental Reduced and Let Agreed listings |  | Ashik | Completed
176 | 2023-10-04 | Discuss |  | Rental Reduced | is add to 20-20 campaign button needed in all listing pages? |  | Rijo | Completed | [7 empty] | update 10 oct: 20-20 button required in 1. all properties listing and detail 2. Let agreed listing and detail pages
177 | 2023-10-04 | Discuss |  | Targeted | no data is shown for some outcodes, is this because there aren't any company owned properties |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04 |  |  | Yes, Company owned properties only shows in targeted section
178 | 2023-10-04 | Issue | Demo | Property Report | rental comparable pop up keeps loading, not getting rental comparables in report |  | Sharan | Completed |  |  |  | 2023-10-10 | 2023-10-19 |  |  | updated oct 6: please try this address 5, Millfield Close, Retford, Nottinghamshire, DN22 7TW with addresses that dint have rental comparables the message was shown but for some addresses the pop up kept loading | No178_rental_comparable_update_10_10_2023_Sharan_N_P
179 | 2023-10-04 | Suggestion | Demo | Property Detail Page | message shown when comparables are not available in all detail pages - make f small in the message https://tinyurl.com/ywu3jj2z |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No179_text_change_13_10_2023_Sharan_N_P
180 | 2023-10-04 | Suggestion |  | Targeted | change the message shown when properties owned by company is loading to "Other properties owned by the company loading. Just a moment please." https://tinyurl.com/yu77kuo5 |  | Sharan | Completed |  |  |  | 2023-10-04 | 2023-10-04 |  |  |  | No180_msg_change_04_10_2023_Sharan_N_P
181 | 2023-10-04 | Issue |  | Targeted | showed forbidden page when we click on an address listed under Other properties owned by the company 1, Morris Mews, High Wycombe, Wycombe, Buckinghamshire, HP11 1AL - showed forbidden on clicking 152, Melton Road, West Bridgford, Nottingham, NG2 6ER from the listing |  | Sharan | Completed |  |  |  | 2023-10-05 | 2023-10-05 |  |  |  | No181_showed_forbidden_page_05_10_2023_Sharan_N_P
182 | 2023-10-04 | Issue | Demo | Property Report | rental comparables are shown in the targeted detail page but not in the report 2, Botanical Grove, Luton, LU2 7GZ - https://demolettings.devidiamober.com/report/report_storage/report_15_041020231452808029.pdf |  | Sharan | Completed |  |  |  | 2023-10-05 | 2023-10-05 |  |  |  | No182_rental_comparables_not_in_the_report_05_10_2023_Sharan_N_P
183 | 2023-10-04 | Issue |  | Letter | the border between the side panel and content does not look aligned https://tinyurl.com/ypntp3ku |  | Rijo | Completed | [8 empty] | no183_thick_border_sidepanel_edit_Rijo_10Oct2023
184 | 2023-10-04 | Issue |  | Filter By 14-30 Days | in 14-30 days please show the properties listed between 15days and 30 days |  | Sharan | Completed |  |  |  | 2023-10-09 | 2023-10-09 |  |  |  | No184_filter_days_count_error_09_10_2023_Sharan_N_P
185 |  | Issue |  |  | https://docs.google.com/spreadsheets/d/1awSumAqk4DpZR-834f1sUdkKtPvwnyp7jTT_7S5priE/edit?usp=sharing |  |  | Closed
186 | 2023-10-05 | Issue |  | Property Detail Page | no data is shown only the title is in the detail page https://demolettings.devidiamober.com/properties/p-35269 |  | Sharan | Completed |  |  |  | 2023-10-09 | 2023-10-09
187 | 2023-10-05 | Issue |  |  | shows something went wrong when we click on the prospecting button |  | Rijo | Completed
188 | 2023-10-05 | Issue |  | Settings | when compared to prospecting tool, the images added are not shown in Lettings |  | Anisha | Completed
189 | 2023-10-06 | Task |  | Wallet | when letters are sent for letting properties, in the wallet please mention if it's sent through Lettings or Prospecting |  | Rijo | Completed
190 | 2023-10-06 | Issue | Demo | Live Campaign | the trigger names shown for second instruction is not correct, name given is that of probate |  | Rijo | Completed
191 | 2023-10-06 | Issue | Demo | Live Campaign | 20-20 bulk mail - getting an error page https://tinyurl.com/ypoagdjg |  | Sharan | Completed
192 | 2023-10-06 | Issue | Demo | Live Campaign | targeted campaign - getting an error page when we send bulk mail https://tinyurl.com/yt7ryjdr |  | Sharan | Completed
193 | 2023-10-06 | Issue | Demo | Live Campaign | 20-20 campaign and targeted campaign - the local print pop up is not shown |  | Rijo | Completed
194 | 2023-10-06 | Issue |  | Property Report | tenant description and landlord description is not shown in the report |  | Sharan | Completed |  |  |  | 2023-10-10 | 2023-10-10 |  |  |  | No194_description_not_shown_in_report_10_10_2023_Sharan_N_P
195 | 2023-10-06 | Task |  | Property Report | on market comparable property - change the title to On Market Sale Comparables |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No195_title_change_on_market_comparable_property_13_10_2023_Sharan_N_P
196 | 2023-10-06 | Issue | Demo | Let Agreed | add to 20-20 campaign button is missing in the detail page |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No196_add_to_20_20_campaign_button_missing_detail_page_13_10_2023_Sharan_N_P
197 | 2023-10-06 | Discuss |  | Property Report | in property in for page should it be market price or rent? |  | Sharan | Completed
198 | 2023-10-06 | Discuss |  | Property Detail Page | Property Sold History section - should the text be Property Listing Price or something else? |  | Rijo | Completed
199 | 2023-10-10 | Issue |  | Targeted | company details of the property needs to be loaded first and then only the rest of the properties owned by the company needs to load |  | Sharan | Completed |  |  |  | 2023-10-11 | 2023-10-11 |  |  |  | No199_company_needs_load_11_10_2023_Sharan_N_P
200 | 2023-10-10 | Issue |  | Live Campaign | when adding targeted properties to the campaign from the detail page, the company address is not shown |  | Sharan | Completed |  |  |  | 2023-10-11 | 2023-10-11 |  |  |  | No200_company_address_11_10_2023_Sharan_N_P
201 | 2023-10-10 | Issue |  | Settings | if we upload profile image, report logo or team image in lettings, the images are not updated in sales account it changes to the default images same happens when we upload images in sales account |  | Anisha | Completed
202 | 2023-10-10 | Issue | Demo | Admin | if we login to a users lettings account via admin side, the account opens in a new tab and also is still logged into the admin account |  | Ashik | Completed
203 | 2023-10-10 | Issue | Demo | Property Report | Planning Data on Property - if decision issued date is not available it is given as 01-01-1970 |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  | please check with Abhijith as he dealt with a similar issue in prospecting | No203_issued_date_not_available_13_10_2023_Sharan_N_P
204 | 2023-10-10 | Issue | Demo | Side Panel | getting an error page when we click on settings if we clear the input and then submit https://tinyurl.com/ynzu5s6d |  | Rijo | Completed
205 | 2023-10-10 | Issue | Demo | Side Panel | if we give an input and submit even if we havent enabled that data after submitting it automatically is enabled |  | Rijo | Completed
206 | 2023-10-10 | Issue | Demo | Dashboard | campaign insight - the letter sent count for all 3 campaigns is not correct |  | Sharan | Completed |  |  |  | 2023-11-08 | 2023-11-08
207 | 2023-10-10 | Issue | Demo | Live Campaign | targeted - the triggers names are not correct, instead of Adhoc it shows Targeted Letter 3 |  | Rijo | Completed | [7 empty] | update 19 oct ------------------ Cache clear in demo working, letter type fixed
208 | 2023-10-10 | Issue |  | Live Campaign | 20-20 - shows an error page when we click on 20-20 campaign tab |  | Rijo | Completed
209 | 2023-10-10 | Issue |  | Live Campaign | 2nd instruction - the triggers shown are that of probate |  | Rijo | Completed
210 | 2023-10-10 | Issue | Demo | Property Detail Page | campaign history section - if we do 20-20 campaign for the property in campaign history section is only letter sent date and status is shown the name and trigger is blank https://tinyurl.com/yl6lfvef |  | Sharan | Completed |  |  |  | 2023-10-25 | 2023-10-25 |  |  |  | No210_Campaign_history_section_values-_missing_25_10_2023_Sharan_N_P
211 | 2023-10-10 | Issue | Demo | Campaign History | for local print letters the file icon is missing |  | Sharan | Completed |  |  |  | 2023-10-19 | 2023-10-19 |  |  |  | No211_pdf_icon_missing_campaign_history_19_10_2023_Sharan_N_P
212 | 2023-10-10 | Issue |  | Live Campaign | targeted campaign - shows an error page when we do bulk mail https://tinyurl.com/ypv8envn |  | Rijo | Completed
213 | 2023-10-10 | Issue | Demo | Live Campaign | targeted campaign - when we click on Print Letterhead and content it shows the warning message saying letterhead does not exist |  | Sharan | Completed |  |  |  | 2023-10-19 | 2023-10-19 |  |  |  | No211_pdf_icon_missing_campaign_history_19_10_2023_Sharan_N_P
214 | 2023-10-10 | Issue | Demo | Letter | data shown in the sidepanel is not what was given by user |  | Rijo | Completed
215 | 2023-10-10 | Issue | Live | Dashboard | Sending bulk mail loader takes time to close |  | Ashik | Completed
216 | 2023-10-10 | Issue | Demo | Quick Send | if the user's credit is low while attempting a quick send, a notification is displayed. However, if the user then selects fewer letters and sends, letters are sent to all the addresses in the quick send list even though the balance is low |  | Sharan | Closed | [7 empty] | please speak to Abhijith as he dealt with this issue in prospecting
217 | 2023-10-10 | Issue |  | Property Detail Page | shows an error page when we click on the campaign in Campaign History section https://tinyurl.com/ys5tc8w9 |  | Not Assigned | Completed
218 | 2023-10-10 | Issue | Demo |  | shows privacy error page when we click on Prospecting button on Lettings platform |  | Ashik | Completed | [7 empty] | Demo server https missing. wont be problem in production
219 | 2023-10-11 | Issue |  | Property Detail Page | for some listing the Deposit is given as £0 in RM but it's blank on the lettings platform |  | Ashik | Completed
220 | 2023-10-11 | Issue | Demo | Let Agreed | please change to Let Agreed Date |  | Sharan | Completed |  |  |  | 2023-10-13 | 2023-10-13 |  |  |  | No220_please_change_to_Let_Agreed_Date_13_10_2023_Sharan_N_P
221 | 2023-10-11 |  |  | Rental Reduced | 2, Osier Mews, London, W4 2NT - need to check after posting for price reduced |  | Not Assigned | Completed
222 | 2023-10-11 | Issue | Demo | Property Listing | for properties with multiple listing please make sure the price and deposit of the latest listing is shown 11, Chiswick Lane, London, W4 2LR |  | Rijo | Completed
223 | 2023-10-11 | Discuss |  | Wallet | top up credit - will the card number field be active when it's live |  | Rijo | Completed
224 | 2023-10-12 | Issue | Demo | Targeted | for some addresses the company name and address is given as Not Available but it is given in the detail page 15, Hart Hill Lane, Luton, LU2 0AZ |  | Sharan | Completed |  |  |  | 2023-10-25 | 2023-10-25 |  |  |  | No224_Company_details_missing_25_10_2023_Sharan_N_P
225 | 2023-10-12 | Issue | Demo | Targeted | takes time for the detail page to load 51, Rusthall Avenue, London, Ealing, W4 1BN |  | Sharan | Completed
226 | 2023-10-12 | Issue | Demo | Campaign History | 2nd instruction - shows a warning pop up when we open bulk mail campaign |  | Sharan | Completed
227 | 2023-10-12 | Issue | Demo | Live Campaign | 20-20 campaign - the page keeps loading when we click on pdf preview while doing bulk mail |  | Sharan | Completed
228 | 2023-10-12 | Issue | Demo | Dashboard | Campaign - Activity Summary does not work |  | Ashik | Completed
229 | 2023-10-13 | Issue | Demo | Live Campaign | 20-20 campaign - listed date is missing for some address |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  | https://tinyurl.com/yk97ntlk - still missing for some | No229_20_20_campaign_listed_date_missing_properties_26_10_2023_Sharan_N_P
230 | 2023-10-13 | Issue | Demo | Property Listing | even if letters have been sent to properties the status does not change to Letter Sent in All Properties listing and Filtered by listing |  | Ashik | Completed
231 | 2023-10-13 | Issue | Demo | Rental Reduced | shows a warning pop up when we click on Rental Reduced |  | Sharan | Completed |  |  |  | 2023-10-20 | 2023-10-20 |  |  | Just check once again and confirm the issue
232 | 2023-10-13 | Issue | Demo | Let Agreed | campaign history pop up is not shown when we click on View button |  | Ashik | Completed | [7 empty] | pop up not shown when we click on View in Lets Agreed listing
233 | 2023-10-13 | Issue | Demo | Campaign History | 20-20 campaign - in the local print campaign when we click on view button it shows letter not available https://tinyurl.com/yvlav25n |  | Sharan | Completed
234 | 2023-10-13 | Issue | Demo | Let Agreed | the selections are not cleared after adding properties to 20-20 campaign and 2nd instruction campaign please check in Rental Reduced listing as well |  | Sharan | Completed |  |  |  | 2023-10-24 | 2023-10-24 |  |  | when we add properties to campaign and then return to the listing page the selections are still there 1. add any property to the campaign 2. go to a different listing or to the detail page 3. return back to the listing | No234_select_all_clear_issue_26_10_2023_Sharan_N_P
235 | 2023-10-13 | Issue | Demo | Quick Send | quick send not working |  | Not Assigned | Completed
236 | 2023-10-16 | Issue | Demo | Live Campaign | none of the campaigns are working |  | Rijo | Completed | [7 empty] | no236_payment_out_of_job_edit_Rijo_24oct23
237 | 2023-10-17 | Issue | Live | Live Campaign | 2nd instruction, 20-20, targeted - shows server error when sending bulk mail |  | Rijo | Completed
238 | 2023-10-17 | Issue | Live | Live Campaign | preview does not work |  | Rijo | Completed
239 | 2023-10-17 | Issue | Live | Letter Management | shows server error when we view the added letters |  | Rijo | Completed
240 | 2023-10-17 | Issue | Live | Letter Management | when editing or adding letters in the letter view section it shows server error |  | Rijo | Completed
241 | 2023-10-17 | Issue | Live | Wallet | top up credit - card number field is not shown |  | Ashik | Completed
242 | 2023-10-17 | Issue | Live | Settings | shows server error when we edit the profile |  | Rijo | Completed
243 | 2023-10-17 | Issue | Live | Property Report | nothing happens when we click on confirm address |  | Not Assigned | Completed
244 | 2023-10-17 | Issue | Live | Quick Send | shows something went wrong when we click on print preview before doing quick send |  | Not Assigned | Completed
245 | 2023-10-17 | Issue | Demo | Rental Reduced | even if we update the status it does not change in the rental reduced listing page |  | Sharan | Completed |  |  |  | 2023-10-24 | 2023-10-24
246 | 2023-10-18 | Task | Demo | Property Report | after report is generated the agent can email report and also a link which they can send to the customer and once the customer opens the report the agents will be notified. in the dynamic url pop up add a toggle for email address - When the toggle is enabled, the user must input their email to access the report when clicking the link. |  | Anisha | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | no246-dynamicreport_link_anisha26oct
247 | 2023-10-18 | Task | Demo | Summary | add a section for report in the summary page to show the view count and other details |  | Anisha | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | no247-summaryreport_link_anisha26oct
248 | 2023-10-18 | Issue | Demo | Targeted | in the rental comparable the Available Date is given as 01-01-1970 98, High Street, Plaistow, London, Newham, E13 0AJ |  | Sharan | Completed |  |  |  | 2023-10-20 | 2023-10-20 |  |  |  | No248_targeted_rental_comp_available_date_default_20_10_2023_Sharan_N_P
249 | 2023-10-19 | Issue | Live | Let Agreed | 6, Roma Road, Greet, Birmingham, West Midlands B11 2JN - still on market but listed under Let Agreed and also the rent was reduced but not listed in Rental Reduced |  | Rishika | Closed
250 | 2023-10-19 | Issue | Live |  | To check after next run: 26, Longfield Avenue, Strelley, Nottingham, Nottinghamshire NG8 4JP - rent reduced |  | Rishika | Closed
251 | 2023-10-20 | Issue | Demo | Property Detail Page | rental comparable - available date is not in UK format, dd-mm-yyyy https://tinyurl.com/ylykqmo9 |  | Sharan | Completed |  |  |  | 2023-10-24 | 2023-10-24 |  |  |  | No251_rental_comparables_available_date_format_correction_24_10_2023_Sharan_N_P
252 | 2023-10-20 | Issue | Demo | Property Report | comparables are not shown in the report but in the detail page there are comparables 56, Boscombe Road, Birmingham, West Midlands B11 3RJ Apartment 14, Crozier House, The Boulevard, Leeds, West Yorkshire LS10 1LQ |  | Sharan | Completed |  |  |  | 2023-10-24 | 2023-10-25 |  |  |  | No252_comparable_missing_report_24_10_2023_Sharan_N_P
253 | 2023-10-20 | Issue | Demo | Rental Reduced | add to 20-20 campaign button is not required in rental reduced detail page |  | Sharan | Completed |  |  |  | 2023-10-24 | 2023-10-24 |  |  |  | No253_remove_20_20-button_rental_reduced_detail_page_24_10_2023_Sharan_N_P
254 | 2023-10-24 | Suggestion | Live | Wallet | when credits are refunded for letting properties, in the wallet please mention if it's sent from Lettings or Prospecting |  | Rijo | Not Started | Low
255 | 2023-10-24 | Issue | Demo | Property Detail Page | comparables section keeps loading for some addresses 22, Beechways, Retford, Nottinghamshire DN22 7RL 6, Pine Close, London, N14 5QA 56, Boscombe Road, Birmingham, West Midlands B11 3RJ 149, Solihull Road, Sparkhill, Birmingham, West Midlands B11 3AE 30, Masefield Crescent, London, N14 4AG |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | No255_comparables_section_keeps_loading_26_10_2023_Sharan_N_P
256 | 2023-10-24 | Issue | Demo | Property Report | when generating reports even if there are comparables in the detail page, it is shown in the report only when we enter the bedroom count for on market and targeted properties |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26
257 | 2023-10-24 | Issue | Demo | Summary | the campaign counts are not correct |  | Sharan | Completed |  |  |  | 2023-11-08 | 2023-11-08 |  |  | updated 1 Nov: https://docs.google.com/spreadsheets/d/1WjnUjBmxpyUdjSZ_jo_ebfFABn2g78Pkl4hRvaLRBlg/edit#gid=1155931630&range=293:295 | No257_Campaign_count_error_summary_page_31_10_2023_Sharan_N_P
258 | 2023-10-24 | Issue | Demo | Quick Send | If a user initially selects a few addresses, previews them, and then proceeds to deselect or add more addresses, the letters will be sent only to the addresses that were initially selected. to get the issue: 1. select few addresses from the bulk mail list 2. preview the letter 3. select more addresses or deselect addresses 4. send bulk mails |  | Sharan | Closed | [7 empty] | please speak to Abhijith as he dealt with the issue in Letsbid
259 | 2023-10-24 | Discuss | Live | Property Detail Page | when Let Available Date is given as Now in Rightmove, the date shown is the date of scraping but it does not get updated later so even if the property is still on market, the displayed available date will be in the past. | web | Rijo | Discuss | Medium | [6 empty] | date of first scrapping is shown when Now is given in RM ------- need to discuss with Rahul
260 | 2023-10-24 |  | Demo |  | To check after next run: 26, Longfield Avenue, Strelley, Nottingham, Nottinghamshire NG8 4JP - rent reduced https://www.rightmove.co.uk/properties/141209972#/?channel=RES_LET https://www.rightmove.co.uk/properties/140498051#/?channel=RES_LET |  |  | Completed
261 | 2023-10-24 | Issue | Demo | Rental Reduced | the selections are not cleared after adding properties to 20-20 campaign and 2nd instruction campaign |  | Sharan | Completed | [7 empty] | similar to task 234
262 | 2023-10-24 | Issue | Demo | Live Campaign | after local printing the print letter pop up is not shown |  | Anisha | Completed | [7 empty] | pub-sub configuration | no262_localprint_popup_anishaoct27
263 | 2023-10-24 | Issue | Demo | Property Report | Sold Date in Sold Comparable Properties list and List Date in On Market Rental Comparable Properties List are not in the correct format, dd-mm-yyyy |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | No263_date_format_correction_report_26_10_2023_Sharan_N_P
264 | 2023-10-25 | Issue | Demo | Property Detail Page | in On Market comparables section in the detail page for some addresses the last sold price is £0 10, Orpington Drive, Coventry, West Midlands CV6 4NJ |  | Sharan | Completed |  |  |  | 2023-10-30 | 2023-10-30 |  |  |  | No264_last_sold_price_£0_detail_page_30_10_2023_Sharan_N_P
265 | 2023-10-25 | Issue | Demo | Live Campaign | 2nd instruction bulk mail list - even if the property is not company owned it shows the Company owned tag https://tinyurl.com/ykurpbpn |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No265_Company_owned_tag_01_11_2023_Sharan_N_P
266 | 2023-10-25 | Issue | Demo | Quick Send | spelling error in the Company Address tag https://tinyurl.com/ywmc5nq9 |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | No266_Spelling_error_26_10_2023_Sharan_N_P
267 | 2023-10-25 | Issue | Demo | Property Report | sold comparable, on market sale comparable, on market rental comparable pop up's keep loading when generating report 2, Berkshire Gardens, London, N13 6AB Cator Lodge, South Row, London, SE3 0NU |  | Sharan | Completed |  |  |  | 2023-10-26 | 2023-10-26 |  |  |  | No267_While_error_no_found_msg_comparable_report_26_10_2023_Sharan_N_P
268 | 2023-10-25 | Discuss | Demo | Targeted | targeted detail page - in company details section the title number shown is that of the property we are viewing? |  | Sharan | Completed |  |  |  | 2023-11-08 | 2023-11-08
269 | 2023-10-26 | Task | Demo | Property Detail Page | if Let Available Date and Deposit is blank show Ask Agent |  | Sharan | Completed |  |  |  | 2023-10-27 | 2023-10-27 |  |  |  | No269_Let_Available_Date_Deposit_blank_Ask_Agent_27_10_2023_Sharan_N_P
270 | 2023-10-26 | Issue | Demo | Property Listing | campaign history pop up - if we do 20-20 campaign for the property in the pop up only letter sent date and status is shown the name and trigger is blank https://tinyurl.com/ytkfsafc |  | Sharan | Completed |  |  |  | 2023-10-27 | 2023-10-28 |  |  | please check the listing page | No270_trigger_blank_28_10_2023_Sharan_N_P
271 | 2023-10-26 | Issue | Demo | Property Report | on market sale comparable - miles is blank for all properties listed |  | Sharan | Completed |  |  |  | 2023-11-09 | 2023-11-09 |  |  |  | No271_on_market_comparable_miles_missing_09_11_2023_Sharan_N_P
272 | 2023-10-26 | Issue | Demo | Targeted | the title number displayed is not correct 8, The Triangle, Nottingham, City Of Nottingham, NG2 1AE |  | Sharan | Completed |  |  |  | 2023-10-27 | 2023-10-27 |  |  |  | No272_Title_number_not_correct_27_10_2023_Sharan_N_P
273 | 2023-10-26 | Issue | Demo | Property Report | when generating tenant report even though Rental comparable is selected, the pop up is not shown automatically |  | Sharan | Completed |  |  |  | 2023-10-27 | 2023-10-28 |  |  |  | No273_Rental_comparable_popup_not_showing_27_10_2023_Sharan_N_P
274 | 2023-10-26 | Task | Demo | Targeted | in the detail page title number of property to be separated from company details section |  | Sharan | Completed |  |  |  | 2023-10-28 | 2023-10-28
275 | 2023-10-27 | Issue | Live | Email | mail received when agent clicks on the mail icon, there is a section in the mail that is not required https://tinyurl.com/yrjosrpb |  | Rijo | Completed | High |  |  | 2024-01-24 | 2024-01-24 | 2024-01-24 |  | cannot check mails in demo | 275_mail_issues_Rijo_24Jan24
276 | 2023-10-27 | Issue | Demo | Property Detail Page | comparables are not shown in the detail page but it's there in the report 22, Beechways, Retford, Nottinghamshire DN22 7RL 11, Railway Terrace, Sandycroft, Deeside, Flintshire CH5 2QF 49, Skircoat Green, Halifax, West Yorkshire, HX3 0RX 5, Crimble Close, Halifax, West Yorkshire HX3 8BL |  | Sharan | Completed |  |  |  | 2023-10-29 | 2023-10-29 |  |  |  | No276_Comparables_missing_detail_page_29_10_2023_Sharan_N_P
277 | 2023-10-27 | Issue | Demo | Property Detail Page | rental comparables - the addresses which are linked does not redirect to the correct detail page, it shows a different address please check the Rental comparables listed 5, Crimble Close, Halifax, West Yorkshire HX3 8BL 124, Brendon Avenue, Luton LU2 9LH 11, Chelsworth Close, Luton LU2 9SU 10, Cricketers Close, London, N14 4BT |  | Sharan | Completed |  |  |  | 2023-10-30 | 2023-10-30
278 | 2023-10-27 | Issue | Demo | Property Detail Page | property sold history and comparables section are not shown 8, Baylam Dell, Luton LU2 9ST |  | Sharan | Completed |  |  |  | 2023-10-30 | 2023-10-30 |  |  |  | NO278_sold_history_missing_details_page_30_10_2023_Sharan_N_P
279 | 2023-10-27 | Issue | Demo | Property Detail Page | shows an error page when we click on some properties listed under Rental Comparables 1, Cricketers Close, London, N14 4BT - click on 10, Cricketers Close, London, Greater London, N14 4BT https://tinyurl.com/ylwnr5g5 |  | Sharan | Completed |  |  |  | 2023-10-29 | 2023-10-29 |  |  |  | No277_addresses_linked_not_redirect_to_detail_page_29_10_2023_Sharan_N_P
280 | 2023-10-27 | Issue | Demo | Property Report | On Market Rental Comparable Properties List pop up - the righmove icon is not linked properly, it's linked to https://www.rightmove.co.ukhttps//www.rightmove.co.uk/properties/138751073#/?channel=RES_LET |  | Sharan | Completed |  |  |  | 2023-10-28 | 2023-10-28 |  |  |  | No280_Comparables_portal_link_issue_28_10_2023_Sharan_N_P
281 | 2023-10-27 | Issue | Demo | Property Detail Page | campaign history section - 2 campaigns are shown in the campaign history section in the detail page when we do local print/bulk mail for company owned address using quick send https://tinyurl.com/ytms3rpr |  | Sharan | Completed |  |  |  | 2023-10-31 | 2023-10-31 |  |  | please contact Sandeep | No281_Cmpaign_history_duplicates_01_11_2023_Sharan_N_P
282 | 2023-10-30 | Task | Demo | Property Listing | deposit, furnish type blank in the listing |  | Sharan | Completed |  |  |  | 2023-10-30 | 2023-10-30 |  |  |  | No282_deposit_furnish_type_missing_listing_30_10_2023_Sharan_N_P
283 | 2023-10-31 | Issue | Live | Property Report | nothing happens when we submit the email to view the report |  | Rijo | Completed
284 | 2023-10-31 | Issue | Live | Summary | shows an error page when we click on summary https://tinyurl.com/ys25a35c |  | Rijo | Completed
285 | 2023-10-31 | Suggestion | Demo | Property Listing | in Rightmove the furnish type is given as Ask Agent but on the platform it's given as N/A, please change |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No287_deposit_0_not_available_01_11_2023_Sharan_N_P
286 | 2023-10-31 | Suggestion | Demo | Property Detail Page | in Rightmove the furnish type is given as Ask Agent but on the platform it's given as N/A, please change to Ask Agent |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No287_deposit_0_not_available_01_11_2023_Sharan_N_P
287 | 2023-10-31 | Issue | Demo | Property Detail Page | if the deposit is £0 please show £0, it shows Ask Agent now 10, Brougham Street, Halifax, West Yorkshire HX3 6NF 26, Melrose Street, Halifax, West Yorkshire HX3 5BZ |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No287_deposit_0_not_available_01_11_2023_Sharan_N_P
288 | 2023-10-31 | Issue | Demo | Property Detail Page | if the property is withdrawn, shouldnt it be mentioned in the listing activity 69, Bath Place, Halifax, West Yorkshire HX3 6EG 15, St Georges Crescent, Halifax, West Yorkshire HX3 5LR |  | Ashik | Completed |  |  |  | 2023-11-03 | 2023-11-03 | 2023-11-10 |  |  | 288-withdrawn-listing-activity-ack
289 | 2023-10-31 | Issue | Demo | Property Detail Page | rental comparable - if the Deposit, Furnish Type, Available Date is given as Ask Agent in Rightmove, it shows Not Available in the rental comparable section 22, Beechways, Retford, Nottinghamshire DN22 7RL 5, Crimble Close, Halifax, West Yorkshire HX3 8BL |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No289_Not_available_to_ask_agent_comparables_01_11_2023_Sharan_N_P
290 | 2023-11-07 | Issue | Live | Property Report | comparables keep loading when generating the report |  | Sharan | Completed |  |  |  | 2023-11-07 | 2023-11-07
291 | 2023-11-01 | Issue | Demo | Property Detail Page | comparables section is missing in detail page For results, please ensure you select both property type and number of bedrooms. Sqft is optional! 8, Baylam Dell, Luton LU2 9ST |  | Sharan | Completed |  |  |  | 2023-11-01 | 2023-11-01 |  |  |  | No291_comparable_parameter_missing_01_11_2023_Sharan_N_P
292 | 2023-11-01 | Issue | Demo | Property Detail Page | if Let Available Date is Ask Agent in Rightmove it's not shown in the detail page, please show Ask Agent 61, Doe Quarry Lane, Dinnington, Sheffield, South Yorkshire S25 2NJ 35, Scarsdale Street, Dinnington, Sheffield, South Yorkshire S25 2RN |  | Sharan | Completed |  |  |  | 2023-11-06 | 2023-11-06 |  |  |  | No292_Let_available_date_not_showing_property_detail_page_06_11_2023_Sharan_N_P
293 | 2023-11-01 | Issue | Demo | Summary | targeted summary - campaign count remains 0 - local print letter count is not correct, the company address count is not included |  | Sharan | Completed |  |  |  | 2023-11-08 | 2023-11-08
294 | 2023-11-01 | Issue | Demo | Summary | 20-20 summary - local print and bulk mail campaign count is not correct |  | Sharan | Completed
295 | 2023-11-01 | Issue | Demo | Summary | 2nd instruction summary - letter sent and bulk mail letter sent count is not correct |  | Sharan | Completed
296 | 2023-11-01 | Issue | Live | Summary | if any of the letters fail and the user is refunded the count does not need to increase |  | Not Assigned | Hold
297 | 2023-11-01 | Discuss | Live | Let Agreed | for let agreed properties, in the detail page can we not show the let agreed activity in the listing the Let Agreed date is given, can we not show it in the detail page also? |  | Rijo | Discuss | Medium
298 | 2023-11-02 | Issue | Live | Property Listing | in campaign tag is not shown after adding properties to campaign, the tag is displayed only when the page is refreshed |  | Sharan | Completed |  |  |  | 2023-11-08 | 2023-11-08
299 | 2023-11-02 | Issue | Live | Property Detail Page | furnish type is shown in between ¦¦ https://tinyurl.com/2xxqg7ey |  | Sharan | Completed |  |  |  | 2023-11-06 | 2023-11-06 |  |  |  | No299_furnish_type_extra_icon_detail_page_06_11_2023_Sharan_N_P
300 | 2023-11-02 | Issue | Live | Property Report | in the targeted detail page comparables are shown but when generating a report there are no comparables |  | Sharan | Completed | [7 empty] | Sharan : Add custom values for gettings comparables
301 | 2023-11-02 | Issue | Live | Property Report | title number of the property is not shown in the report 38, Kingsford Road, Coventry, West Midlands, CV6 3LP 14, Cressex Road, High Wycombe, Buckinghamshire, HP12 4TY |  | Sharan | Completed |  |  |  | 2023-11-07 | 2023-11-07
302 | 2023-11-02 | Task | Live | Property Detail Page | in the detail page of company owned property, the title number of property to be separated from company details section |  | Sharan | Completed |  |  |  | 2023-11-06 | 2023-11-06 |  |  |  | No302_seperate_title_number_company_owned_detail_section_06_11_2023_Sharan_N_P
303 | 2023-11-01 | Issue | Live | Targeted | title number of the property is not correct 6, Calver Close, Nottingham, NG8 1AT |  | Sharan | Completed |  |  |  | 2023-11-06 | 2023-11-06 |  |  |  | No303_title_number_of_property_not_correct_06_11_2023_Sharan_N_P
304 | 2023-11-03 | Issue | Live | All Properties | property is not let agreed but it shows Yes 11, Kenerne Drive, Barnet, London, EN5 2NW |  | Ashik | Completed
305 | 2023-11-06 | Issue | Live | Live Campaign | 2nd instruction, targeted - when many addresses are selected for local print, the preview takes a lot of time or it just keeps loading |  | Sharan | Completed | Urgent |  |  | 2023-11-06 | 2023-11-06 |  |  |  | No307_live_campaign_loading_multiple_times_06_11_2023_Sharan_N_P
306 | 2023-11-06 | Issue | Live | Live Campaign | 2nd instruction bulk mail - when sending letters to multiple addresses, after clicking on Confirm and send bulk mail button it doesnt show the bulk mail confirmation pop up https://tinyurl.com/ympufkzv |  | Sharan | Completed
307 | 2023-11-06 | Issue | Live | Live Campaign | targeted - when viewing the preview for local print it loads multiple times and then only can the user see the letter preview |  | Sharan | Completed
308 | 2023-11-07 | Issue | Live | Property Detail Page | shows an error page when we click on any of the properties https://tinyurl.com/yuc5s4zx |  | Sharan | Completed | Urgent |  |  | 2023-11-07 | 2023-11-07
309 | 2023-11-07 | Suggestion | Live | UI Changes | delete confirmation pop up is in the old format 1. Settings: Company Icon, Report Logo, Team Image 2. Letter Management - confirmation pop up shown when we delete letters 3. Targeted detail page - confirmation pop up shown when deleting comments |  | Sharan | Hold | Low |  |  | Hold | Hold |  |  | please speak to Sandeep regarding this
310 | 2023-11-07 | Issue | Live | Dashboard | 30 Days+ count not correct 31-90 days |  | Sharan | Completed | Medium |  |  | 2023-11-08 | 2023-11-08
311 | 2023-11-07 | Issue | Live | Live Campaign | local print preview - there is a delay in showing Preparing preview pdf loader after clicking on preview button |  | Sharan | Completed | Medium |  |  | 2023-11-08 | 2023-11-08 |  |  | please speak to Sandeep
312 | 2023-11-07 | Issue | Live | Property Detail Page | comparables section keeps loading in the detail page |  | Sharan | Completed | Medium |  |  | 2023-11-07 | 2023-11-07 |  |  |  | No312_mongodb_password_change_07_11_2023_Sharan_N_P
313 | 2023-11-07 | Issue | Live | Property Detail Page | comparable section keeps loading for addresses in EH11 outcode |  | Sharan | Completed | Medium |  |  | 2023-11-07 | 2023-11-07 |  |  |  | No313_comparable_keep_loading_07_11_2023_Sharan_N_P
314 | 2023-11-07 | Issue | Live | Quick Send | if the user's credit is low while attempting a quick send, a notification is displayed. However, if the user then selects fewer letters and sends, letters are sent to all the addresses in the quick send list even though the balance is low |  | Sharan | Completed | Medium |  |  | 2023-11-08 | 2023-11-08 |  |  | please speak to Abhijith regarding this issue | No314_bulksend_amount_issue_08_11_2023_Sharan_N_P
315 | 2023-11-07 | Issue | Live | Quick Send | If a user initially selects a few addresses, previews them, and then proceeds to deselect or add more addresses, the letters will be sent only to the addresses that were initially selected. to get the issue: 1. select few addresses from the bulk mail list 2. preview the letter 3. select more addresses or deselect addresses 4. send bulk mails |  | Sharan | Completed | Medium |  |  | 2023-11-09 | 2023-11-09 |  |  |  | No315_quicksend_preview_issue_09_11_2023_Sharan_N_P
316 | 2023-11-08 | Task |  | Settings | user details for lettings should be seperate and blank agent name shown in qr form profile report images email header (hi *name*) |  | Rijo | Hold | Medium |  |  | 2023-11-16 |  |  |  | 23 feb ======= wait for UK team confirmation
317 | 2023-11-09 | Issue | Live | Email | content when report is sent - property report attachment mail Dear *Name*, Please find the attached report with this mail. Thank you. LetsBid Team |  | Rijo | Completed | High |  |  | 2024-01-24 | 2024-01-24 | 2024-01-24 |  |  | 275_mail_issues_Rijo_24Jan24
318 | 2023-11-09 | Issue | Live | Email | property report attachment mail remove Sub: Property Report Attachment Mail shown with the mail content |  | Rijo | Completed | High |  |  | 2024-01-24 | 2024-01-24 | 2024-01-24 |  |  | 275_mail_issues_Rijo_24Jan24
319 | 2023-11-11 | Suggestion | Live | Property Listing | list of estate agent pop up - make the first letter capital for Platform |  | Sharan | Completed | Low |  |  | 2023-11-13 | 2023-11-13 |  |  |  | No319_Platform_spelling_mistakes_13_11_2023_Sharan_N_P
320 | 2023-11-11 | Suggestion | Live | Property Detail Page | list of estate agent pop up - make the first letter capital for Platform |  | Sharan | Completed | Low |  |  | 2023-11-13 | 2023-11-13 |  |  |  | No319_Platform_spelling_mistakes_13_11_2023_Sharan_N_P
321 | 2023-11-11 | Issue | Live | Property Detail Page | comparable section keeps loading 4/3, Easter Dalry Drive, Edinburgh, Midlothian, EH11 2TD |  | Sharan | Completed | Medium |  |  | 2023-11-13 | 2023-11-15 |  |  |  | No321_comparables_loading_13_11_2023_Sharan_N_P
322 | 2023-11-11 | Issue | Live | Rental Reduced | in campaign tag is not shown after adding properties to campaign, the tag is displayed only when the page is refreshed |  | Sharan | Completed | Medium |  |  | 2023-11-15 | 2023-11-15 |  |  |  | No322_campaign_tag_missing_rental_reduced_15_11_2023_Sharan_N_P
323 | 2023-11-11 | Issue | Live | Let Agreed | in campaign tag is not shown after adding properties to campaign, the tag is displayed only when the page is refreshed |  | Sharan | Completed | Medium |  |  | 2023-11-15 | 2023-11-15 |  |  |  | No322_campaign_tag_missing_rental_reduced_15_11_2023_Sharan_N_P
324 | 2023-11-11 | Issue | Live | Targeted Campaign | addresses are repeating in Neighbour Properties list for some addresses 3, Keepers Close, Hockley, Birmingham, West Midlands B18 5SN https://tinyurl.com/yr7emdew |  | Sharan | Hold | Low |  |  | Hold | Hold |  |  | Once Abhijith will completed the task in Letsbid
325 | 2023-11-11 | Issue | Live | Dashboard | campaign insight - 2nd instruction count is not correct |  | Sharan | Completed | Medium |  |  | 2023-11-16 | 2023-11-17 | 2024-01-24 |  |  | No325_campaign_insight_2nd_instruction_count_16_11_2023_Sharan_N_P
326 | 2023-11-11 | Issue | Live | All Properties | Let Agreed is shown as Yes even though it's still on market 35, Scarsdale Street, Dinnington, Sheffield, South Yorkshire, S25 2RN 58, Kettlebaston Road, London, Greater London, E10 7PF 64, Monkfrith Way, London, Greater London, N14 5ND 12, Franklyn Gardens, Nottingham, City Of Nottingham, NG8 3NZ 19, Maude Street, Connahs Quay, Deeside, Flintshire, CH5 4EQ Flat 20, Warner House, Abercorn Place, London, Greater London, NW8 9YA 1, Greythorn Drive, West Bridgford, Nottingham, Nottinghamshire NG2 7GG 117, Silverdales, Dinnington, Sheffield, South Yorkshire, S25 2RS |  | Not Assigned | Closed | High
327 | 2023-11-11 | Issue | Live | All Properties | it doesnt show price reduced in Rightmove but in the detail page it shows that the price has been reduced for the property 58, Kettlebaston Road, London, Greater London, E10 7PF |  | Ashik | Completed | Medium
328 | 2023-11-11 | Issue | Live | All Properties | properties are let agreed in Rightmove but not updated on our platform check after next run: 24, Ealham Close, Willesborough, Ashford, Kent, TN24 0UQ |  | Rishika | Completed | Medium
329 | 2023-11-13 | Issue | Live | All Properties | property type error |  | Sharan | Completed | Medium |  |  | 2023-11-15 | 2023-11-16 |  |  |  | No329_property_type_error_16_11_2023_Sharan_N_P
330 | 2023-11-13 | Issue | Live | All Properties | in the listing the property type is given as Not Specified but in the detail page the type is given 65, Godwin Way, Stoke-on-trent, ST4 6JP 35, Ardmore Close, Nottingham, City Of Nottingham, NG2 4GP 7, Baden Powell Street, Gateshead, Tyne And Wear, NE9 5LD |  | Sharan | Completed | Medium |  |  | 2023-11-16 | 2023-11-16
331 | 2023-11-14 | Issue | Live | Property Report | Ofcom error |  | Sharan | Completed | Medium |  |  | 2023-11-15 | 2023-11-15 |  |  |  | No331_Ofcom_error_15_11_2023_Sharan_N_P
332 | 2023-11-15 | Task |  | Targeted | 20-20 button on Targeted |  | Sharan | Hold | Medium
333 | 2023-11-15 | Task |  | Direct Mail Anywhere | direct mail anywhere feature |  | Rijo | Completed | High |  |  | 2023-12-15 | 2023-12-27 | 2023-12-29
334 | 2023-11-15 | Issue | Live | Admin | lettings platform not activated when the email address is not same |  | Rijo | Completed | Medium
334 | 2023-11-16 | Task | Live | Targeted | Server Error on targeted detail page |  | Sharan | Completed | Urgent |  |  | 2023-11-16 | 2023-11-16 |  |  |  | No334_server_error_targeted_detail_page_16_11_2023_Sharan_N_P
336 | 2023-11-27 | Issue | Live | Property Detail Page | property has images but in the detail page it shows broken image |  |  | Closed | Medium
337 | 2023-11-28 | Issue | Live | QR | 20-20 campaign and targeted letters - shows server error when we scan qr code in the letter |  | Sharan | Completed | High |  |  | 2024-01-17 | 2024-01-17 |  |  |  | No337_qr_code_server_error_17_01_2023_Sharan_N_P
338 | 2023-11-28 | Issue | Live | All Properties | the property type is in capital in the listing |  | Sharan | Completed | Medium |  |  | 2024-01-17 | 2024-01-17 |  |  |  | No337_qr_code_server_error_17_01_2023_Sharan_N_P
339 | 2023-11-28 | Issue | Live | Property Detail Page | please make sure the latest price is shown in the detail page, the price in listing and detail page are different 4, Far End, Hatfield, Hertfordshire, AL10 8UG |  | Sharan | Closed | Medium |  |  | 2024-02-20 | 2024-02-20 |  |  |  | No339_property_detail_page_latest_listing_data_20_02_2024_Sharan_N_P
340 | 2023-11-28 | Issue | Live |  | Mongo DB Driver |  | Sharan | Completed | High | [7 empty] | No340_mongo_db_driver_29_11_2023_Sharan_N_P
341 | 2023-11-29 | Issue | Live | Summary | bulk mail letter sent counts are not correct: 2nd instruction, 20-20, targeted, Direct mail anywhere this happens when we sent bulk mail for these campaigns in prospecting tool |  | Sharan | Completed | High |  |  | 2024-01-18 | 2024-01-18 | 2024-01-24 |  |  | No342_bulk_mail_count_error_in_dashboard_and-_summary_18_01_2024_Sharan_N_P
342 | 2023-11-29 | Issue | Live | Dashboard | bulk mail letter sent counts are not correct: 2nd instruction, 20-20, targeted, Direct mail anywhere this happens when we sent bulk mail for these campaigns in prospecting tool |  | Sharan | Completed | High |  |  | 2024-01-18 | 2024-01-18 | 2024-01-24 |  |  | No342_bulk_mail_count_error_in_dashboard_and-_summary_18_01_2024_Sharan_N_P
343 | 2023-11-29 | Suggestion | Live | Property Report | in the targeted detail page comparables are shown but when generating a report there are no comparables the comparables are shown only if the agent enters custom values |  | Sharan | Completed | Medium | [6 empty] | Targeted Detail Page : Fetch comparables based on which all are variables you have Report and Other pages : current_postcode_id, property_type, square_feet, bed_rooms these variables are compulsory any variable is missing we don't get comparables (This is the perfect comparable logic) For targeted these values we can't get it so we didn't change the targeted logic
344 | 2023-11-29 | Issue | Live | Live Campaign | 2nd instruction local print preview - there is a delay in showing Preparing preview pdf loader after clicking on preview button |  | Sharan | Completed | Medium |  |  | 2024-01-17 | 2024-01-17
345 | 2023-12-01 | Issue | Live | Targeted | Targeted filter updated |  | Sharan | Completed | Medium |  |  | 2023-12-01 | 2023-12-01 |  |  |  | No345_targeted_filter_update_01_12_2023_Sharan_N_P
346 | 2023-12-01 | Issue | Live | Wallet | credit top up not working |  | Rijo | Completed | High
347 | 2023-12-08 | Issue | Live | Quick Send | preview issue - please show the confirmation message only after user has previewed the letter |  | Sharan | Completed | Medium |  |  | 2024-02-20 | 2024-02-20 | 2024-03-04 |  |  | No347_quick_sent_peview_issue_20_02_2024_Sharan_N_P
348 | 2023-12-08 | Issue | Live | Quick Send | quick send preview takes time save and show only the preview of the first address in the quick send mail list as there is a delay in showing the preview |  | Sandeep | Closed | Medium
349 | 2023-12-12 | Issue | Live | Targeted | shows dangerous site message when we click on any targeted property shorten url |  | Sharan | Completed | High |  |  | 2024-01-15 | 2024-01-15 | 2024-01-24 |  |  | No349_targeted_shorten_url_15_01_2024_Sharan_N_P
350 | 2023-12-14 | Task | Live |  | Mongo DB Driver |  | Sharan | Completed | High |  |  | 2023-12-14 |  | 2023-12-29 |  |  | No350_Mongo_db_driver_14_12_2023_Sharan_N_P
351 | 2023-12-22 | Issue | Live | Property Detail Page | sold history section is missing for some addresses Apartment 10, Barons Court, Barons Close, Kirby Muxloe, Leicester, Leicestershire, LE9 2BU |  | Sharan | Completed | Medium |  |  | 2024-01-18 | 2024-01-18 | 2024-01-24 |  |  | No351_sold_history_error_in_property_details_page_18_01_2024_Sharan_N_P
352 | 2023-12-22 | Issue | Live | Property Report | title number is not shown in the report |  | Sharan | Completed | Medium |  |  | 2024-01-24 | 2024-01-24 |  |  |  | No352_title_number_error_24_01_2024_Sharan_N_P
353 | 2023-12-22 | Issue | Live | Targeted | Other properties owned by the company section 1. postcode in the address is in small letter 2. please make the first letter capital http://tinyurl.com/yv9eu3n3 |  | Sharan | Completed | Medium |  |  | 2024-01-17 | 2024-01-17 | 2024-01-24 |  |  | No349_targeted_shorten_url_15_01_2024_Sharan_N_P
354 | 2023-12-28 | Issue | Live | Direct Mail Anywhere | nothing happens when we click on View button |  | Sharan | Completed | Medium |  |  | 2024-01-22 | 2024-01-22 |  |  |  | No354_direct_mail_anywhere_view_button_22_01_2024_Sharan_N_P
355 | 2023-12-28 | Issue | Live | Dashboard | direct mail anywhere - bulk mail count not correct |  | Sharan | Closed | Medium
356 | 2023-12-28 | Issue | Live | Summary | direct mail anywhere - bulk mail count not correct |  | Sharan | Closed | Medium
357 | 2023-12-28 | Issue | Live | Live Campaign | direct mail anywhere - remove in edit address for local print does not work, even if we remove addresses letters are still printed for these addresses |  | Sharan | Completed | Medium |  |  | 2024-01-22 | 2024-01-23 |  |  |  | No357_direct_mail_anywhere_edit_address_23_01_2024_Sharan_N_P
358 | 2023-12-28 | Issue | Live | Wallet | when credits are deducted for Direct Mail Anywhere Bulk Mail please change the title in wallet accordingly |  | Sharan | Completed | Medium |  |  | 2024-01-19 | 2024-01-19 | 2024-01-24 |  |  | NO358_please_change_the_title_in_wallet_accordingly_19_01_2024_Sharan_N_P
359 | 2023-12-28 | Issue | Live | Dashboard | Campaigns ¦ Last 30 Days graph not correct |  | Sharan | Completed | Medium |  |  | 2024-01-19 | 2024-01-19 | 2024-01-24 |  |  | No359_Campaign_doughnut_charts_dasboard_19_01_2024_Sharan_N_P
360 | 2023-12-28 | Issue | Demo | Live Campaign | second instruction tab - please change the title http://tinyurl.com/yktqeutt |  | Rijo | Completed | Medium
361 | 2023-12-28 | Issue | Demo | Live Campaign | direct mail anywhere - print preview does not work when the address has house name and side panel is enabled |  | Rijo | Completed | High
362 | 2023-12-28 | Issue | Demo | Live Campaign | direct mail anywhere - local print does not work when the address has house name and side panel is enabled |  | Rijo | Completed | High
363 | 2023-12-28 | Issue | Demo | Live Campaign | direct mail anywhere - shows an error page when we do bulk mail , if the address has house name and side panel is enabled |  | Rijo | Completed | High
364 | 2023-12-29 | Suggestion | Live | Direct Mail Anywhere | after adding few properties to campaign the searched postcode gets cleared |  | Sharan | Testing | Low |  |  | 2024-11-15 | 2024-11-15 | 2024-12-17 |  |  | No364_DMA_postcode_session_set_Sharan_N_P_15_11_2024
365 | 2023-12-29 | Suggestion | Live | Live Campaign | direct mail anywhere - remove all property popup - Display the text across the entire width of the popup - please change the text of the pop up to: Are you sure you want to remove all properties? Please confirm on removing all the properties from campaign https://tinyurl.com/yryrgjta |  | Sharan | Completed | Low |  |  | 2024-02-08 | 2024-02-08 |  |  |  | No365_dma_remove_campaign_msg_change_08_02_2024_Sharan_N_P
366 | 2023-12-29 | Suggestion | Live | Direct Mail Anywhere | When users choose multiple addresses to add into the campaign, they need to scroll to the top of the page to access the button. Unlike other pages where the button remains fixed at the top while scrolling |  | Rijo | Completed | Medium |  |  | 2024-01-24 | 2024-01-24 | 2024-01-24 |  |  | no366_DirectMailAnywhere_fixed-component_edit_Rijo24Jan24
367 | 2024-01-08 | Issue | Live | Wallet | please make sure that the titles for credits deducted for prospecting campaign are similar to that shown in prospecting wallet Planning Bulk Mail Payment - shown as Bulk Mail Payment in lettings side Active Buyer Bulk Mail Payment - shown as Bulk Mail Payment in lettings side Twenty Target Bulk Mail Payment - shown as Twenty Bulk Mail Payment in lettings side |  | Sharan | Completed | Low |  |  | 2024-02-08 | 2024-02-08 | 2024-03-04
368 | 2024-01-08 | Issue | Live | Targeted Campaign | shows something went wrong when we try bulk mail or local print in targeted campaign |  | Sharan | Completed | High |  |  | 2024-01-08 | 2024-01-08 |  |  |  | N0368_Mongo_error_08_01_2024_Sharan_N_P
369 | 2024-01-11 | Task | Live | Property Report | NHS response time issue |  | Rijo | Completed | High
370 | 2024-01-12 | Issue | Live | Campaign History | when in 20-20 and targeted tabs, direct mail anywhere tab is missing |  | Rijo | Completed | Medium |  |  | 2024-02-14 | 2024-02-16 | 2024-02-19 |  | update 16 feb 24 ========== please test Letter management Live Campaign tabs Letter history | no370_missing_tabs_Rijo_14feb24
371 | 2024-01-22 | Issue | Demo | Letter | targeted letter - when we scan the qr in the targeted letter sent to company address, the address is not shown in the form |  | Sharan | Completed | Medium |  |  | 2024-01-23 | 2024-01-23 |  |  | no issue in live | No371_Qr_company_address_targeted_23_01_2024_Sharan_N_P
372 | 2024-01-22 | Issue | Live | Letter | dma letter - when we scan the qr in DMA letter the address is not shown in the form |  | Sharan | Completed | Medium |  |  | 2024-01-23 | 2024-01-23 |  |  |  | No372_Qr_error_dma_23_01_2024_Sharan_N_P
373 | 2024-01-24 | Issue | Live |  | properties missing on lettings platform - need to recheck after next run AL10 https://www.rightmove.co.uk/properties/143943332#/?channel=RES_LET |  | Rishika | Closed | Medium
374 | 2024-01-26 | Task | Live | Targeted | remove all properties from targeted that do not have company data 1, Fountain Square, Stoke-on-trent, ST1 1LE |  | Sharan | Completed | Medium |  |  | 2024-02-08 | 2024-02-08 |  |  |  | No374_targeted_removed_no_company_data_08_02_2024_Sharan_N_P
375 | 2024-02-05 | Task | Live |  | company owned changes made on sales prospecting tool should be implemented here company owned tag missing in the report 51, Market Place, Hornsea, East Riding Of Yorkshire HU18 1AP 5, Shuttleworth Court, Hornsea, Yorkshire, HU18 1PP 8, Birinus Close, High Wycombe, HP12 3LZ 21, Laurel Bank Mews, Bromsgrove, Worcestershire, B60 1PD 10a, Austin Avenue, Bromley, Kent, BR2 8AJ 13, Norton Road, Luton LU3 2NX |  | Sharan | Closed | Medium |  |  | 2024-02-13 | 2024-02-13 | 2024-03-19 |  | cannot check in demo | No375_company_owned_changes_13_02_2024_Sharan_N_P
376 | 2024-02-05 | Issue | Live | Property Report | if habitable room is 0 don't display it in the report 7, Gloucester Drive, Southampton, Hampshire, SO31 7PE |  | Sharan | Completed | Medium |  |  | 2024-02-07 | 2024-02-07 |  |  |  | No376,377_epc_habitable_rooms_08_02_2024_Sharan_N_P
377 | 2024-02-05 | Issue | Live | Property Report | EPC page - if habitable room is 0 in the EPC page please shown Not Available 7, Gloucester Drive, Southampton, Hampshire, SO31 7PE Summerhill House, Fingest Lane, Bolter End, High Wycombe, Buckinghamshire HP14 3LS |  | Sharan | Completed | Medium |  |  | 2024-02-07 | 2024-02-08 |  |  |  | No376,377_epc_habitable_rooms_08_02_2024_Sharan_N_P
378 | 2024-02-06 | Issue | Live | DMA Campaign | remove the comma after the building number when pushing to Stannp |  | Sharan | Completed | Medium |  |  | 2024-02-07 | 2024-02-07 | 2024-02-19 |  | status is Pending for the letters in campaign history - solved | No378_dma_address_correction_07_02_2024_Sharan_N_P
379 | 2024-02-07 | Issue | Demo | Settings | Profile - no data |  | Rijo | Hold | Medium | [6 empty] | Incomplete task in demo Rijo
380 | 2024-02-07 | Issue | Demo | Letter Management | getting an error page when we create a letter http://tinyurl.com/2bbmqwkm |  | Sharan | Completed | Medium |  |  | 2024-02-07 | 2024-02-07
381 | 2024-02-08 | Issue | Live | Property Report | Clean the url after download report |  | Sharan | Completed | Medium |  |  | 2024-02-08 | 2024-02-08 |  |  |  | No381_Report_url_clear_08_02_2024_Sharan_N_P
382 | 2024-02-09 | Issue | Live | Property Report | Planning dates error 18, Steel Close, Bromsgrove, Worcestershire, B60 3GQ |  | Sharan | Completed | Medium |  |  | 2024-02-09 | 2024-02-09 | 2024-02-19 |  |  | No382_report_planning_date_error_09_02_2024_Sharan_N_P
383 | 2024-02-13 | Issue | Demo | Targeted Campaign | local print and bulk mail not working, getting an error page when we send bulk mail http://tinyurl.com/26tq3noy |  | Sharan | Completed | Medium |  |  | 2024-02-14 | 2024-02-14
384 | 2024-02-13 | Issue | Demo | 20-20 Campaign | local print and bulk mail not working, getting an error page when we send bulk mail http://tinyurl.com/27m6dbvm |  | Sharan | Completed | Medium |  |  | 2024-02-14 | 2024-02-14
385 | 2024-02-13 | Issue | Demo | 2nd Instruction Campaign | local print and bulk mail not working |  | Sharan | Completed | Medium |  |  | 2024-02-14 | 2024-02-14
386 | 2024-02-13 | Issue | Demo | Property Report | not able to generate report |  | Sharan | Completed | Medium |  |  | 2024-02-14 | 2024-02-14
387 | 2024-02-19 | Task | Live | Property Report | Lettings Reports - Need to remove sold comps/ sold prices/ on market sales comps pre ticked and need to input let agreed comps ticked. |  | Sharan | Completed | Medium |  |  | 2024-02-19 | 2024-02-19 | 2024-03-04 |  |  | No387_landlord_custom_pages_19_02_2024_Sharan_N_P
388 | 2024-02-19 | Issue | Live | Property Report | from the Select sections page if we click on the back button 3-4 times, on returning to Select sections page the Submit button is missing user will have to go back again and then return to submit |  | Sharan | Completed | Medium |  |  | 2024-02-19 | 2024-02-19 | 2024-03-04 |  |  | No388_report_generate_button_hidden_19_02_2024_Sharan_N_P
389 | 2024-02-19 | Issue | Live | Targeted Campaign | PE38 - the postcodes are not shown once the address is added to the campaign the address in the listing has ' in the address and on adding to campaign, texts after the ' are not shown (please compare with Targeted in prospecting) |  | Sharan | Completed | Medium |  |  | 2024-02-19 | 2024-02-20 | 2024-03-04 |  |  | No389_targeted_PE38_address_error_19_02_2024_Sharan_N_P
390 | 2024-02-20 | Issue | Live | 20-20 Campaign | bulk mail, local print and remove buttons are not working |  | Sharan | Completed | Urgent |  |  | 2024-02-20 | 2024-02-20 | 2024-02-21 |  |  | No390_391_20_20_targeted_campaign_issues_20_02_2024_Sharan_N_P
391 | 2024-02-20 | Issue | Live | Targeted Campaign | bulk mail, local print and remove buttons are not working |  | Sharan | Completed | Urgent |  |  | 2024-02-20 | 2024-02-20 | 2024-02-21 |  |  | No390_391_20_20_targeted_campaign_issues_20_02_2024_Sharan_N_P
392 | 2024-02-20 | Issue | Live | Property Report | Hospitals / GP / Dentists / NHS page - Response spelling error http://tinyurl.com/22kuc3ol |  | Sharan | Completed | Medium |  |  | 2024-02-20 | 2024-02-20 | 2024-03-04 |  |  | No392_NHS_spelling_error_20_02_2024_Sharan_N_P
393 | 2024-02-20 | Suggestion | Live | Property Detail Page | the confirmation pop up shown when we delete a comment is in the old format http://tinyurl.com/2avdw4mw |  | Sharan | Completed | Low |  |  | 2024-02-21 | 2024-02-21 | 2024-03-04 |  |  | No393_Detail_page_delete_comment_21_02_2024_Sharan_N_P
394 | 2024-02-20 | Issue | Live | Property Detail Page | quick send pop up - the column names are not shown above the correct data http://tinyurl.com/25wv8wnd |  | Sharan | Completed | Medium |  |  | 2024-02-20 | 2024-02-20 | 2024-03-04 |  |  | No394_Quick_send_popup_column_error_20_02_2024_Sharan_N_P
395 | 2024-02-20 | Issue | Live | Targeted | shows 1 Row Selected at the bottom (near page numbers) when we select a property or click somewhere near the address |  | Sharan | Completed | Low |  |  | 2024-02-21 | 2024-02-21 | 2024-03-04 |  |  | No395_targeted_rows_selected_21_02_2024_Sharan_N_P
396 | 2024-02-20 | Issue | Live | Property Report | Rental Comparables - even after giving custom values, no rental comparables are shown in the report but when we check in the detail page there are comparables 87, High Street, Snodland, Tonbridge And Malling, Kent, ME6 5AN 1C, Claremont Road, London, NW2 1BP |  | Sharan | Completed | Medium | [6 empty] | Connected to 343 --------------------- Targeted Detail Page : Fetch comparables based on which all are variables you have Report and Other pages : current_postcode_id, property_type, square_feet, bed_rooms these variables are compulsory any variable is missing we don't get comparables (This is the perfect comparable logic) For targeted these values we can't get it so we didn't change the targeted logic
397 | 2024-02-21 | Task | Live | Property Detail Page | when doing quick send in the detail page, show the edit box first | UI | Sandeep | Not Started | Medium
398 | 2024-02-27 | Issue | Live | Property Detail Page | when doing quick send if we preview the letter and close the pop up or send letters, the button changes to Added to Campaign |  | Sharan | Completed | Medium |  |  | 2024-02-28 | 2024-02-28 | 2024-03-19 |  |  | No398_Quick_send_added_to_campaign_28_02_2024_Sharan_N_P
399 | 2024-02-27 | Task | Live | Live Campaign | Local Print - When agents choose this option sometimes the PDF comes up when it says letters to print sometimes it doesnt so we need to add in some text on that last box to say something like 'All pdf letters to print can be found via campaign history' clarify wording with Milton. |  | Sharan | Completed | Medium |  |  | 2024-02-28 | 2024-02-28 | 2024-03-19 |  |  | No399_Report_print_letter_text_change_28_02_2024_Sharan_N_P
400 | 2024-03-01 | Issue | Live | Property Report | planning dates not correct for the property 1, Steel Close, Bromsgrove, Worcestershire, B60 3GQ 15, Railway Walk, Bromsgrove, Worcestershire, B60 3GJ 17, Railway Walk, Bromsgrove, Worcestershire, B60 3GJ please check if there is any issues with the dates for Bromsgrove |  | Sharan | Completed | Medium |  |  | 2024-03-08 | 2024-03-08 |  |  |  | No400_report_planning_date_error_08_03_2024_Sharan_N_P
401 | 2024-03-01 | Issue | Live | Property Report | planning dates missing in report 31, Illshaw Close, Redditch, B98 0QY 6, Alton Close, Redditch, Worcestershire, B97 5XH 210, Barnet Road, Potters Bar, Hertsmere, Hertfordshire, EN6 2SE |  | Sharan | Completed | Medium |  |  | 2024-03-08 | 2024-03-08 |  |  |  | No400_report_planning_date_error_08_03_2024_Sharan_N_P
402 | 2024-03-04 | Issue | Live | Property Listing | property type in the listing page has _ in between the texts https://tinyurl.com/yvqhp6ez |  | Sharan | Completed | Low |  |  | 2024-10-14 | 2024-10-14 | 2024-10-24 |  |  | No402_property_type_hyphen_Sharan_N_P_14_10_2024
403 | 2024-03-04 | Issue | Live | Property Listing | property type is shown as Unknown in the listing page (no issue in detail page) when checked in Rightmove/Zoopla the property type is House 90, Cheveral Avenue, Coventry, West Midlands, CV6 3EF 19, Turnstone Gardens, Lordswood, Southampton, SO16 8EW |  | Rijo | Closed | Medium
404 | 2024-03-04 | Suggestion | Live | Targeted | page numbers overlap the no. of entries when we move to another page https://tinyurl.com/ylhybtk6 |  | Satheesh | Closed | Low | [6 empty] | It will be corrected once the design change was done.
405 | 2024-03-04 | Issue | Live | Let Agreed | after doing quick send, the button remains as Added to campaign |  | Sharan | Completed | Medium |  |  | 2024-03-20 | 2024-03-20 |  |  | Can't regenerate the issue
406 | 2024-03-04 | Issue | Live | Property Report | not able to generate reports |  | Rijo | Completed | Urgent
407 | 2024-03-06 | Issue | Live | Targeted | Compnay Owned properties missing 326, Lincoln Road, Enfield, EN3 4AA 328, Lincoln Road, Enfield, EN3 4AA |  | Sharan | Completed | High |  |  | 2024-03-06 | 2024-03-06 | 2024-03-19 |  |  | No407_company_owned_properties_missing_06_03_2024_Sharan_N_P
408 | 2024-03-11 | Task |  |  | Lettings redesign |  | Satheesh | Completed | High |  | 8 days | 2024-03-12 | 2024-03-22
409 | 2024-03-13 | Task |  | Selective Licensing | selective licensing - add to lettings if address available for landlord send to landlord address, if not available send letter to property address |  | Rijo | Completed | Medium |  | 3 days | 2024-04-25
410 | 2024-03-14 | Issue | Live | Targeted | targeted url shorten |  | Sharan | Completed | High |  | 1 day | 2024-03-14 | 2024-03-15 | 2024-03-20 |  |  | No410_targeted_detail_page_url_shorten_15_03_2024_Sharan_N_P
411 | 2024-03-18 | Suggestion | Live | Quick Send | quick send in dashboard and detail page - after clicking on local print buttons the pop up doesn't close and also the buttons are not disabled agent can click on local print multiple times |  | Sharan | Test Staging | Medium |  | 1hr | 2024-03-20 | 2024-03-20 |  |  |  | No411_412_quick_send_modal_hide_20_03_2024_Sharan_N_P
412 | 2024-03-18 | Suggestion | Live | Property Detail Page | quick send in dashboard and detail page - after clicking on local print buttons the pop up doesn't close and also the buttons are not disabled agent can click on local print multiple times |  | Sharan | Test Staging | Medium |  | 1hr | 2024-03-20 | 2024-03-20 |  |  |  | No411_412_quick_send_modal_hide_20_03_2024_Sharan_N_P
413 | 2024-03-20 | Task |  |  | zoopla rentals |  | Rahul | Completed | High
414 | 2024-03-20 | Task | Live | Property Report | Static Datas are shifted to mongodb |  | Sharan | Completed | Medium |  | 4hrs | 2024-03-20 | 2024-03-20 |  |  |  | No414_Static_datas_shifted_to_mongo_db_20_03_2024_Sharan_N_P
415 | 2024-03-20 | Issue | Live | Property Report | customize report takes time to load |  | Sharan | Completed | Medium
416 | 2024-03-20 | Issue | Live | Targeted | when company registration number not provided - the other properties owned by company has wrong data eg: Flat 2, 17, Bower Road, Harrogate, North Yorkshire, HG1 1BE 81 not owned by that company |  | Sharan | Completed | High |  | 2hrs | 2024-03-20 | 2024-03-20 |  |  |  | No416_company_own_properties_company_registration_20_03_2024_Sharan_N_P
417 | 2024-03-21 | Task |  |  | Redesign support work |  | Rijo | Completed | High |  | 2 days | 2024-03-20 | 2024-03-22
418 | 2024-03-21 | Suggestion | Live | Targeted |  |  | Rijo | Closed | Low
419 | 2024-03-21 | Task |  | Property Report | report redesign |  | Satheesh | Completed | High
420 | 2024-03-21 | Task |  | Title Plan/Register | option to purchase title plan and title register (refer Propmarker) |  | Sharan | Completed | High |  | 2 weeks | 2024-03-22 |  |  |  |  | No420_Land_registry_feature_25_03_2024_Sharan_N_P
421 | 2024-03-21 | Task |  | Title Plan/Register | design for title plan/register page |  | Satheesh | Completed | High
422 | 2024-03-21 | UK Team | Live | Comparable Tool | Comparable tool add option to export data | UI | Sharan | Discuss | Medium
423 | 2024-03-21 | Task |  | HMO Register | hmo register - add to lettings if address available for landlord send to landlord address, if not available send letter to property address |  | Rijo | Completed | Medium |  | 3 days | 2024-04-04 | 2024-04-24 |  |  | updated Apr 24: * from the detail page when we return to the listing page, the first council is selected and data displayed is of Ashfield * getting error page for some addresses - Ipswich 68 Grimwade Street, Ipswich, Suffolk, IP4 1LW - https://tinyurl.com/2xt6w8ys 3B Bolton Lane, Ipswich, Suffolk, IP4 2BX - https://tinyurl.com/252udl9o * if license issued and expiry is not available, it is blank in the listing please show Not Available * please change the message shown when no address is available when we search - https://tinyurl.com/2xlm7ju5 * | No423_hmo_register_20_04_2024_Sharan_N_P
424 | 2024-03-26 | Issue | Live | Property Report | comparables are not shown but when we check the same address in prospecting we are getting comparables 8, Birinus Close, High Wycombe, HP12 3LZ 13, Norton Road, Luton LU3 2NX |  | Sharan | Completed | Medium
425 | 2024-03-26 | Issue | Live | Property Report | title number is not shown in the report 10a, Austin Avenue, Bromley, Kent, BR2 8AJ 8, Birinus Close, High Wycombe, HP12 3LZ 21, Laurel Bank Mews, Bromsgrove, Worcestershire, B60 1PD |  | Sharan | Completed | Medium |  |  | 2024-11-07 | 2024-11-07 | 2024-11-08 |  | 07/11/2024 Sharan N P Can't test in demo server, I will show you working model | No_425_Report_title_number_missing_Sharan_N_P_07_11_2024
426 | 2024-03-27 | Issue | Live | Property Detail Page | the deposit is given as Not Available in Zoopla but we are showing as £0 |  | Sharan | Duplicate Task | Medium
427 | 2024-04-03 | Issue |  | All Properties | properties are let agreed but it's given as No on lettings platform 89 Lime Grove, Sidcup, DA15 8PH 2 Claremont, High Street, Upper Beeding, Steyning, BN44 3HZ 27, Beckside, Hornsea, East Riding Of Yorkshire, HU18 1RT |  | Rijo | Closed | Medium
428 | 2024-04-03 | Issue |  | Filtered Properties | let agreed and withdrawn properties are shown in the filtered properties listing |  | Rijo | Completed | Medium
429 | 2024-04-09 | Issue |  | Property Detail Page | for some addresses in the detail page, the property type is given as NO DATA! House 34 Anstee Road, Shaftesbury, SP7 8GT 7 Mount Pleasant Lane, Bricket Wood, St. Albans, AL2 3UX https://tinyurl.com/2d369tue |  | Sharan | Completed | Medium |  |  | 2024-10-14 | 2024-10-14 | 2024-10-24 |  |  | No429_detail_page_property_type_error_Sharan_N_P_14_10_2024
430 | 2024-04-10 | Issue |  | Targeted | sold comparables keeps loading in the detail page for some addresses Apartment 12, Barons Court, Barons Close, Kirby Muxloe, Leicester, Hinckley And Bosworth, Leicestershire, LE9 2BU Flat 1, 75, High Street, Earl Shilton, Leicester, Hinckley And Bosworth, Leicestershire, LE9 7DH |  | Sharan | Closed | Medium
431 | 2024-04-10 | Issue |  | Rental Reduced | shows server error when we click on some address Flat 4, Lewis House, 173–175 Terminus Road, Eastbourne, BN21 3NX |  | Rijo | Completed | High |  | 1hr | 2024-04-18 | 2024-04-18 | 2024-04-18 |  |  | No431_rental_reduced_server_error_issue_18Apr24
432 | 2024-04-11 | Issue |  | Title Plan/Register | in the history section, please change the title to Title Plan/Register History |  | Sharan | Completed | Medium |  |  | 2024-05-31 | 2024-05-31 |  |  |  | No432_title_plan_portal_property_letagreed_update_Sharan_N_P_31_05_2024
433 | 2024-04-11 | Issue |  | Title Plan/Register | title numbers are not shown for some addresses |  | Sharan | Closed | High
434 | 2024-04-11 | Issue |  | Title Plan/Register | if user has already selected an address and then searches the suggestions dropdown is shown underneath https://tinyurl.com/26mv3ews |  | Sharan | Closed | Medium
435 | 2024-04-11 | Issue |  | Property Listing | if a property has multiple listing and one of the listing is withdrawn, should the price shown in the listing and detail page be that of the listing that is active? 27a Ulleswater Road, Southgate, N14 7BL |  | Rijo | Closed | Medium
436 | 2024-04-11 | Issue | Live | Property Listing | the count shown for RM and Z icons are not aligned properly https://tinyurl.com/2crh2nda |  | Sharan | Completed | Low |  |  | 2024-11-15 | 2024-11-15 | 2024-11-21 |  |  | No436_platform_count_align_Sharan_N_P_15_11_2024
437 | 2024-04-17 | Issue |  | Targeted | Properties owned by the company code change |  | Sharan | Test Staging | High |  | 2024-04-17 | 2024-04-17 | 2024-04-17 |  |  |  | No437_company_owned_code_change_17_04_2024_Sharan_N_P
438 | 2024-04-18 | Suggestion | Live | Title Plan/Register | if the agent has already bought a title plan or title register for the searched address, please show a message asking to check in the history (similar to propmarker) |  | Rijo | Not Started | Medium
439 | 2024-04-18 | Suggestion |  | Title Plan/Register | please change the breadcrumb to Title Plan & Find owner |  | Sharan | Completed | Medium |  |  | 2024-10-14 | 2024-10-14 | 2024-10-24 |  |  | No439_Title_plan_register_breadcrumb_Sharan_N_P_14_10_2024
440 | 2024-04-18 | Issue |  | Let Agreed | property is not let agreed but it shows Yes 14, Park Place, Park Street, St. Albans, Hertfordshire, AL2 2RQ |  | Sharan | Closed | Medium |  |  | 2024-05-31 | 2024-05-31 |  |  |  | No432_title_plan_portal_property_letagreed_update_Sharan_N_P_31_05_2024
441 | 2024-04-22 | UK Team |  | Property Report | show a page showing recently sold properties for other property types Other Property Type on Street * if the property is semi detached, in this page we will be showing Terraced and Detached proeprties * if property is detached, in this page we will be showing Semi-detached and terraced * if property is terraced, in this page we will show detached and semi-detached * For Flat, we will be shown Maisonette and terraced |  | Sharan | Discuss | Medium | [6 empty] | 15/11/2024 Sharan N P Check with UK Team weather to increase the sold data
442 | 2024-04-22 | Task |  | Property Report | comparables - change it to the same logic as Propmarker |  | Sharan | Completed | High |  |  | 2024-08-23 | 2024-08-23
443 | 2024-04-22 | Issue | Live | Targeted | in the detail page under "other properties owned by company", properties are missing 328, Lincoln Road, Enfield, EN3 4AA 326, Lincoln Road, Enfield, EN3 4AA |  | Sharan | Completed | Medium |  |  | 2024-11-18 | 2024-11-18 | 2024-11-21 |  |  | No443_details_company_owned_properties_Sharan_N_P_18_11_2024
444 | 2024-04-22 | Issue |  | Targeted | even if property has comparables in the detail page only if we give custom values comparables are shown (in prospecting if there are comparables for the property, it is shown in the report without giving custom values) |  | Sharan | Closed | Medium
445 | 2024-04-22 | Issue |  | Targeted | Sold comparable section keeps loading in the detail page 6, Croft Road, Cosby, Leicester, Blaby, Leicestershire, LE9 1RE |  | Sharan | Closed | Medium
446 | 2024-04-23 | UK Team |  | Property Report | add a page for Let agreed properties in the area 1 miles |  | Sharan | Discuss | Medium
447 | 2024-04-25 | Issue |  | HMO Register | from the detail page when we return to the listing page, by default the first council is shown please make sure the selected council is shown |  | Sharan | Completed | Medium
448 | 2024-04-25 | Issue |  | HMO Register | getting an error page when we select some councils Windsor and Maidebhead Breckland Cheshire East Epsom and Ewell Gloucester Harlow North Hertfordshire |  | Rijo | Completed | High |  | 3hrs | 2024-04-25 | 2024-04-25 |  |  |  | No448_address_key_exist_25_04_2024_Sharan_N_P
449 | 2024-04-29 | Issue |  | Wallet | if agents have purchased title plan or title register, in the wallet the title is given as Top Up |  | Rijo | Completed | Medium
450 | 2024-04-29 | Issue |  | Wallet | if agents purchase title plan/register, please check if credits are being added |  | Rijo | Completed | High
451 | 2024-04-30 | Issue | Demo | Selective Licensing | in the detail page, all the data is shown as not available even if it's available |  | Rijo | Completed | High
452 | 2024-04-30 | Suggestion | Demo | Selective Licensing | on clicking on the MANAGER AGENT NAME, it should open a google search (similar to probate) |  | Rijo | Completed | Medium
453 | 2024-04-30 | Issue | Live | Selective Licensing | the property address in the listing and the address shown when we go into the detail page are different - the building number is not shown in the detail page Wirral Flat 3, 29A Wright Street, Egremont, Wallasey, Wirral, CH44 8BD Southwark Flat 8 41, East Dulwich Road, London, SE22 9AN |  | Sharan | Completed | Medium |  |  | 2024-11-11 | 2024-11-11 | 2024-11-13 |  |  | No453_selective_licensing_address_issue_Sharan_N_P_11_11_2024
454 | 2024-04-30 | Issue | Demo | Selective Licensing | in the detail page it's given as HMO Detail https://tinyurl.com/ywgbjtty |  | Rijo | Completed | Medium
455 | 2024-04-30 | Issue | Demo | Selective Licensing | shows a warning message when we click on the last page Ealing |  | Rijo | Completed | Medium
456 | 2024-04-30 | Issue | Demo | Selective Licensing | if LICENSE ISSUED and LICENSE EXPIRY dates are not available instead of showing blank in the listing please show Not Availabe |  | Rijo | Completed | Medium
457 | 2024-05-01 | Task | Live | Property Report | Report Static data take from mongo function update |  | Sharan | Test Staging | Medium |  | 2024-05-01 | 2024-05-01 |  |  |  |  | No457_Static_data_fetch_from_mongo_01_05_2024_Sharan_N_P
458 | 2024-05-09 | Issue | Live | Property Detail Page | if the deposit is given as Ask Agent in zoopla listing but we are showing it as £0 46 Aldermoor Road, Southampton, SO16 5NJ - https://www.zoopla.co.uk/to-rent/details/67297507/ 3 Jura Grove, Hartlepool, TS25 3PJ - https://www.zoopla.co.uk/to-rent/details/42353701/ 33 Mellowdew Road, Coventry, CV2 5GH - https://www.zoopla.co.uk/to-rent/details/68031806/ |  | Sharan | Duplicate Task | High
459 | 2024-05-09 | Issue | Live | Rental Reduced | zoopla activity not updated 37, Hay Close, Rushden, East Northamptonshire, Northamptonshire, NN10 0TT |  | Rishika | Completed | Medium
460 | 2024-05-27 | Task |  | Campaign History | option to redo campaign on clicking the redo button all the addresses in that campaign gets added to the respective campaign |  | Sandeep | Not Started | Medium
461 | 2024-05-30 | Issue | Live | Let Agreed | property is not let agreed but we have marked it as Yes Flat 5, Dundalk House, Clark Street, London, E1 3ET Apartment 1906, Crawford Building, 112 Whitechapel High Street, London, E1 7AQ Flat 68, Bernhard Baron House, 71 Henriques Street, London, E1 1LZ Flat 19, Burnham Court, Brent Street, London, NW4 2RE 11, Babington Road, London, Barnet, Greater London, NW4 4LD |  | Sharan | Completed | High |  |  | 2024-05-31 | 2024-05-31 |  |  |  | No432_title_plan_portal_property_letagreed_update_Sharan_N_P_31_05_2024
462 | 2024-05-30 | Issue | Live | Rental Reduced | rent reduced is not shown in the activity Apartment 8, Sterling Mansions, 75 Leman Street, London, E1 8EY Flat 9, 49 Crispin Street, London, E1 6HQ Flat 20, Lavender House, 1b Ratcliffe Cross Street, London, E1 0HS 30 Nelson Street, Stoke-on-trent, ST4 3QD Flat 3, Ray Mill Inn, Boulters Lock Island, Maidenhead, Windsor And Maidenhead, SL6 8PE |  | Unassigned | Closed | Medium
463 | 2024-05-30 | Issue | Live | Rental Reduced | in the listing activity it is shown as Withdrawn but the property is still On Market 6 Carisbrooke Way, Stoke-on-trent, ST4 8UR |  | Unassigned | Closed | Medium
464 |  |  |  | Let Agreed | Property is let agreed but we have marked it as No Flat 5, Dundalk House, Clark Street, London, E1 3ET |  | Rijo | Closed | Medium
465 | 2024-06-24 | Issue | Live |  | zoopla properties are not listed, the last listed for zoopla is 30 days ago |  | Rijo | Completed | Urgent
466 | 2024-06-24 | Issue | Live | Property Report | property is on market but when generating report it shows off market Flat 4, Lewis House, 173–175 Terminus Road, Eastbourne, BN21 3NX 3, Montrose Drive, Goole, Yorkshire, DN14 5XY |  | Rijo | Closed | Medium
467 | 2024-06-24 | Issue | Live | Property Detail Page | there are lots of sold data shown for the property, but when checked with sold history the last sold was 2018 High Cross, Loddington Lane, Belton In Rutland, Oakham, Rutland, LE15 9LA - https://lettings.letsbidproperty.co.uk/properties/p-241265 https://www.rightmove.co.uk/properties/api/soldProperty/transactionHistory/61460680 |  | Sharan | Completed | Medium |  |  | 2024-10-18 | 2024-10-18 | 2024-10-24 |  |  | No467_property_details_sold_history_Sharan_N_P_18_10_2024
468 | 2024-06-28 | Task | Live | Property Report | in the report please change to Current Market Price and instead of last sold change it to Last Let |  | Rijo | Closed | Medium
469 | 2024-06-28 | Task | Live | Property Report | sold data - shouldn't automatically pop up in the report they should have to select it |  | Rijo | Completed | Medium
470 | 2024-06-28 | Task | Live | Property Report | change the comparable logic |  | Sharan | Closed
471 | 2024-06-28 | Task | Live |  | Menu order Dashboard Property Reports Outcodes Properties Rental Reduced Let Agreed Targeted Direct Mail anywhere Title Plan HMO Selective Register Live Campaign Campaign History Letter Management Summary Settings |  | Sharan | Completed | Medium |  |  | 2024-10-14 | 2024-10-14 | 2024-10-24 |  |  | No471_menu_reorder_the-links_Sharan_N_P_14_10_2024
472 | 2024-06-28 | Task |  | Property Report | report revamp |  | Sharan | Completed | High |  |  | 2024-08-12 |  |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
473 | 2024-07-10 | Task |  | Property Report | Comparable logic change |  | Sharan | Completed | High |  |  | 2024-07-10 | 2024-07-16 |  |  |  | No473_comparable_logic_change_Sharan_N_P_11_07_2024
474 |  |  |  | Property Detail Page | comparable in property details page |  | Sharan | Completed | High |  |  | 2024-07-10 | 2024-07-16 |  |  |  | No473_comparable_logic_change_Sharan_N_P_11_07_2024
475 | 2024-07-15 | Issue | Live | Title Plan/Register | Title purchase payment errors |  | Sharan | Completed |  |  |  | 2024-07-15 | 2024-07-15 |  |  |  | No475_title_purchase_payment_error_Sharan_N_P_15_07_2024
476 | 2024-07-16 | Task | Live | Title Plan/Register | When ordering title plans on Lets bid or propmaker the charge is currently £3 for each document please increase this cost to £3.50 for each document as our card provider charges us per transaction |  | Rijo | Completed | Medium |  |  | 2024-11-11 | 2024-11-11 |  |  | developer testing
477 | 2024-07-22 | Issue | Live | Property Detail Page | getting server error page when we click on some addresses under Rental Comparables https://lettings.letsbidproperty.co.uk/properties/p-273338 |  | Sharan | Completed | High
478 | 2024-07-22 | Issue | Live | Property Report | on market sales comparable - shows server error when we click on the property addresses |  | Sharan | Completed | High
479 | 2024-07-22 | Issue | Live | Property Report | market analysis - Average Area Price/Sqft is not shown even if we have sold comparables |  | Sharan | Completed | High |  |  | 2024-08-23 | 2024-08-23 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
480 | 2024-07-22 | Issue | Live | Property Listing | if the deposit is given as Ask Agent in zoopla listing but we are showing it as £0 46 Aldermoor Road, Southampton, SO16 5NJ - https://www.zoopla.co.uk/to-rent/details/67297507/ 3 Jura Grove, Hartlepool, TS25 3PJ - https://www.zoopla.co.uk/to-rent/details/42353701/ 46 Aldermoor Road, Southampton, SO16 5NJ - https://www.zoopla.co.uk/to-rent/details/67297507/ 3 Jura Grove, Hartlepool, TS25 3PJ - https://www.zoopla.co.uk/to-rent/details/42353701/ 33 Mellowdew Road, Coventry, CV2 5GH - https://www.zoopla.co.uk/to-rent/details/68031806/ |  | Sharan | Completed | High |  |  | 2024-10-17 | 2024-10-17 | 2024-10-24 |  |  | No480_Property_listing_deposit_key_Sharan_N_P_14_10_2024
481 | 2024-07-22 | Issue | Live | Property Detail Page | if comparables are not available, please hide the column names Flat 5, Dundalk House, Clark Street, London, E1 3ET https://tinyurl.com/2bkf5wpo |  | Sharan | Completed | Low
482 | 2024-07-23 | Issue | Live | Targeted | from targeted detail page, when we click on any of the rental address please open it in a new tab when we click on the back button from the detail page it remains in the property detail page itself |  | Sharan | Completed | Medium
483 | 2024-07-23 | Issue | Live | Title Plan/Register | property type fetching issue for title plan |  | Sharan | Completed | High | [7 empty] | No483_title_purchase_log_error_Sharan_N_P_23_07_2024
484 | 2024-07-24 | Issue | Live | HMO Register | When back button clicked previously selected drop down return to default value |  | Sharan | Completed | High
485 | 2024-07-25 | Issue | Live | Property Report | comparables - remains at the bottom when we click on next or previous button |  | Sharan | Completed | Low |  |  | 2024-11-07 | 2024-11-07 | 2024-11-13 |  |  | No485_Report_comps_page_scroll_up_Sharan_N_P_07_11_2024
486 | 2024-08-04 | Issue | Live | Property Report | Comparables sort error and sold in street |  | Sharan | Completed | High |  |  | 2024-08-04 | 2024-08-04 |  |  |  | No486_comparable_sort_error_Sharan_N_P_04_08_2024
487 | 2024-08-04 | Issue | Live | Property Detail Page | when we do a quick send bulk mail, the campaign history is shown only when the page is refreshed | web | Sandeep | Not Started | Low
488 | 2024-08-04 | Issue | Live | Property Report | on market sale comparable and rental comparable - when we reset the filters, the filters are cleared but the comparables are shown below https://tinyurl.com/28e99sgg |  | Sharan | Completed | Medium |  |  | 2024-08-22 | 2024-08-22 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
489 | 2024-08-06 | Issue | Live | Property Report | EPC error |  | Sharan | Completed | Urgent |  |  | 2024-08-06 | 2024-08-06 | 2024-10-24 |  |  | No489_Report_epc_error_Sharan_N_P_06_08_2024
490 | 2024-08-12 | Task | Live | Census 2021 | Census 2021 Page |  | Sharan | Completed | Medium |  |  | 2024-10-25 | 2024-10-25 | 2024-10-25 |  | updated Aug 13: please add New tag in menu | Check the branch name while merging No490_Census_2021_page_Sharan_N_P_25_10_2024
491 | 2024-08-21 | Issue | Demo | Property Report | customise report page - it takes time to load doesnt take much time in sales |  | Sharan | Completed | Medium |  |  | 2024-08-22 | 2024-08-22 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
492 | 2024-08-21 | Issue | Demo | Property Report | property type, bed room is known for the property but in the comparable pop up it is not shown 270, Parkhouse Court, Hatfield, Hertfordshire, AL10 9RE |  | Sharan | Completed | Medium |  |  | 2024-08-22 | 2024-08-22 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
493 | 2024-08-21 | Issue | Demo | Property Report | on market rental comparable - comparable limit message is not shown if we select more than 8 comparable |  | Sharan | Completed | Medium |  |  | 2024-08-22 | 2024-08-22 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
494 | 2024-08-21 | Issue | Live | Property Report | no data is shown for average area price/sqft even though sold comparables are available |  | Sharan | Completed | Medium
495 | 2024-08-21 | Issue | Demo | Property Report | customise report page - when we click on OK in the alert pop up, it scrolls to the bottom of the page |  | Sharan | Completed | Medium |  |  | 2024-08-23 | 2024-08-23 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
496 | 2024-08-21 | Issue | Demo | Property Report | sold comparable and rental comparable pop - change the message shown below the filter Please select up to 8 properties to include in the report. If no properties are chosen, comparable properties will not be displayed in the report. |  | Sharan | Completed | Medium |  |  | 2024-08-27 | 2024-08-27 |  |  | https://tinyurl.com/23cj3pt9 | No472_Report_revamp_Sharan_N_P_12_08_2024
497 | 2024-08-21 | Issue | Live | Property Report | Default report color changed as Letsbid blue |  | Sharan | Testing | Medium |  |  | 2024-11-13 | 2024-11-13 | 2024-11-21 |  |  | No497_Report_default_color_Sharan_N_P_13_11_2024
498 | 2024-08-21 | Issue | Demo | Property Report | remove google image of property for off market address, the front page for off market properties should be our map for standard |  | Sharan | Completed | Medium |  |  | 2024-08-23 | 2024-08-23
499 | 2024-08-21 | Issue | Demo | Property Report | report history - shows 404 page when we click on view report |  | Sharan | Completed | Medium |  |  | 2024-08-23 | 2024-08-23
500 | 2024-08-21 | Issue | Demo | Property Report | company owned properties are not marked as Yes in the report |  | Sharan | Completed | Medium |  |  | 2024-08-23 | 2024-08-23 |  |  | updated Aug 26: works for on market properties but it's still not shown for Targeted properties updated Aug 27: need to check in live, as we are not getting title number in demo
501 | 2024-08-23 | Issue | Demo | Property Report | Default pages |  | Sharan | Completed | Medium |  |  | 2024-08-23 | 2024-08-23 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
502 | 2024-08-26 | Issue | Demo | Property Report | when Rental Comparables are selected by default for Landlord report, since no addresses are selected it won't be shown in the report |  | Sharan | Completed | Medium |  |  | 2024-08-27 | 2024-08-27 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
503 | 2024-08-26 | Issue | Demo | Property Report | please change the message shown when we try to select more than 8 addresses to You can select up to 8 comparables to display in the report. |  | Sharan | Completed | Medium |  |  | 2024-08-27 | 2024-08-27 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
504 | 2024-08-26 | Issue | Demo | Property Report | if it's an off market property, in the primary image section it shows a broken image icon https://tinyurl.com/2aq3sm83 |  | Sharan | Completed | Medium |  |  | 2024-08-27 | 2024-08-27 |  |  |  | No472_Report_revamp_Sharan_N_P_12_08_2024
505 | 2024-08-29 | Issue | Live | Property Report | Reports take time to download |  | Sharan | Completed | High
506 | 2024-09-02 | Task | Live | Summary | instruction received count |  | Sharan | Not Started | Medium
507 | 2024-09-03 | Issue | Live | Property Report | comparable property missing while change distance |  | Sharan | Completed | High |  |  | 2024-09-03 | 2024-09-03 | 2024-10-24 |  |  | No507_Report_comparable_sort_error_Sharan_N_P_03_09_2024
508 | 2024-09-03 | Issue | Live | Property Report | Report Speed cehck |  | Sharan | Completed | High |  |  | 2024-09-03 | 2024-09-03 |  |  |  | No508_Report_fetch_speed_check_Sharan_N_P_03_09_2024
509 | 2024-09-03 | Issue | Live | Property Report | market analysis - to calculate Average Area Price/Sqft, we need to change to minimum 3 sold comparables |  | Sharan | Completed | Medium |  |  | 2024-09-03 | 2024-09-03 | 2024-10-24 |  |  | No507_Report_comparable_sort_error_Sharan_N_P_03_09_2024
510 | 2024-09-03 | UK Team | Live | Targeted | in the detail page the comparables section needs to be expandable and collapsible. |  | Rijo | Completed | Medium
511 | 2024-09-03 | UK Team | Live | Property Detail Page | in the detail page the comparables section needs to be expandable and collapsible. |  | Rijo | Completed | Medium
512 | 2024-09-23 | Task |  | Property Report | comparables - shorten search radius to quarter and half mile. |  | Sharan | Completed | Medium |  |  | 2024-10-14 | 2024-10-14 | 2024-10-24 |  |  | No512_Comparables_shorten_radius_Sharan_N_P_14_10_2024
513 | 2024-09-23 | UK Team |  | Property Report | comparable cart system |  | Sharan | Completed | Medium | [7 empty] | No517_Report_connect_custom_values_table_Sharan_N_P_15_10_2024
514 | 2024-09-23 | UK Team |  | Property Report | there should be an option for the user to choose the primary image multiple images of the property will be listed and the agent can select from those |  | Sharan | Completed | Medium | [7 empty] | No517_Report_connect_custom_values_table_Sharan_N_P_15_10_2024
515 | 2024-10-09 | UK Team |  | Property Report | utility supplies should be enabled by default when generating a report |  | Rijo | Completed | Medium
516 | 2024-10-11 | Issue |  | Targeted | Incomplete sentence https://www.awesomescreenshot.com/image/51035258?key=50c1fe6e61e42eeb50cfa0029e068523 |  | Sandeep | Duplicate Task | Low
517 | 2024-10-15 | Task |  | Property Report | Connect to new custom values table Modify the property address Implement a comparable cart system Enable multiple image uploads and implement drag-and-drop for property images Implement other property type comparables |  | Sharan | Completed | Medium |  |  | 2024-10-15 |  | 2024-10-25 |  |  | No517_Report_connect_custom_values_table_Sharan_N_P_15_10_2024
518 | 2024-10-16 | Task |  | Property Listing | updating loader in the listing pages |  | Sandeep | Not Started | Medium
519 | 2024-10-16 | Task |  | Property Listing | Filtered by section UI |  | Sandeep | Not Started | Medium
520 | 2024-10-16 | UK Team |  | Property Report | property image page - Display property images side by side, across two pages (similar to the old report) |  | Sharan | Completed | High |  |  | 2024-11-05 | 2024-11-05 | 2024-11-06 |  | Issue No 542 | No542_report_proerty_images_page_Sharan_N_P_05_11_2024
521 | 2024-10-16 | UK Team |  | Property Listing | Add filters for bedroom count and price range (values similar to Rightmove), allowing multiple selections remove the platform filter. |  | Sandeep | In Progress | High |  | 1 week
522 | 2024-10-18 | Issue |  | Property Report | When the address is modified and the "Modify the selected property address" button is unchecked, the modified address is displayed . |  | Sharan | Completed | Medium | [7 empty] | No517_Report_connect_custom_values_table_Sharan_N_P_15_10_2024
523 | 2024-10-23 | UK Team |  | Property Report | On the reports section in customer values please add on bedroom count the option ‘studio’ |  | Sharan | Completed | Medium |  |  | 2024-11-07 | 2024-11-07 | 2024-11-13 |  |  | No523_report_property_type_studio_Sharan_N_P_07_11_2024
524 | 2024-10-25 | Issue |  | Property Listing | property type is shown as Unknown in the listing page |  | Sharan | Not Started | Medium | [6 empty] | Unknown : House, Town House, Barn Conversion, Parking
525 | 2024-10-25 | Issue | Live | Property Report | when we search some addresses that are currently on market it's shown as off market but shown as on market when we generate from the detail page Flat 6a, Parkside, High Street, Potters Bar, EN6 5AU https://lettings.letsbidproperty.co.uk/properties/p-417474 Flat 4, Lewis House, 173–175 Terminus Road, Eastbourne, BN21 3NX 3, Montrose Drive, Goole, Yorkshire, DN14 5XY |  | Sharan | Completed | Medium
526 | 2024-10-25 | Issue | Live | Property Report | additional property comparables page not shown in the report |  | Sharan | Completed | Medium
527 | 2024-10-25 | Issue | Live | Property Report | the images are repeating in the report 9, Torrington Drive, Potters Bar, Hertsmere, Hertfordshire, EN6 5HS 97, Kimptons Mead, Potters Bar, Hertsmere, Hertfordshire, EN6 3HY |  | Sharan | Completed | Medium |  |  | 2024-11-05 | 2024-11-05 | 2024-11-08 |  |  | No527_report_duplicate_property_images_Sharan_N_P_05_11_2024
528 | 2024-10-25 | Issue | Live | Property Report | change the page title to On Market Sale Comparable |  | Sharan | Completed | Medium
529 | 2024-10-25 | Suggestion | Live |  | move Census 2021 above Settings |  | Sharan | Completed | Low |  |  | 2024-11-05 | 2024-11-05 | 2024-11-06 |  |  | No529_Navigations_order_change_Sharan_N_P_05_11_2024
530 | 2024-10-29 | Issue | Live | Property Report | the title number shown in the report is not correct 1, MOULTON RISE, LUTON, LU2 0AF 5, MOULTON RISE, LUTON, LU2 0AF title number missing in the report 116a, St. Marks Road, Enfield, Greater London, EN1 1BB 116 EN1 1BB |  | Sharan | Completed | High |  |  | 2024-11-05 | 2024-11-05 | 2024-11-08 |  |  | No530_report_title_number_missing_Sharan_N_P_05_11_2024
531 | 2024-10-29 | Issue | Live | Title Plan/Register | property has title plan but when we search, it shows No title plan available 116a, St. Marks Road, Enfield, Greater London, EN1 1BB 116 EN1 1BB |  | Sharan | Completed | High |  |  | 2024-11-07 | 2024-11-07
532 | 2024-10-29 | Issue | Live | Let Agreed | let agreed not updating for zoopla properties |  |  | Completed | High
533 | 2024-10-29 | Issue | Live | Property Listing | company details are shown in the listing but when we go into the detail page it shows Company Details not found Flat 5, 57, Finchley Lane, London, Barnet, NW4 1BY 73 Kenwyn Drive, London, NW2 7NX |  | Sharan | Completed |  |  |  | 2024-11-06 | 2024-11-07 | 2024-11-13 |  | Company Owned issue https://demolettings.devidiamober.com/properties/p-188436 | No533_listings_company_owned_Sharan_N_P_06_11_2024
534 | 2024-10-31 | Issue | Live | Wallet | wallet details not loading |  | Rijo | Completed | High |  |  | 2024-10-31 | 2024-10-31 | 2024-10-31
535 | 2024-10-31 | Issue | Live | Targeted Campaign | bulk mail - after sending bulk mail, the address is removed from the list only after we refresh the page |  | Sharan | Duplicate Task
536 | 2024-10-31 | Issue | Live | QR | qr form - the texts are not visible against the background |  | Sharan | Completed | Medium |  |  | 2024-11-11 | 2024-11-11 | 2024-11-13 |  |  | No536_qr_form_text_not_visible_Sharan_N_P_11_11_2024
537 | 2024-11-04 | Issue | Live | Property Report | the status is not correct 48 Clark Street, London, E1 2HD |  | Sharan | Completed | Medium |  |  | 2024-11-07 | 2024-11-07
538 | 2024-11-04 | Issue | Live | Targeted Campaign | when letters are being sent to multiple addresses, the addresses are not greyed out like the rest when processing |  | Sandeep | Not Started | Medium
539 | 2024-11-04 | Issue | Live | Targeted Campaign | when sending 50+ letters, it takes more than 1 min for the Edit Address section to load |  | Rijo | Not Started | Medium
540 | 2024-11-04 | Issue | Live | Campaign History | targeted - the campaign name and other details are not visible https://tinyurl.com/22xngg8b |  | Sharan | Completed | Medium |  |  | 2024-11-05 | 2024-11-05 | 2024-11-06 |  |  | No540_targeted_campaign_history_heading_not_visible_Sharan_N_P_05_11_2024
541 | 2024-11-05 | Issue | Live | Filter By 0-7 Days | let agreed property is listed under 0-7 days Apartment 309, Amazon Lofts, Tenby Street, Birmingham, West Midlands, B1 3AJ |  | Sharan | Completed | High |  |  | 2024-11-08 | 2024-11-08
542 | 2024-11-05 | Issue | Live | Property Report | Redesign Property Images page in report |  | Sharan | Completed | Medium |  |  | 2024-11-05 | 2024-11-05 | 2024-11-06 |  |  | No542_report_proerty_images_page_Sharan_N_P_05_11_2024
543 | 2024-11-05 | Issue | Live | Property Report | When we enlarge the floor plan in report generating page, the close button is not visible |  | Sharan | Completed | Medium |  |  | 2024-11-05 | 2024-11-05 | 2024-11-06 |  |  | No543_report_floorplan_carousel_Sharan_N_P_05_11_2024
544 | 2024-11-05 | Issue | Live | All Properties | When the property type "Studio" is selected, the bed count for some addresses is missing. |  | Sharan | Completed | High |  |  | 2024-11-06 | 2024-11-06 | 2024-11-13 |  | Updated Nov 5: not updated in Let agreed Updated Nov 6: updated in Let agreed & Rental reduced | No544_properties_bed_count_null_Sharan_N_P_05_11_2024
545 | 2024-11-06 | Issue | Live | Targeted Campaign | addresses are duplicating in stannp |  | Sandeep | Not Started | High
546 | 2024-11-06 | Issue | Live | Direct Mail Anywhere | when we search some postcode it shows invalid postcode M5 2XH Handle the error |  | Sharan | Completed | Medium |  |  | 2024-11-08 | 2024-11-08 |  |  | Updated No 8 : Sharan N P Postcode not valid
547 | 2024-11-06 | Issue | Live | Property Detail Page | Some property images are enlarged, https://www.awesomescreenshot.com/image/51413365?key=d0c4cb8be09beec82c843ef8146166871 9, Torrington Drive, Potters Bar, Hertsmere, Hertfordshire, EN6 5HS https://demolettings.devidiamober.com/properties/p-319034 |  | Sharan | Testing | Medium |  |  | 2024-11-07 | 2024-11-13 | 2024-12-17 |  | 07/11/2024 : Assign to Satheesh Need confirmation | No547_detail_page_property_image_enlarge_error_Sharan_N_P_07_11_2024
548 | 2024-11-06 | Issue | Live | DMA Campaign | addresses are duplicating in stannp |  | Sharan | Completed | High |  |  | 2024-11-08 | 2024-11-08 | 2024-11-13 |  | Will test in live - 12th Nov | No545_targeted_campaign_addresses_duplicating_stannp_Sharan_N_P_08_11_2024
549 | 2024-11-06 | Issue | Live | Property Report | in the sub titles of a page make sure the selected color is the same as the color chosen by the agent |  | Sharan | Closed | Medium
550 | 2024-11-06 | Issue | Live | Property Detail Page | Property image error in detail page https://demolettings.devidiamober.com/properties/p-281453 43, Lambs Close, Cuffley, Potters Bar, Welwyn Hatfield, Hertfordshire, EN6 4HD Flat 12, Christopher Court, 90 Great North Way, London, NW4 1HE |  | Sharan | Completed | High |  |  | 2024-11-06 | 2024-11-06 | 2024-11-13 |  |  | No550_details_images_error_Sharan_N_P_06_11_2024
551 | 2024-11-07 | Issue | Live |  | In lettings todays date shown as 0 days https://drive.google.com/file/d/1ygpxTs1qefvrLD6Uhb7v3mX6hoJQUWkY/view?usp=drive_link |  | Sharan | Completed | Medium |  |  | 2024-11-11 | 2024-11-11 | 2024-11-13 |  |  | No551_properties_todays_date_Sharan_N_P_11_11_2024
552 | 2024-11-08 | Issue | Live | Targeted | Property type different in rightmove, 159, Crawford Road, Hatfield, Welwyn Hatfield, Hertfordshire, AL10 0PB |  | Sharan | Completed | Low |  |  | 2024-11-18 | 2024-11-18 |  |  | 18/11/2024 Sharan N P Check with sold history and the type is Semi-detached
554 | 2024-11-11 | Issue | Live | Title Plan/Register | Page is not responding while searching a property , it shows loading 47 Tudor Close, Hatfield, AL10 9EJ 36 Lakeside Place, London Colney, St. Albans, AL2 1PZ 29, Thamesdale, London Colney, St Albans, Hertfordshire, AL2 1TA 21, Broadlake Close, London Colney, St Albans, Hertfordshire, AL2 1NS |  | Sharan | Completed | Medium | Linta |  | 2024-11-12 | 2024-11-12 | 2024-11-13 |  | Test these pages too Comparable Report Detail page Developer testing completed | No554_report_clean_image_fn_error_Sharan_N_P_12_11_2024
555 | 2024-11-11 | Issue | Live | Property Report | The property area is available on the EPC, but it is showing as "not available" in the report. |  | Sharan | Testing | Low | Aayisha | [5 empty] | 04/12/2024 Mention the reprot address
556 | 2024-11-11 | Issue | Live | Property Report | The property address format is incorrect when the address is confirmed. Address before confirmation : 134 Wordsworth Court, Middlefield, Hatfield, AL10 0EQ Address after confirmation : Flat Flat, Wordsworth Court, Hatfield, Hertfordshire, AL10 0EQ |  | Sharan | Completed | Low | Aayisha |  | 2024-11-18 | 2024-11-18 | 2024-11-21 |  | Getaddress returns the address as "Flat", "Wordsworth Court", "Middlefield", "Hatfield", "Hertfordshire" | No556_Report_flat_duplicate_Sharan_N_P_18_11_2024
557 | 2024-11-11 | Issue | Live | Property Report | Incorrect address Format: 30, ENDYMION ROAD, HATFIELD, HERTFORDSHIRE, AL10 8AR Address in epc site : 30 Malting Mead Endymion Road HATFIELD AL10 8AR |  | Sharan | Not Started | Low | Aayisha
558 | 2024-11-11 | Issue | Live | HMO Register | Postcode is missing in listing page but it is displayed in detail page (Amber Valley,Dover) | Data | Vishnu | Not Started | Low | Linta | [5 empty] | 12/11/2024 Informed to Vishnu
559 | 2024-11-11 | Issue | Live | HMO Register | Address are repeating under Worcester,Nottingham and postcode is missing in listing page Address are repeating under Breckland |  | Sharan | Completed | Medium | Linta |  | 2024-11-12 | 2024-11-12 | 2024-11-13 |  | 12/11/2024 Address are duplicate but reference nuumber are different Need confirmation | No560_HMO_empty_listing_Sharan_N_P_12_11_2024
560 | 2024-11-11 | Issue | Live | HMO Register | Blank listing is shown for Wokingham,Westminister https://drive.google.com/file/d/1T46kBBuTLbTeaKmQj5H-iVaRfTDHQcF0/view?usp=drive_link |  | Sharan | Completed | Medium | Linta |  | 2024-11-12 | 2024-11-12 | 2024-11-13 |  | 12/11/2024 Blank Listings Removed Expiry Null to Not Available License NUmber Displayed | No560_HMO_empty_listing_Sharan_N_P_12_11_2024
561 | 2024-11-11 | Issue | Live | HMO Register | some addresses are shown as Not available or Address in the listing under Hammersmith and fulham,Dover(last page) https://drive.google.com/file/d/1xNY1WL_Xm5k3pNvXi9_iahFcNgRAbAYq/view?usp=drive_link |  | Sharan | Completed | Medium | Linta |  | 2024-11-13 | 2024-11-13 |  |  | 12/11/2024 Informed to Vishnu
562 | 2024-11-11 | Issue | Live | HMO Register | Address are displayed as null for hertfordshire, blank listing for Rother(last page) https://drive.google.com/file/d/10Lhgkyqda2G_4-3D9_h2jo0VbRZSR5R9/view?usp=drive_link |  | Sharan | Completed | Medium | Linta |  | 2024-11-12 | 2024-11-12 | 2024-11-13 |  |  | No560_HMO_empty_listing_Sharan_N_P_12_11_2024
563 | 2024-11-11 | Issue | Live | HMO Register | Address are not spaced out properly in listing page for Basingstoke and deane | Data | Vishnu | Not Started | Medium | Linta | [5 empty] | 12/11/2024 Informed to Vishnu
564 | 2024-11-11 | Issue | Live | HMO Register | Address mentioned as temporary Exemption in listing and in detail page the address is different https://drive.google.com/file/d/16XyRcfd_t_N5cuxZKBq9GiNN0HfBsirc/view?usp=drive_link Under Kensington and chelsea | Data | Vishnu | Not Started | Medium | Linta | [5 empty] | 12/11/2024 Informed to Vishnu
563 | 2024-11-11 | Issue | Live | Title Plan/Register | When searching for a property without a title number, a message appears indicating that the title number is not available. However, this message still remains on the screen even after selecting a property that have a title number. https://drive.google.com/file/d/1HvRRGw_5d8rPPft_phP8bhJvyW1X3Fmi/view?usp=drive_link |  | Sharan | Completed | Medium | Linta |  | 2024-11-12 | 2024-11-12 | 2024-11-13 |  | Testing cannot be done in the demo environment. Will test the issue in live session.(developer testing completed) | No565_title_number_remove_error_msg_Sharan_N_P_12_11_2024
564 | 2024-11-12 | Issue | Live | Dashboard | Outcode is repeated 'YO32' https://www.awesomescreenshot.com/image/51546797?key=acac8c9a0e68ca7e185c2471a2feb7f3 https://www.awesomescreenshot.com/image/51546853?key=bbe378fa2592d3e5bd54b4b9874e404d https://drive.google.com/file/d/19nwrCDSbht4OfN_4r3Pfc5iyV-7MlcyF/view?usp=drive_link |  | Sharan | In Progress | Low | Linta |  | 2025-01-03 | 2025-01-03 |  |  | 03/01/2025 Sharan Once you click on the submit button the button must be disabled ---------------------------- UPDATED Jan 7: - on double clicking on the submit button, the outcode gets added twice
565 | 2024-11-13 | Issue | Live | Title Plan/Register | Disable search bar in non working hours |  | Sharan | Completed | Medium |  |  | 2024-11-12 | 2024-11-12 | 2024-11-21 |  |  | No565_title_number_remove_error_msg_Sharan_N_P_12_11_2024
567 | 2024-11-13 | Issue | Live | Property Report | In the "custom values" , the square feet field is currently accepting alphabets and special characters. It should only accept numerical input. |  | Sharan | Completed | Low | Aayisha |  | 2024-11-15 | 2024-11-15 | 2024-11-21 |  |  | No567_Report_custom_values_sqft_Sharan_N_P_15_11_2024
568 | 2024-11-15 | Issue | Live | Property Detail Page | Blank coloumn in Company details https://www.awesomescreenshot.com/image/51580047?key=aee3e70b0bdfae42902b4b9f165b4602 https://lettings.letsbidproperty.co.uk/properties/p-446017 |  | Sharan | Completed | Medium | Aayisha |  | 2024-11-15 | 2024-11-15 | 2024-11-21 |  |  | No568_details_company_owned_empty_Sharan_N_P_15_11_2024
569 | 2024-11-15 | Issue | Live | HMO Register | Data table warning in council Hammersmith and Fulham when all entries are selected |  | Sharan | Completed | Medium | Aayisha |  | 2024-11-15 | 2024-11-15 | 2024-11-21 |  |  | No569_hmo_register_all_error_Sharan_N_P_15_11_2024
570 | 15 Nov 0224 | Issue | Live | HMO Register | The address is present on the detail page but is displaying as "Not Available" in the listing. Property Council : Rother |  | Sharan | Completed | Low | Aayisha |  | 2024-11-18 | 2024-11-18 | 2024-11-21 |  |  | No560_HMO_empty_listing_Sharan_N_P_12_11_2024
571 | 2024-11-18 | UK Team | Live | Property Report | Delete the property Image without seclect a thumbnail |  | Sharan | Completed | Medium |  |  | 2024-11-18 | 2024-11-18 | 2024-11-21 |  |  | No571_report_delete_property_image_Sharan_N_P_18_11_2024
572 | 2024-11-20 | Task |  | Property Detail Page | grey out listing activity in detail page |  | Sandeep | Not Started | Medium
573 | 2024-11-20 | Task |  |  | New listing date logic |  | Sandeep | Not Started | Medium
574 | 2024-11-20 | Task | Live | Property Report | Implement the design changes made in sales report |  | Rijo | Not Started | High
575 | 2024-11-20 | Task | Live | Letter Management | When side panel is enabled when editing letter the page refreshes, content changes |  | Sharan | Test Demo | Medium | Aayisha |  | 2024-12-04 | 2024-12-04 |  |  | updated Jan 7: - when we enable/disable the Side Panel from the letter management listing, the content gets cleared | No575_Letter_management_side_panel_trigger_Sharan_N_P_04_12_2024
576 | 2024-11-21 | Issue | Live | Property Report | In the "custom values" , the square feet field is currently accepting "-" All price fields comparable price filter estimation price |  | Sharan | Completed | Low | Aayisha |  | 2024-12-04 | 2024-12-04 | 2024-12-10 |  |  | No576_Report_custom_values_field_Sharan_N_P_04_12_2024
577 | 2024-11-21 | Issue | Live | Property Detail Page | the count shown for RM and Z icons are not aligned properly https://lettings.letsbidproperty.co.uk/properties/p-19502 |  | Sharan | Approval | Low |  |  | 2025-01-03 | 2025-01-03
578 | 2024-11-22 | Task | Live | Dashboard | dashboard optimisation |  | Sandeep | Not Started | Medium
579 | 2024-11-25 | Suggestion | Live | Property Report | Key details - for planning application, if no application is available instead of Nil show Not Available |  | Sharan | Testing | Medium |  |  | 2025-01-03 | 2025-01-03 | 2025-01-07 |  |  | No579_Report_planning_key_nil_Sharan_N_P_03_01_2025
580 | 2024-11-25 | UK Team | Live | Targeted | Targeted lettings – Option to filter companies that have multiple properties any company that owns multiple properties, we need an option to filter the listing - 2+ properties |  | Rijo | Not Started | Medium
581 | 2024-11-25 | UK Team | Live | Targeted | Targeted on lettings – cant see what letters have been sent? letter sent status in the listing like the rest of the pages |  | Sharan | Not Started | High
582 | 2024-11-25 | UK Team | Live | HMO Register | HMO’s – License holders address – cant add this into the campaign? Need reference to come up like Probate Add to campaign button in the detail page for property address and license holder address The property address should be shown as the Reference when sending letter to the license holder address |  | Rijo | Not Started | High
583 | 2024-11-26 | Issue | Live | Property Report | The labels should be "Price From" and "Price To," but currently, both are incorrectly displayed as "Price From." https://www.awesomescreenshot.com/image/51760416?key=10c6f29ac7344e8388ff79879e17e5f3 | UI | Sharan | Completed | Low | Aayisha |  | 2024-12-04 | 2024-12-04 | 2024-12-10
584 | 2024-12-03 | Issue | Live | Selective Licensing | Server error Croydon - Council Name https://www.awesomescreenshot.com/image/51856164?key=cd793567c5dc7ce7ed20df7675da35f6 |  | Sharan | Completed | High | Aayisha |  | 2024-12-04 | 2024-12-04 | 2024-12-10 |  |  | No584_Selective_register_server_error_Sharan_N_P_04_12_2024
585 | 2024-12-03 | Issue | Live | Settings | Need to remove dot and space for the message 'profile updated successfully' https://drive.google.com/file/d/1t2Q3Rkt0_-1edezRYc0xDgSPQBuzt2hk/view?usp=drive_link |  | Sharan | Completed | Low | Linta |  | 2024-12-04 | 2024-12-04 | 2024-12-10 |  |  | No585_msg_correction_Sharan_N_P_04_12_2024
586 | 2024-12-03 | Issue | Live | HMO Register | License issue and expiry dates are not correct under Dudley | Data | Vishnu | Testing | Medium | Linta |  | 2024-12-06 | 2024-12-06 |  |  | 04/12/2024 : Informed to data team by mail
587 | 2024-12-03 | Issue | Live | HMO Register | Postcode is repeating for some address for Hammersmith & fulham https://drive.google.com/file/d/1wgwQfJLFKSaKRyLzuLObDCwV4VoFO7m6/view?usp=drive_link | Data | Vishnu | Not Started | Low | Linta | [5 empty] | 04/12/2024 : Informed to data team by mail
588 | 2024-12-03 | Issue | Live | Selective Licensing | \n' is displayed in listing page,detail page under croydon https://drive.google.com/file/d/1q74dKX-9WUP2WUqv667FH3hemCmN6CSz/view?usp=drive_link |  | Sharan | Testing | Low | Linta |  | 2024-12-04 | 2024-12-04 | 2024-12-17 |  |  | No588_Selective_licensing_croydon_text_cleaning_Sharan_N_P_04_12_2024
589 | 2024-12-04 | Issue | Live | Property Report | The Population section on the Report page is currently not displaying any content. https://lettings.letsbidproperty.co.uk/view-report/report_540_041220240407903764.pdf https://lettings.letsbidproperty.co.uk/properties/p-464399 | web | Sharan | Testing | Low | Aayisha |  | 2024-12-04 | 2024-12-04 | 2024-12-17 |  |  | No589_Report_empty_planning-section_corrected_Sharan_N_P_04_12_2024
590 | 2024-12-04 | Issue | Live | Rental Reduced | Server error https://lettings.letsbidproperty.co.uk/properties/p-437542 https://lettings.letsbidproperty.co.uk/properties/d-477392 | web | Sharan | Testing | Medium | Aayisha | [5 empty] | 04/12/2024 Portal json data related issue
591 | 2024-12-04 | Issue | Live | Targeted | while going back from detail page the selected postcodes are not displayed in listing https://drive.google.com/file/d/1fr-5uFo4NhsHdKIVc4ipYZPkqkixK12m/view?usp=drive_link |  | Sharan | In Progress | Medium | Linta |  | 2025-01-07
592 | 2024-12-04 | Issue | Live | Rental Reduced | -Listed date displayed in listing page and detail page is different -Date displayed in the detail page is displayed under campaign 69, Whitehall Road, Aberdeen, Aberdeenshire AB25 2PQ https://lettings.letsbidproperty.co.uk/properties/d-183968 https://lettings.letsbidproperty.co.uk/properties/d-457079- | web | Sandeep | Not Started | High | Linta
593 | 2024-12-04 | Task | Live | Title Plan/Register | When ordering title plans on Lets bid or propmaker the charge is currently £3 for each document please increase this cost to £7.5 for each document |  | Rijo | Testing | High |  |  | 2024-12-04 | 2024-12-04 |  |  | updated Dec 4: should be £7 for each
594 | 2024-12-05 | Issue | Live | Live Campaign | Replace the option 'print' with 'open PDF' in local print https://www.awesomescreenshot.com/image/51910348?key=1fae83b43cca8885a35d838ff934ca7b | UI | Sharan | Test Demo | Low | Aayisha |  | 2025-01-03 | 2025-01-03 |  |  |  | No594_Live_campaign_change_text_Sharan_N_P_03_01_2025
595 | 2024-12-09 | Issue | Live | Selective Licensing | Server error Council Name: North Yorkshire Scarborough North Yorkshire YO11 2RP | web | Sharan | Testing | Low | Aayisha |  | 2025-01-03 | 2025-01-03
596 | 2024-12-09 | Task | Live | Live Campaign | Negative balance checking make sure the agents are not able to send letters if they don't have enough balance | web | Rijo | Test Demo | High | [7 empty] | no596_negative_balance_02Jan2025
597 | 2024-12-09 | Enhancement |  | Summary | Summary page enhancement |  | Sandeep | Not Started | Medium
598 | 2024-12-09 | Issue | Live | Targeted | Need to change the text 'Group' to 'range' https://drive.google.com/file/d/1d_kz8Jked89IMYcLlcdUA1cUYYDtPxBA/view?usp=drive_link | UI | Sharan | Test Demo | Low | Linta |  | 2025-01-03 | 2025-01-03 |  |  | updated Jan 7: - when we click on clear filter the text changes to Year Group - remove - in between | No598_Targeted_year_range_filter_Sharan_N_P_03_01_2025
599 | 2024-12-10 | Issue | Live | Outcodes | Need to remove few suggestions under dropdown Gre Zimba JMBT Argent DH22 O CO NOR SP cyp sk gre x2 https://drive.google.com/file/d/1fU_1GSf05-L6D809NfzbxWoYhY4Xkqmw/view?usp=sharing |  | Sharan | Completed | Medium | Linta |  | 2025-01-02 | 2025-01-02 | 2025-12-07 |  |  | No599_Outcodes_select_valid_outcodes_Sharan_N_P_02_01_2025
600 | 2024-12-10 | Issue | Live | Property Report | Under comparables While filtering using 'price from' and 'price to,' the values are not coming out correctly (the filter is not being applied). | web | Sharan | Test Demo | Medium | Linta |  | 2025-01-03 | 2025-01-03 |  |  |  | No600_Report_comparable_price_filter_Sharan_N_P_03_01_2025
601 | 2024-12-10 | Issue | Live | Targeted | addresses are repeating in the listing | web | Sharan | Completed | High
602 | 2024-12-11 | Issue | Live | Live Campaign | An error message is displayed when more than 90 addresses are selected in the Targeted Campaign. SQLSTATE: Integrity constraint violation: 1452 Cannot add or update a child row: a foreign key constraint fails (`lettings_live`.`targeted_campaign_collections`, CONSTRAINT `targeted_campaign_collections_user_id` FOREIGN KEY (`campaign_id`) REFERENCES `campaigns` (`id`)) |  | Sandeep | Not Started | Medium | Aayisha
603 | 2024-12-11 | Issue | Live | Targeted Campaign | Not able to send bulk mail or local print in targeted campaign it's showing an error message after clicking on confirm and send |  | Sharan | Completed | High
604 | 2024-12-12 | Issue | Live | HMO Register | The address shown on the listing page differs from the address displayed on the detail page. Council - Canterbury | web | Sharan | Test Demo | Medium | Aayisha |  | 2025-01-06 | 2025-01-06 |  |  |  | No604_HMO_Register_address_issue_Sharan_N_P_06_01_2025
605 | 2024-12-12 | Issue | Live |  | menu - when the user is in outcode page and then click on Properties, the highlights overlap | UI | Sharan | Testing | Medium |  |  | 2025-01-05 | 2025-01-05 | 2025-01-07 |  |  | No605_Sidebar_overlap_issue_Sharan_N_P_05_01_2025
606 | 2024-12-13 | Discuss | Live | DMA Campaign | Address repeating in postcode : E1 3JH https://www.awesomescreenshot.com/image/52036556?key=7a41e61bb99341c4b3b5a1e6dd8d58f4 | web | Sharan | Testing | Medium | Aayisha |  | 2025-01-03 | 2025-01-03 |  |  |  | No606_DMA_address_duplicating_Sharan_N_P_03_01_2025
607 | 2024-12-16 | Issue | Live | Letter Management | Cant submit the message in contact 1.type subject then message it wont work 2.type message then subject it works | web | Sharan | Completed | Low | Linta |  | 2025-01-02 | 2025-01-02 |  |  | Linta Dominic please let me know the issues 607, 610 are still exist
608 | 2024-12-16 | Suggestion | Live | Rental Reduced | Property type is shown as blank in listing and detail page https://lettings.letsbidproperty.co.uk/properties/d-408434 3 Denny Abbey Cottages, Ely Road, Waterbeach, Cambridge, CB25 9PQ | web | Sharan | Testing | Low | Linta |  | 2025-01-06 | 2025-01-06 | 2025-01-07 |  | 06/01/2025 Sharan Instead of empty added Not Available | No608_Rental_reduced_Property_type_Sharan_N_P_06_01_2025
609 | 2024-12-16 | Issue | Live | Targeted | Text is overlapping https://drive.google.com/file/d/1VDXId1_cB2zzY4HI20sTApzupuRyIB1Q/view?usp=drive_link | UI | Sharan | Completed | Low | Linta |  | 2025-01-02 | 2025-01-02 | 2025-12-07 |  |  | No609_Targeted_text_overlapping_Sharan_N_P_02_01_2025
610 | 2024-12-16 | Task | Live | Live Campaign | Clicking on 'Preview' displays both the bulk mail preview and the bulk mail confirmation page https://drive.google.com/file/d/1zeHWi2kr8crPihUlcOuiHO0DXrVd83Kk/view?usp=drive_link |  | Sharan | Completed | Low | Linta |  | 2025-01-02 | 2025-01-02 |  |  | Linta Dominic please let me know the issues 607, 610 are still exist
611 | 2024-12-18 | Issue | Live | Let Agreed | If we filter the listing by Semi-Detached,end terrace type, addresses that have the type Semi Detached,end-terrace (without -) are excluded (copy same concept in sales) |  | Sandeep | Not Started | Medium | Linta
612 | 2024-12-18 | Issue | Live | 2nd Instruction Campaign | when sending letters to lots of addresses, please show loaders - after clicking on bulk mail or local print button it takes some time to show the edit box - there is a delay in showing the Bulk Mail Confirmation pop up after clicking on Confirm and send bulk mail button" |  | Sandeep | Not Started | Medium
613 | 2024-12-18 | Issue | Live | 2nd Instruction Campaign | when sending letters to many addresses, the preview takes time to load |  | Sandeep | Not Started | Medium
614 | 2024-12-18 | Issue | Live | Targeted Campaign | when sending letters to many addresses, the edit address takes time to load | web | Sandeep | Not Started | Medium
615 | 2024-12-18 | Issue | Live | Property Report | not able to generate report for this address 22 Muswell Hill, London, N10 3TA | web | Sharan | Testing | Medium |  |  | 2025-01-02 | 2025-01-02 | 2025-01-07 |  |  | No615_Report_check_address_error_Sharan_N_P_02_01_2025
616 | 2024-12-18 | Issue | Live | Property Report | the epc certificate number in the report and epc page is different -------------------- we are showing the lm key now, instead of that can we move the valid until date to the next line so the design looks aligned | web | Sharan | Testing | Medium |  |  | 2025-01-02 | 2025-01-02 | 2025-01-07 |  |  | No616_Report_epc_page_key_Sharan_N_P_02_01_20
617 | 2024-12-18 | Issue | Live | Targeted | comparables section in the detail page - on clicking anywhere near the title should open the accordion - or place the arrows near the title like Other properties owned https://tinyurl.com/25do8pr6 | UI | Sharan | Testing | Medium |  |  | 2024-12-31 | 2025-01-02 | 2025-01-07 |  |  | No617_Targeted_comparable-click_Sharan_N_P_31_12_2024
618 | 2024-12-18 | Issue | Live | Property Report | if property type is not selected, it shows blank in additional comparable pop up 235, Longford Road, Coventry, West Midlands, CV6 6BG https://tinyurl.com/2ddl9g6u | web | Sharan | Testing | Medium |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No618_Report_additional_comps_property_type_Sharan_N_P_31_12_2024
619 | 2024-12-18 | Suggestion | Live | Property Listing | do we need to show the address in a box when we hover over it? | UI | Sharan | Testing | Medium |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No619_Properties_listing_hover_Sharan_N_P_31_12_2024
620 | 2024-12-18 | Suggestion | Live | Property Report | population - if the graph is not available, please move the table to the center or to the left https://tinyurl.com/223b92bu 25, HENRIETTA STREET, COVENTRY, WEST MIDLANDS, CV6 5EF | UI | Sharan | Testing | Medium |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No624_Report_population_page_align_Sharan_N_P_31_12_2024
621 | 2024-12-18 | Suggestion | Live | Property Report | after selecting an address and clicking on Confirm, make sure it scrolls to the report customisation section | web | Sharan | Testing | Low |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No621_Report_Address_confirm_click_scroll_up_Sharan_N_P_31_12_2024
622 | 2024-12-18 | Issue | Live | Property Report | when generating a report, the info text gets cropped when the user scrolls https://tinyurl.com/25mena4u | UI | Sharan | Testing | Low |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No622_Report_info_content_hidden_Sharan_N_P_31_12_2024
623 | 2024-12-18 | Issue | Live | Property Report | Clicking anywhere on the map page triggers the image upload box for the primary image. | web | Sharan | Testing | Medium |  |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No623_Report_map_click_disabled_Sharan_N_P_31_12_2024
624 | 2024-12-18 | Issue | Live | Property Report | Alignment issue in the population page https://lettings.letsbidproperty.co.uk/view-report/report_564_181220240841919657.pdf | UI | Sharan | Testing | Low | Aayisha |  | 2024-12-31 | 2024-12-31 | 2025-01-07 |  |  | No624_Report_population_page_align_Sharan_N_P_31_12_2024
625 | 2024-12-23 | Issue | Live | Targeted | Company address in listing and detail page is different 32, Ness Road, Burwell, Cambridge, East Cambridgeshire, Cambridgeshire, CB25 0AA 32, Fox Lane, London, Enfield, N13 4AH | web | Sharan | In Progress | Medium | Linta |  | 2025-01-06 | 2025-01-06 |  |  | updated Jan 7: - the company address in the detail page is the same as the registration page, the address in the listing page is not correct | No625_Targeted_company_address_correction_Sharan_N_P_06_01_2025
626 | 2024-12-23 | Issue | Live | Outcodes | When adding an outcode, the summary shows '7-15 days' twice https://drive.google.com/file/d/147OQ9Pui0glOQ8jhTCzhJUvk19jf7HyD/view?usp=drive_link | Web | Sharan | Completed | Medium | Linta |  | 2024-12-31 | 2024-12-31 | 2025-12-07 |  |  | No626_Outcode_7_15_days_twice_Sharan_N_P_31_12_2024
627 | 2024-12-30 | Issue | Live | Property Listing | getting server error page for some addresses Apartment 1704, 1 Boxwood Gardens, London, E1W 2DX - https://lettings.letsbidproperty.co.uk/properties/p-502083 Apartment 1703, 1 Boxwood Gardens, London, E1W 2DX - https://lettings.letsbidproperty.co.uk/properties/p-502084 |  | Sharan | Testing | High |  |  | 2025-01-06 | 2025-01-06 | 2025-01-07 |  |  | No627_Properties_postcode_error_Sharan_N_P_06_01_2025
628 | 2024-12-30 | Issue | Live | Quick Send | Error message is shown https://drive.google.com/file/d/1NGZ3LSi70bkHeSAVPQ5W177-lV3pHIU2/view?usp=drive_link | Web | Rijo | Not Started | Medium | Linta
629 | 2024-12-30 | Issue | Live | Settings | Change password option is not working as expected | Web | Sharan | Test Demo | Low | Aayisha |  | 2025-01-03 | 2025-01-03 |  |  |  | No629_Setting_change_password_disabled_Sharan_N_P_03_01_2025
630 | 2025-01-02 | Issue | Live | Selective Licensing | The council name "Harrow" is repeated in the address on the listing page, but it does not appear on the detail page. |  | Sharan | Testing | Low | Aayisha |  | 2025-01-03 | 2025-01-03 | 2025-01-07 |  |  | No630_Selective_license_tounty_duplicate_Sharan_N_P_03_01_2025
631 | 2025-01-02 | Issue | Live | Dashboard | Incorrect data in Campaign - Activity Summary graph https://www.awesomescreenshot.com/image/52280052?key=6bb30823e26c7acf198e03eec7b78093 | Web | Sharan | Not Started | Low | Aayisha
632 | 2025-01-02 | Issue | Live | Property Report | boundary editor - close editor move it to the right box |  | Sharan | Testing | Medium |  |  | 2025-01-03 | 2025-01-03 | 2025-01-07 |  |  | No632_Report_os_map_editor_Sharan_N_P_03_01_2025
633 | 2025-01-03 | Issue | Live | HMO Register | Address repeating in Council Derbyshire Dales https://www.awesomescreenshot.com/image/52292428?key=69fd4818354a88bb2d8090ac3963b246 | Data | Vishnu | Not Started | Low | Aayisha
634 | 2025-01-06 | Issue | Live | Property Report | Belfry Lodge, 8 Thorpe Park Lodges, Middle Lane, Thorpe On The Hill, Lincoln, LN6 9AJ https://lettings.letsbidproperty.co.uk/properties/p-506530 The property type for the above address is displayed as "Chalet" on the detail page, but it appears as "Detached" when editing the report. |  | Sharan | Not Started | Low | Aayisha
635 | 2025-01-06 | Issue |  | Property Report | "epc - no data is shown for the Secondary Heating Efficiency and Floors if no data is available show - instead of leaving it blank" |  | Sharan | Not Started
636 | 2025-01-07 | Issue |  | HMO Register | Incorrect council names are shown in the dropdown |  | Data Team | Not Started | High
637 | 2025-01-07 | Issue | Live | Property Listing | in E1, we are showing properties in E1W |  | Sharan | Not Started | High
638 | 2025-01-07 | Issue | Live | Property Report | property is on market but when generating report it shows off market 294 Terry Road, Coventry, CV3 1NJ - https://lettings.letsbidproperty.co.uk/properties/p-504425

## Report Issues (hidden)
Page | Issue | Assigned To | Status | Priority | Start Date | End Date | Comments
about us | report description - even if the paragraphs are in a new line, in the report it is shown as a single paragraph |  | Complete | High
market analysis page | the avg area price/sqft is not correct |  | Complete | High
| property type is available in the detail page, but when generating the report it's given as Not Available 35, Hall Lane, London, NW4 4TJ | Rijo | In Progress | High |  |  | not cleared
market analysis | even if we select only one sold comparable, Avg area price/sqft is shown in the market analysis page | Rijo | In Progress | High | 2024-08-01
| sold history issue 21, Orchard Square, Broxbourne, Hertfordshire, EN10 6JA 4, 7 Glebe Road, Harrogate, North Yorkshire, HG2 0LZ (never been sold for 379k where's the info coming from) | Sharan | In Demo | High | 2024-08-01
| Sold prices on street - none of them are on the street? They should only be properties sold on the street the report has been generated for | Sharan | Testing | High | 2024-08-01
market analysis page | avg sold price is shown as 0 in market analysis page if avg sold price is not available are we showing it as 0? 140, New Barn Street, London, E13 8JW | Rijo | Complete | High | 2024-08-01 | 2024-08-01
| when the marker for map is enabled, show the marker on the map in the report generation page itself | Sharan | Not Started | Medium
| sometimes when we generate the report, only the first page and last page is shown once the report is generated |  | Testing | High
avg price changes in the area | the price overlaps with the legend above the graph https://tinyurl.com/2amx2dc9 | Rijo | Complete | Medium
epc | the certificate number goes outside the box 19, Myln Meadow, Ingatestone, Essex, CM4 9NE https://tinyurl.com/2a3btub6 | Rijo | Not Started | Medium
| Property Address should be in bold and the property type/bedrooms underneath. Basically the opposite format to what you have got at the minute: | Sharan | Complete | Medium
| Buyers/ Seller's description needs to change to 'About us' so agents know its the page 2 about us section | Sharan | Complete | Medium
| Market analysis - remove outcode because its showing the whole council, not just HG2. Either have the council or just the postcode as it does not read properly at all | Sharan | Complete | Medium
| Primary / Secondary schools - easier to read on old report so need to add lines to make it clearer | Satheesh | Complete | Medium
| Carbon footprint and broadband mobile speed need to be separated. Agents don't like including carbon footprint so can it be a seperate box selection to tick on report customisation section so it appears on separate pages | Sharan | Complete | Medium
property analysis & highlights | remove gross yield, net yield, ROI, difference | Rijo | Complete
property analysis & highlights | property price is always £250,000 | Rijo | Complete
property analysis & highlights | average sold and rent is given in % and is always the same | Rijo | Complete
property analysis & highlights | price reduced section is shown in the report, even if the price has not been reduced for the property | Rijo | Complete
epc page | please show the inspection date in uk format dd-mm-yyyy | Rijo | Complete
market analysis | please remove { after time period | Rijo | Complete
market analysis | please make sure the texts are of the same font size | Satheesh | Complete
market analysis | property sale in the area - for average price please make sure the price is formatted and add £ symbol | Rijo | Complete
on market comparable | if sqft is not available, instead of 0 sqft please show - or n/a | Rijo | Complete
| option to edit boundaries boundary lines missing for some address | Jinto | In Progress |  | 2024-08-01
planning application | the description and address sometimes gets overlapped ort cropped off 931E, Romford Road, London, Newham, London, E12 5JT https://tinyurl.com/25gs8hh9 | Satheesh | Complete | Medium
about us | change the color of the name to black https://tinyurl.com/2d7x4bna |  | Complete
| when the report has been generated change the text to Report Generated |  | Complete
floor plan | floor plan needs to be centered |  | Complete
primary school | move the address to the right below the first line, so it looks aligned | Satheesh | Complete
secondary school | move the address to the right below the first line, so it looks aligned | Satheesh | Complete
property type analysis > avg price changes in the area | the tags are overlapping with the numbers https://tinyurl.com/22hyqzzz | Satheesh | Closed |  |  |  | graph cannot be changed
crime rate | the data is overlapping with the numbers and months https://tinyurl.com/2xrfzek6 | Satheesh | Closed |  |  |  | graph cannot be changed
first page | report status should be according to the current property status if the property is withdrawn, it should show Withdrawn stc - STC under offer off market | Rijo | Not Started
| is 'Go to contents' needed in all the pages? it's not linked |  | Complete
rental comparable | center the page title |  | Complete
additional property comparable | center the page title |  | Complete
sold comparable | center the page title |  | Complete
on market comparable | center the page title |  | Complete
tenure | remove _ from Share of Freehold | Rijo | Complete
key features | change Market price to Current Market Price | Rijo | Complete
primary and secondary school | spelling error for some texts Pupils HAS NURSERY | Rijo | Complete
primary and secondary school | in the map legend, show Requires Improvement | Rijo | Complete
rental comparable | the bed icon is not aligned properly | Satheesh | Complete
content | change to Secondary Schools | Rijo | Complete
key features | last sold price - please make sure the price is formatted; separated with , | Rijo | Complete
epc | energy rating when we compare to the epc page 20, Draper Way, Norwich, Norfolk NR5 9NA | Rijo | Complete
epc | property type is given as House | Rijo | Complete |  |  |  | Data type provided through EPC API data
report generation | in the comparables pop up, change the count accordingly in the text Please select up to 10 properties to include in the report. If no properties are chosen, comparable properties will not be displayed in the report. | Sharan | Complete |  |  |  | staging
report preview | got an error page 22, Otters Reach, Kennington, Oxford, Oxfordshire OX1 5QL https://stage.devidiamober.com/report-preview-new/8457 | Rijo | Complete
property image | if image is not available for the address, it shows a blank page with just the title | Rijo | Complete
report generation | when we click on the OK button in the alert pop up, it scrolls to the bottom | Sharan | Complete |  |  |  | staging
report generation | when generating seller report, after clicking on the Generate report button the comparable pop ups are again shown | Sharan | Complete |  |  |  | staging
market analysis | avg rent price - £ is missing | Rijo | Complete
report generation | about us and report content page was not selected but it's still shown in the report | Sharan | Complete
| change supplies to Supply | Rijo | Complete
first page | remove the line in the side | Rijo | Complete
| os map missing | Sharan - Rijo | Complete
key details | even if we enable utility supply it's shown as No | Sharan | Complete |  |  |  | staging
property image | if no image is available, please hide the page | Rijo | Complete
epc page | epc rating issue - energy rating, wording, current efficiency | Rijo | Complete
epc page | floor height - add the unit | Rijo | Complete
epc page | inspection date - change date format | Rijo | Complete
sold price | remove marker | Rijo | Complete
neighbouring planning | increase count to 14 | Rijo | Complete
sold comparable | style issue increase image size | Rijo | Complete
additional property comparable | style issue increase image size | Rijo | Complete
on market comparable | style issue increase image size marker missing | Rijo | Complete
rental comparable comparable | style issue increase image size | Rijo | Complete
universities | for red marker - show 2 and 1 stars Gray - no rating | Rijo | Complete
crime rate | change text to Crime rate in postcode | Rijo | Complete
crime rate | show the data in boxes like the rest of the pages | Rijo | Not Started
census data | style issue - the % is sometimes shown in the next line, the graphs can be moved to the side so it gets aligened properly | Rijo | Complete
hospitals | gap needed between the address columns | Rijo | Complete
hospitals | response times C1, C1T etc show as tabs spacing | Rijo | Complete
Carbon footprint | change page title to Carbon Footprint & connectivity | Rijo | Complete
last page | remove the dummy logos below the email address | Rijo | Complete
first page | when the address is in multiple lines, the email address overlaps https://tinyurl.com/2y3vjytg | Rijo | Complete
sold price on street | style issue increase image size | Rijo | Complete
universities | not rated is not shown, it gets cropped | Rijo | Complete
transportation | the address sometimes overlap the marker 47, GLEBE ROAD, HARROGATE, NORTH YORKSHIRE, HG2 0LZ FLAT 4, 2, SOUTH DRIVE, HARROGATE, NORTH YORKSHIRE, HG28AU https://tinyurl.com/2a4luds https://tinyurl.com/2ysldzns | Rijo | Not Started
census data | the graphs look a little blurry in the sides | Rijo | Not Started
population | the graphs look a little blurry in the sides | Rijo | Not Started
property summary | the marker is too small and also the map looks a bit stretched | Rijo | Complete
epc page | inspection date is shown as - | Rijo | Complete
last page | even if the hospital page isn't selected, in the report last page the response time section is shown | Sharan | Complete
report for price reduced property | for price reduced property, are we showing the price redcued section in the report? |  | Discuss
content | even if property image is not available, it is shown in the content page | Sharan | Testing
additional property comparable | the marker colors on the map and listing are different also the count is not correct |  | Not Started
universities and college | in the title, the icon and heading is not aligned | Satheesh | Not Started | Low

## Design Changes
DATE | MODULE | DESCRIPTION | ASSIGNED TO | STATUS | COMMENTS
2024-02-29 | Dashboard | property report and summary buttons, is there any change in the button color? http://tinyurl.com/26penoxk | Satheesh | CLOSED
2024-02-29 | Dashboard | when we click on "What's New" the text color changes http://tinyurl.com/25djudfh | Satheesh | CLOSED
2024-02-29 | Report | report history section reduce the action button size and make the buttons round http://tinyurl.com/2562s3hj | Satheesh | CLOSED
2024-02-29 | Report | * reduce the text size above search bar * few of the button colors are not same as the rest of the pages * reload button not round http://tinyurl.com/24m4bna6 | Satheesh | CLOSED
2024-02-29 | Report | * color shown when toggles are enabled - http://tinyurl.com/2awrbah5 | Satheesh | CLOSED
2024-02-29 | Report | comparables pop ups - select button color - http://tinyurl.com/2coz7yg2 | Satheesh | CLOSED | please confirm if this is the color being used?
2024-02-29 | Report | Dynamic Report Link pop up - https://tinyurl.com/275sk6jr make the copy url button round toggle button - color shown when it's enabled | Satheesh | CLOSED
2024-02-29 | Outcodes | icons are too big - http://tinyurl.com/23wtnf55 | Satheesh | CLOSED
2024-02-29 | Listing Page | texts and toggle button is too big | Satheesh | CLOSED
2024-02-29 |  | footer remains at the bottom of the page, sticky footer | Satheesh | NOT STARTED
2024-02-29 | Detail Page | * title - font size is too big, please make it a bit smaller * bedroom, bathroom and type looks congested and doesn't look aligned * R and Z icons and the count doesn't look good, too close to the text Platform http://tinyurl.com/223aj68x | Satheesh | CLOSED
2024-02-29 | Detail Page | buttons after the property has been added to campaign is too light and difficult to see http://tinyurl.com/27hexdtw | Satheesh | IN PROGRESS
2024-02-29 | Detail Page | sub- texts are too small and light, difficult to see http://tinyurl.com/2xvgs7hd | Satheesh | NOT STARTED
2024-02-29 | Probate Detail | Check Deceased Will and View More button are too big | Satheesh | CLOSED
2024-02-29 | Probate Detail | sub- texts are too small and light, difficult to see make it similar to executor section | Satheesh | NOT STARTED
2024-02-29 | Probate Detail | buttons after the property has been added to campaign is too light and difficult to see | Satheesh | CLOSED
2024-02-29 | Letter management | planning tab looks cropped https://tinyurl.com/25mr8u2z | Satheesh | NOT STARTED
2024-02-29 | Letter management | Does the tab height need to be this tall? https://tinyurl.com/242t5eec | Satheesh | IN PROGRESS
2024-02-29 | Letter management | color when the toggle is enabled https://tinyurl.com/22zos2gm | Satheesh | CLOSED
2024-02-29 | Dashboard | Campaigns ¦ Last 30 Days please make sure the colors used for the campaigns are same | Satheesh | IN PROGRESS | not changed please compare the colors used in Campaign Insight ¦ Last 90 Days and summary page
2024-02-29 | Summary | color used for targeted and report url is the same | Satheesh | IN PROGRESS
2024-02-29 | Summary | please confirm the colors used for Anniversary and Planning, in the dashboard for planning blue is used but in summary blue is used for Anniversary | Satheesh | IN PROGRESS
2024-02-29 | Summary | spelling error - please change to TOTAL INSTRUCTIONS RECEIVED | Rijo | IN PROGRESS
2024-02-29 | Active Buyer | property list - can this pop up be a bit better https://tinyurl.com/29jebxyq | Satheesh | IN PROGRESS
2024-02-29 | Active Buyer | can the boxes be made uniform https://tinyurl.com/23mn5mne | Satheesh | IN PROGRESS
2024-02-29 | Listing Page | clear filter button is a bit light | Satheesh | CLOSED
2024-02-29 | Listing Page | pagination color | Satheesh | CLOSED
2024-02-29 | Detail Page | listing activity - pagination color | Satheesh | CLOSED
2024-02-29 | Listing Page | outcodes dropdown - please change the color for selected outcode a bit different when compared to the rest | Satheesh | NOT STARTED
2024-02-29 | Live Campaign | Does the tab height need to be this tall? https://tinyurl.com/279oc3eb | Satheesh | NOT STARTED
2024-02-29 | 20-20 Campaign | Neighbour Properties list - the selected address color https://tinyurl.com/2dz6fhxb | Satheesh | NOT STARTED
2024-02-29 | 20-20 Targeted Campaign | Neighbour Properties list - the selected address color https://tinyurl.com/2dz6fhxb | Satheesh | NOT STARTED
2024-02-29 | Campaign History | detail page - Delivery Status button not round https://tinyurl.com/2bc58nmv | Satheesh | IN PROGRESS
2024-02-29 |  | Hide Column dropdown - when we hover over the options please change the color https://tinyurl.com/2y3bge3x | Satheesh | CLOSED
2024-02-29 | Anniversary Letter | toggle button color when enabled https://tinyurl.com/28rxmvny | Satheesh | CLOSED
2024-02-29 | Anniversary Letter | text in the banner - can be shown within the full box, do we need the blank space there? https://tinyurl.com/296wk5kk | Satheesh | CLOSED
2024-02-29 |  | info button - needs to match the new color theme and make it a bit more neater https://tinyurl.com/24eowbqy | Satheesh | CLOSED
2024-02-29 | Quick Send | quick send list - color of the select button | Satheesh | NOT STARTED
2024-02-29 | Report | when downloading the report should we show a message saying reports are being downloaded, please check in downloads? | Rijo | NOT STARTED
2024-03-01 | Report | Selected property - can this section be a bit more nicer? the texts are a bit light https://tinyurl.com/2ac569v7 | Satheesh | NOT STARTED
2024-03-01 | Report | Edit Sections on Generated Report - if any of the sections are not selected, the texts are a bit light https://tinyurl.com/272tktg9 | Satheesh | NOT STARTED
2024-03-01 | Settings | edit profile - toggle for Mobile Number to Send Notification is too big and not aligned properly, please change the color when the toggle button is enabled https://tinyurl.com/2dgzr3hz | Satheesh | CLOSED
2024-03-01 | Wallet | pagination section color | Satheesh | CLOSED
2024-03-01 | Settings | sidepanel data - toggle buttons are too big and not aligned properly, please chnage the color when the button is enabled https://tinyurl.com/22w9etqx | Satheesh | CLOSED
2024-03-01 | Settings | placeholder texts - please make a bit darker | Satheesh | NOT STARTED
2024-03-01 | Probate | reduce the toggle button size | Satheesh | NOT STARTED
2024-03-01 | Listing Page | filtered by section - please make the text a bit darker | Satheesh | NOT STARTED
2024-03-01 | Probate Detail | please make the texts a bit smaller - name, addresses | Satheesh | NOT STARTED
2024-03-01 | Probate Detail | should we separate last sodl date and last sold price? it's currently shown in Details of the deceased section | Rijo | CLOSED
2024-03-01 | Probate Detail | placeholder texts for details of the deceased and executor section, please make it similar https://tinyurl.com/24mc6cf9 | Satheesh | NOT STARTED
2024-03-01 | Detail Page | please make sure the back button is aligned and looks centered https://tinyurl.com/2apo2l5p | Satheesh | NOT STARTED
2024-03-01 | Detail Page | Contacted property pop up shown when we click on quick send reduce the width of the popp up color shown when we hover over Yes button https://tinyurl.com/2yw7tbvy | Satheesh | NOT STARTED
2024-03-01 | Detail Page | when we click on the image, to view it fully we need to scroll | Satheesh | NOT STARTED
2024-03-05 | Report | please reduce the toggle button size https://tinyurl.com/yrdthzna | Satheesh | NOT STARTED
2024-03-05 | Report | Dynamic Report Link pop up - reduce the toggle button size https://tinyurl.com/yvc78zo5 | Satheesh | NOT STARTED
2024-03-05 | Outcodes | if no outcodes are selected by the user please hide the Requested outcodes section only once the user chooses an outcode show the section | Rijo | COMPLETED
2024-03-05 | Listing Page | reduce toggle button size | Satheesh | NOT STARTED
2024-03-05 | Letter management | please use uniform colors for the campaign tabs - please refer the dashboard | Satheesh | NOT STARTED
2024-03-05 | Summary | please make sure the boxes are aligned https://tinyurl.com/ymcm4can | Satheesh | NOT STARTED
2024-03-05 | Anniversary Letter | addresses are not clickable, do we need to show it in blue and underlined ? | Satheesh | NOT STARTED
2024-03-05 | Anniversary Letter | sent history button - pleae make it round | Satheesh | NOT STARTED
2024-03-05 |  | toggle buttons in all the pages are too big, please reduce the size | Satheesh | NOT STARTED
2024-03-05 | Listing Page | do we need to show the button in a dialog box when we hover over the address? | Rijo | NOT STARTED
2024-03-05 | Letter management | create letter - please make sure the text and toggle button is aligned properly https://tinyurl.com/ywvg3yvn | Satheesh | NOT STARTED
2024-03-05 | Active Buyer | please show Find Company button in the same line as Properties Transacted in the Last Twelve Months https://tinyurl.com/ykqp2lnk | Satheesh | NOT STARTED
2024-03-05 | Probate Detail | buttons not aligned properly https://tinyurl.com/248kc5pu | Satheesh | COMPLETED
2024-03-27 | Dashboard | the texts in the banner are a little cropped https://tinyurl.com/27vfsu3m
2024-03-27 | Detail Page | rent and deposit prices are shown in multiple lines https://tinyurl.com/2bmozdks
2024-03-27 | Summary | total instructions received - spelling error
2024-03-27 | Summary | no. of entries are not aligned properly https://tinyurl.com/2cz5o95v
if no outcodes are selected by the user please hide the Requested outcodes section only once the user chooses an outcode show the section

## Letsbid Enhancement
Task | Sub Task | Task Type | Status | Assigned To | Expected Duration | Start Date | End Date | Notes
Lettings report revamp | Report Generation Tool Agent Details & Customise Report Page realign the form | Task | Complete | Sharan | 6 hrs | 2024-08-06 | 2024-08-06
| Report pdf FIRST PAGE ABOUT US REPORT CONTENT -- 4 hrs PROPERTY SUMMARY KEY DETAILS PROPERTY IMAGES FLOOR PLAN EPC -- 8 hrs SOLD PRICES ON STREET PLANNING DATA OF PROPERTY NEIGHBOURING PLANNING HISTORY MARKET ANALYSIS PROPERTY TYPE ANALYSIS -- 8 hrs PROPERTY COMPARABLES ON MARKET PROPERTY COMPARABLES ON MARKET RENTAL COMPARABLES NEAREST PRIMARY SCHOOLS -- 8 hrs NEAREST SECONDARY SCHOOLS UNIVERSITIES AND COLLEGES TRANSPORTATION LINKS CRIME RATE AND POPULATIONS CENSUS DATA -- 8 hrs NEAREST HOSPITAL / GP / DENTIST / NHS CARBON FOOTPRINT CONNECTIVITY -- 4 hrs | Task | Complete | Sharan | 6 days
| Testing | Task | Not Started | Sharan | 3 days
Draw/edit boundary of property |  | Task | Complete | Jinto
on market probate |  | Task | Not Started
Postcard | postcard intergration with Stannp | Task | In Progress
| postcard content/trigger management Create, Edit, View Postcard (Based on triggers) 20-20 20-20 targeted | Task | In Progress
| Create Postcard based on selected property details and selected postcard trigger View and Edit Postcard 20-20 20-20 targeted | Task | In Progress |  |  |  |  | for 20-20 targeted - View and Edit Postcard : Blank Validation Pending (like no address, no images etc)
| dashboard & summary | Task
| history section | Task
| Toggle for letter and postcard sending - user will have the option to either send a postcard or do a normal campaign (local print or bulk mail) | Task | Not Started
| Update and test bulk mail sending | Task | Not Started
| Testing | Task | Not Started
Report improvements https://docs.google.com/document/d/1lnXeye92-qO-j35tXrPSwm1WDM0qKAsgtIsD_n9--4Y/edit?usp=sharing | reports are taking time to donwload | Issue | Complete | Sharan
| All comparables need details page | Task | Not Started | Sharan
| already selected properties should remain even if users filter * if user has selected properties, those properties will be listed above if the user filters the comparables | Task | Not Started | Sharan
| sorting for all columns seperate button | Task | Not Started | Sharan | 4hrs
| Selected values must me in bold in comparable filter | Task | Not Started | Sharan
| multiple page check box - comparable | Task | Not Started | Sharan
| sold on street - the same address is shown, but the format is different mostly in case of flats | Task | Not Started | Sharan
| in the comparable pop ups, if the user selects more than the maximum count show a pop up saying they can only select 8/10 comparables to display in report | Task | Complete | Sharan | 4hrs
| Front page for off market properties should be our map for standard and agents should have options to use that as standard | Task | Complete | Rijo
| Properties are expandable with Information if we have any like floorplans/images/detail page etc | Task | Not Started | Sharan | 6hrs
Comparable tool | Multiple page export | Task | Not Started | Sharan
| when we go into the property detail page of an on market property and click on the back button, all the filters selected and input given by the user is cleared and they will have to select it again | Issue | Not Started | Sharan
| remains at the bottom when we click on next or previous button | Issue | Not Started
Detail page enhancement | probate | Task | In Demo/Staging | Sandeep
| targeted | Task | In Demo/Staging | Sandeep
| active buyer | Task | In Demo/Staging | Sandeep
| new homes | Task | Discuss | Sandeep |  |  |  | need to confirm if detail page is needed for planning application
| display comparables in detail page | Task | In Demo/Staging | Sandeep
| Display extra info in the detail page | Task | Not Started
| Bring in the extra info in report | Task | Not Started | Sharan
UI improvements | design for detail page to display extra info | Task | Not Started
| extra page for report to display extra info | Task | Not Started | Satheesh
| go through Letsbid and give suggestions on how it can be made better - create a report | Task | Not Started | Satheesh |  |  |  | https://docs.google.com/document/d/1l_NVAtuB9QeFHN2NydRZIp1h4QzPDMSBbN8tklDHznY/edit?usp=sharing
Letter management | AI generated content
Performance improvement | reduce listing page loading time | Task | Not Started | Jinto
| loading dashboard – load page and then load each Api for faster performance | Enhancement | Testing | Sandeep
| report generation - compression of image / pdf | Task | Not Started | Jinto
Auction issues |  | Task
Property controller Query checks and Optimization |  | Enhancement
Unwanted resources and queries |  | Enhancement
Coding standard | sublime text editor need to be used with plugin (such as lint, etc.) that will auto identify code issue | Enhancement
Log checking |  | Task
Responsive interface |  | Enhancement
Web view for reports |  | Enhancement
GIT for frontend
Campaign enhancement | Increase letter sending limit | Enhancement
| Card saving feature | Task
| Pagination in campaign | Task
Probate | address correction | Enhancement
| improve code | Enhancement
Management tool |  | Enhancement | Discuss
Automation tool |  | Enhancement | Discuss
Change frontend technology |  | Enhancement | Discuss
Project documentation |  | Task | Not Started | Rishika
Server check |  | Task |  | Jishnu |  |  |  | https://docs.google.com/document/d/1bkvDtENAgbYagowdg9GkUFfesIsbp1INPSc816ZjStk/edit?usp=sharing
APIs used in report

## Website Issues
Task No | Reported Date | Task Type | Page | Description | Assigned | Status | Priority | Expected Duration | Start Date | End Date | Comments
2 | 2024-08-05 | ISSUE |  | on clicking on the instagram icon, it shows something went wrong please make sure it's linked to the correct page |  |  | HIGH
3 | 2024-08-05 | SUGGESTION |  | change the twitter icon to the new logo
4 | 2024-08-05 | SUGGESTION |  | facebook icon is missing in the header
5 | 2024-08-05 | SUGGESTION |  | in the menu the current page is not highlighted in the menu
6 | 2024-08-05 | ISSUE |  | update a new report as the sample report | RIJO | NOT STARTED | URGENT
7 | 2024-08-05 | ISSUE |  | when we click on Auction in the menu it redirects to the homepage, it shouldn't be linked need to show the dropdown | RIJO | NOT STARTED | MEDIUM
8 | 2024-08-05 | SUGGESTION | Auction platform | stop auto play of video
9 | 2024-08-05 | ISSUE | https://letsbidproperty.co.uk/expired_listing.php | when we click on Back to Search button it redirects to the search property page
10 | 2024-08-05 | SUGGESTION | https://letsbidproperty.co.uk/expired_listing.php | please change the message shown in the expired listing page to: The property you're interested in has expired. Please feel free to explore other listings.
11 | 2024-08-05 | ISSUE | auction listing > find agent | enter postcode/area - This Postcode Only text gets cropped https://tinyurl.com/22d8hb89
12 | 2024-08-05 | ISSUE | https://letsbidproperty.co.uk/cont-thank.php | when we click on the back button in the thank you page, please make sure the contact form is cleared when user returns to the contact page
13 | 2024-08-05 | ISSUE | customer login | when we click on Forgot Password, it shows 404 page | RIJO | NOT STARTED | HIGH
14 | 2024-08-05 | SUGGESTION | news & blogs | sort the blogs from the latest date | SATHEESH | NOT STARTED | LOW
15 | 2024-08-05 | SUGGESTION | news & blogs detail page | back button is only shown at the bottom of the page, do we need one at the top also? | SATHEESH | NOT STARTED | LOW
16 | 2024-08-05
18 | 2024-08-04 | ISSUE | Estate Agent Login | need to remove html tage under forgot password mail https://drive.google.com/file/d/1V0ZpHg_VQkYyzxL0FJlCnuX6Sk9Ho1DS/view?usp=drive_link | RIJO | NOT STARTED

## Letsbid - Auction
# | Date | Type | Description | Reported By | Assigned | STATUS | Priority | Expected Duration | Start Date | End Date | Comments
1 | 2023-06-29 | ISSUE | Logo black issue for gr estates and 2 northwood accounts | Rosie | Rijo | COMPLETED | HIGH |  | 2023-06-29 | 2023-06-29
2 | 2023-06-29 | ISSUE | expiry of auction broken | Rosie | Rijo | COMPLETED | HIGH |  | 2023-06-29 | 2023-06-29
3 | 2023-06-29 | ISSUE | auction detail page broken for smaller screens | Rosie | Rijo | COMPLETED | HIGH |  | 2023-06-29 | 2023-06-29
4 | 2023-06-29 | ISSUE | broken theme when filtering from dropdown | Rosie | Nikhila | COMPLETED | HIGH |  | 2023-05-19 | 2023-05-26
5 | 2023-06-30 | ISSUE | new entries not seen | Rosie | Nikhila | COMPLETED | HIGH |  | 2023-07-01 | 2023-07-01
6 | 2023-06-29 | ISSUE | auction image blured | Rosie | Rijo | COMPLETED | HIGH |  | 2023-06-29
7 | 2023-07-03 | ISSUE | filter section design breaks when we select Commercial in property type https://tinyurl.com/24o5csdk | Rishika | Nikhila | COMPLETED | HIGH
8 | 2023-07-03 | SUGGESTION | in the listing page, if the property has expired the text 'expired on' is shown twice https://tinyurl.com/2dxcx3b3 | Rishika | Nikhila | COMPLETED | HIGH
9 |  | TASK | AML API work |  | Nikhila | COMPLETED | HIGH |  | 2023-04-13 |  | testing links and credentials provided for AML testing
10 | 2023-07-03 | ISSUE | logo background is black Medway Premier Homes Keystone Luton Estate Agents Rocket Estate Agents My Move Estate Agents C James Rolitex Estates Kings Group LLP | Rishika | Rijo | NOT STARTED | MEDIUM
11 | 2023-07-03 | ISSUE | find agent - if user searches without entering the location by default the location shown in the search result page is Abbey Hey, Gorton https://tinyurl.com/2229tjmn | Rishika | Nikhila | COMPLETED | MEDIUM
12 | 2023-07-04 | TASK | upload listing - on clicking submit there should be a payment option - only after paying the property will be listed on the website also there will be an option to enter a code, upon entering the code it will be free to list property -> expiry date, individual codes for agents, weekly code | Rishika | Nikhila | NOT STARTED | MEDIUM |  |  |  | need to speak to Nikhila
13 | 2023-07-10 | TASK | option to expiry add time in the property listing and edit it in coutdown timer in listing and detail page | Rosie | Nikhila | COMPLETED | MEDIUM
14 | 2023-07-19 | TASK | change auction end date & time after it has been listed | Rosie | Nikhila | COMPLETED | MEDIUM
15 | 2023-07-19 | TASK | To extend the end of the auction automatically by a minute or more if largest bid automatically | Rosie | Nikhila | COMPLETED | MEDIUM |  |  |  | works when the bid is placed from the property detail page but when a higher bid is placed from the bid page in customer account the end time does not extend
16 | 2023-07-19 | TASK | To set a minimum bid amount for every bid, i.e. £500, £1000 etc | Rosie | Nikhila | COMPLETED | MEDIUM |  |  |  | it works correctly on the property detail page. However, on the bids page within the customer account, users can place bids without adhering to the minimum bid multiple.
17 | 2023-07-19 | ISSUE | The set end time and date box he completes before he lists does not always work and his listings default to the day and time of the posting. | Rosie | Nikhila | COMPLETED | HIGH
18 | 2023-07-19 | TASK | Agents need to be able to change the price during the auction | Rosie | Nikhila | COMPLETED | MEDIUM
19 | 2023-07-19 | TASK | Agents should be able to edit the auction listing , for example they have listed a property and noticed a couple spelling errors. Instead of being able to edit the lsiting he has had to remove it and re upload the whole lisitng. | Rosie | Nikhila | COMPLETED | MEDIUM
20 | 2023-07-19 | ISSUE | Dom has uploaded a new document on two separate live listings and the end time and date in each listing has been affected | Rosie | Nikhila | COMPLETED | HIGH
21 | 2023-07-20 | ISSUE | agent approval mail - logo is not shown | Rishika | Nikhila | COMPLETED | MEDIUM
22 | 2023-07-20 | ISSUE | in the detail page the property images are shown multiple times https://prnt.sc/7fBWZrL1i_G0 | Rishika | Nikhila | COMPLETED
23 | 2023-07-20 | ISSUE | detail page - if the agent has added multiple documents, the buttons are not spaced properly https://prnt.sc/1exgYVTELXiH | Rishika | Nikhila | COMPLETED
24 | 2023-07-20 | ISSUE | detail page - the enquiry form in the detail page does not work, when we submit the user is redirected to the home page | Rishika | Nikhila | COMPLETED | HIGH
25 | 2023-07-20 | ISSUE | arrange viewing form in detail page - when we select a time the tick is not shown properly, the design doesn't look right https://prnt.sc/Bf_kyD-ERxmn only if we click on it twice it's shown properly | Rishika | Nikhila | COMPLETED | MEDIUM
26 | 2023-07-20 | ISSUE | arrange viewing form in detail page and also in the listing - all the days are shown even if the agent has not selected a time https://tinyurl.com/2ecxtm9k https://prnt.sc/6qYivBCO38GZ | Rishika | Nikhila | COMPLETED | HIGH
27 | 2023-07-20 | ISSUE | arrange viewing form in detail page - not able to submit even after accepting captcha | Rishika | Nikhila | COMPLETED | HIGH
28 | 2023-07-20 | SUGGESTION | https://letsbidproperty.co.uk/res-cust.php - please make sure all the external links open in a new tab | Rishika | Nikhila | COMPLETED
29 | 2023-07-20 | ISSUE | when editing a property, the date available field becomes blank | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | https://tinyurl.com/2779wulx the date available field becomes blank
30 | 2023-07-20 | ISSUE | when editing a property, the format of date available field is not correct when editing | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | https://tinyurl.com/2779wulx the date format changes when editing
31 | 2023-07-27 | TASK | if someone has outbid a customer send an email to them A higher offer has been made on the listing you have bid on. Please login to make a further bid. *login link* | Rishika | Nikhila | COMPLETED | MEDIUM
32 | 2023-07-28 | ISSUE | if the user uploads multiple files for one document, the download button is not aligned properly eg: if we upload 5 documents for Legal Contract it's not aligned properly - https://tinyurl.com/2ak7vsgq | Rishika | Nikhila | COMPLETED | MEDIUM
33 | 2023-07-28 | SUGGESTION | detail page > download tab - add space between 2 buttons in a row https://tinyurl.com/2axsy5ak | Rishika | Nikhila | COMPLETED | MEDIUM
34 | 2023-07-28 | ISSUE | agent account - when adding or editing a listing, if the user had checked not applicable for any of the documents when editing it is not shown all the checkboxes are blank | Rishika | Nikhila | COMPLETED | MEDIUM
35 | 2023-07-28 | ISSUE | if the estate agent has rejected a customers bid, the customer should be able to place a new bid from the detail page | Rishika | Nikhila | COMPLETED | MEDIUM
36 | 2023-07-28 | ISSUE | if the agent deactivates a listing and then adds it back onto the listing after clearing the previous bids, in the detail page the previous bids are not cleared | Rishika | Nikhila | COMPLETED | MEDIUM
37 | 2023-08-11 | ISSUE | property detail page - date available format is not correct after the agent edits the property https://tinyurl.com/2d39kx2r | Rishika | Nikhila | COMPLETED | MEDIUM
38 | 2023-08-11 | ISSUE | arrange viewing form shown when we click on the mail icon in listing page - checkboxes are shown for all the dates https://tinyurl.com/297fc7ox please make it similar to the detail page | Rishika | Nikhila | COMPLETED | MEDIUM
39 | 2023-08-11 | ISSUE | notification - only the property image is shown, the texts are not shown https://tinyurl.com/2axu7zho | Rishika | Nikhila | COMPLETED | HIGH
40 | 2023-08-11 | ISSUE | arrange view form - Thursday is missing please check in property detail page and form shown when we click on the mail icon in listing page https://tinyurl.com/23dk2lc3 | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | there is no column for Thursday in arrange viewing form
41 | 2023-08-11 | ISSUE | if user clicks on Place bid button without logging into their account, in the pop up shown buttons are not proper https://tinyurl.com/2xtpwsg8 | Rishika | Nikhila | NOT STARTED | MEDIUM
42 | 2023-08-16 | ISSUE | in all mails with pound symbol needs to be corrected to the proper symbol | Rosie | Nikhila | COMPLETED | HIGH
43 | 2023-08-21 | TASK | add a button so the users can see all properties listed |  | Nikhila | COMPLETED | MEDIUM
44 | 2023-08-22 | TASK | remove Rent option while uploading listing | Rosie | Nikhila | COMPLETED | HIGH
45 | 2023-08-22 | TASK | confirmation after placing bid - show a second pop up asking them to confirm the bid amount | Rosie | Nikhila | COMPLETED | MEDIUM
46 | 2023-08-22 | TASK | if someone has outbid a customer, they should have the option to place a higher bid | Rosie | Nikhila | COMPLETED | HIGH
47 | 2023-08-22 | TASK | in the pop up shown after clicking on place a bid button - the auction time remaining and show the highest bid in the pop up | Rosie | Nikhila | COMPLETED | HIGH
48 | 2023-08-22 | TASK | show the count of people interested or that have favourited the property | Rosie | Nikhila | NOT STARTED | LOW
49 | 2023-08-22 | TASK | extend the end of the auction automatically by a minute or more if someone places the largest bid in the last 5min | Rosie | Nikhila | COMPLETED | HIGH
50 | 2023-08-22 | TASK | add a refresh button/pop up in the detail page to refresh the page before the auction ends | Rosie | Nikhila | COMPLETED | MEDIUM
51 | 2023-08-22 | TASK | date available is given as 01/01/1970 in the detail page if no date is given | Rosie | Nikhila | COMPLETED | HIGH
52 | 2023-08-22 | TASK | send a mail to notify the user that the auction has ended | Rosie | Rijo | COMPLETED | MEDIUM
53 | 2023-08-22 | TASK | when a counter offer is put forward, if the bidder agrees to go to that amount and the agents accept it there is no email sent to the bidder to let them know its been accepted. | Rosie | Nikhila | COMPLETED | MEDIUM |  |  |  | confirm content
54 | 2023-08-22 | TASK | There is no option for the agents to reorder the photos | Rosie | Nikhila | COMPLETED | MEDIUM
55 | 2023-08-22 | TASK | change the mail received after someone places a higher bid Hi *Name*, Please sign in to your profile as you have a bid pending on your property *Address*. Click here to view the property. Guide Price: Your Current Bid: Highest Bid: Thank you, Lets Bid Team | Rosie | Nikhila | COMPLETED | MEDIUM
56 | 2023-08-22 | SUGGESTION | in place a bid pop up please make sure the highest bid price is separated properly i.e use a comma to separate groups of thousand | Rishika | Nikhila | COMPLETED | LOW
57 | 2023-08-23 | SUGGESTION | confirmation pop up after placing a bid * before the price please add the £ symbol * place ? at the end of the sentence - Are you sure you want to bid £*price*? * pop up design is different, can it be made similar to the current pop up * please make sure the price is separated properly i.e use a comma to separate groups of thousand | Rishika | Nikhila | COMPLETED | LOW
58 | 2023-08-23 | DISCUSS | Should the property be listed as available in the system after an agent accepts a bid before the scheduled time is completed? and also can other bidders place bids on the property?
59 | 2023-08-23 | ISSUE | in the mail received after counter offer has been accepted - please make the first letter of accepted small. Hi *Name*, Counter bid has been Accepted Property: test property Click here to view the property. Guide Price: £ Bid: £ Thank you, Lets Bid Team | Rosie | Nikhila | COMPLETED | MEDIUM
60 | 2023-08-24 | TASK | in dashboard section when you go to bid as a customer there is nothing to say what the current highest bid is. | Rosie | Nikhila | COMPLETED | HIGH
61 | 2023-08-24 | TASK | option to allow people to bid under current highest amount or not to. This can be done when they go to set the listing up | Rishika | Nikhila | COMPLETED | HIGH
62 | 2023-09-01 | TASK | Proxy Bids | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | please check https://docs.google.com/spreadsheets/d/1WjnUjBmxpyUdjSZ_jo_ebfFABn2g78Pkl4hRvaLRBlg/edit#gid=950164408&range=74:75
63 | 2023-09-01 | TASK | Button where agents have the option to allow bidding to start | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | change the text for pop up
64 | 2023-09-01 | ISSUE | if we enable view all property and then sort the listing, the results shown are for the initial search | Rishika | Nikhila | NOT STARTED
65 | 2023-09-01 | ISSUE | arrange viewing form - the checkboxes are not shown for Morning, the design is not the same as the rest https://tinyurl.com/2d92kl9g | Rishika | Nikhila | COMPLETED
66 | 2023-09-01 | ISSUE | arrange viewing form - no checkbox is shown if the viewing time selected for Friday is morning https://tinyurl.com/25oywn9s | Rishika | Nikhila | COMPLETED
67 | 2023-09-01 | ISSUE | confirmation pop up after placing a bid - please remove comma between sure and you Are you sure you want to bid £*price*? | Rishika | Nikhila | COMPLETED
68 | 2023-09-01 | ISSUE | not getting any mails after placing bids and also after submitting the contact forms | Rishika | Nikhila | COMPLETED | HIGH
69 | 2023-09-04 | TASK | testimonial page | Rishika | Nikhila | COMPLETED | HIGH |  | 2023-09-04
71 | 2023-09-07 | TASK | change the video in testimonial page and homepage | Rishika | Nikhila | COMPLETED
72 | 2023-09-26 | TASK | add Buyers Guide underneath auction brochures | Rijo | Rijo | COMPLETED
73 | 2023-10-09 | TASK | plugin for multiple image upload |  | Nikhila | COMPLETED | MEDIUM
74 | 2023-10-18 | TASK | please add Your Maximum Bid: below Highest Bid in the pop up the max bid should be shown only for that account | Rishika | Nikhila | NOT STARTED | MEDIUM
75 | 2023-10-18 | ISSUE | please make sure that 2 customers cannot give the same Maximum bid amount, if the customer is adding max bid which has already been added show a message Please provide a different Maximum Bid Amount | Rishika | Nikhila | COMPLETED | MEDIUM
76 | 2023-10-18 | ISSUE | the previous bids are shown in Current Bid pop up when a new bid is placed | Rishika | Nikhila | COMPLETED | MEDIUM
77 | 2023-10-30 | ISSUE | not able to submit bid without entering a value for max bid | Rishika | Nikhila | COMPLETED | MEDIUM
78 | 2023-11-01 | ISSUE | there is a delay in showing the success message after placing the bid | Rishika | Nikhila | COMPLETED | MEDIUM |  |  |  | please show a loader when we submit the bid
79 | 2023-11-01 | ISSUE | in the agent account in bids section, the proxy bid shown is not correct the customer name is not correct and also one proxy bid is missing https://tinyurl.com/yt3t2x3v https://tinyurl.com/yk9njqbl | Rishika | Nikhila | COMPLETED | MEDIUM
80 | 2023-11-06 | SUGGESTION | please mention near the image upload functionality that they can reorder the images by dragging it You can rearrange the images by dragging and dropping them into your preferred sequence. | Rishika | Nikhila | COMPLETED | MEDIUM
81 | 2023-11-06 | ISSUE | listing page - the image in the listing does not change even if we change the order, it shows the image which was first uploaded | Rishika | Nikhila | COMPLETED | MEDIUM
82 | 2023-11-07 | TASK | estate agent - bids section please show only the highest latest bid of the customer https://tinyurl.com/ylj7ka9b | Rishika | Nikhila | COMPLETED | MEDIUM
83 | 2023-11-07 | TASK | please show a loader when we submit the bid | Rishika | Nikhila | COMPLETED | MEDIUM
84 | 2024-01-16 | TASK | To allow customers to make a bid even when they have a "pending bid" already; For example, a customer makes their bid i.e. £126k and then goes back into the platform to increase their last bid, they can't do this currently as the below message appears to the customer: |  | Rijo | NOT STARTED | MEDIUM
85 | 2024-01-16 | TASK | To include a message in the bidding box to inform customers of the minimum bid amount the agent has set. I suggest that some wording be entered below the proxy bid box (see below); For example,where I have entered the wording below in the picture we could enter the following wording: "The minimum bid increment is £ " and what the agent sets as the minimum bid amount at the "upload your listing" stage, will show here, i.e. £2,000 http://tinyurl.com/yods7a2t |  | Rijo | NOT STARTED | MEDIUM
86 | 2024-01-16 | TASK | A message box to appear to a customer that enters a bid which is the same as the current highest bid. For example, as shown in the picture below, three people have on different days/times registered their bid of £126k on the platform. We do not wish to stop this happening but do want a pop up box to appear to inform the customer that they have bid at the same level as another customer and ask them if they would like to increase their bid. http://tinyurl.com/yvu2qmp9 |  | Rijo | NOT STARTED | MEDIUM
87 |  | TASK | share property email changes |  | Rijo | IN PROGRESS | MEDIUM
88 | 2024-02-01 | ISSUE | AML Check issue |  | Rijo | NOT STARTED | HIGH
89 | 2024-02-26 | TASK | show sold properties in the auction listing with Sold tag |  | Rijo | NOT STARTED | MEDIUM
90 | 2024-04-09 | TASK | expired listings should redirect to page stating the listing has expired |  | Rijo | NOT STARTED | HIGH | 2 days
91 | 2024-07-08 | ISSUE

## APIs
GetAddress - autocomplete | https://api.getAddress.io
GetAddress - specific address | https://api.getAddress.io
Postcode | https://api.postcodes.io/postcodes/
Crime | https://data.police.uk/api/crimes-street/all-crime
EPC | https://epc.opendatacommunities.org/api/v1/domestic/search
Land registery (Title Number, Plan & Register)
Google Satellite Map | https://maps.googleapis.com/maps/api/staticmap
GeoApify Map | https://maps.geoapify.com/v1/staticmap
NHS | https://api.nhs.uk/service-search/search-postcode-or-place
Broadband | https://api-proxy.ofcom.org.uk/broadband/coverage/
Mobile | https://api-proxy.ofcom.org.uk/mobile/coverage/
Carbon Intensity | https://api.carbonintensity.org.uk/regional/postcode/
Flood Risk | https://environment.data.gov.uk/flood-monitoring/id/floodAreas
House Price Index | https://landregistry.data.gov.uk/data/ukhpi/region/
Os Map | https://api.os.uk/maps/vector/v1
Stannp | https://dash.stannp.com/api/v1/
Company Owned | https://api.company-information.service.gov.uk/company/
Charts - Open Source Chart Image API ¦ QuickChart

## Incident Report
Incident ID | Date of Incident | Location of Incident | Description of Incident | Immediate Actions Taken | Root Cause | Corrective Actions | Responsible Person | Completion Date | Follow-Up Actions Required | Comments/Notes
1 | 2024-10-30 | Filter by weeks | stc and withdrawn properties were listed under Filter by weeks | Filter changes were reverted |  |  | Sandeep
2